## Total Cost
Year | Category | Detail | Cost ($) | Total
1st year | Developing expense | Salary | 284570 | 536570
|  | Bonus | 2000
|  | Trainning team | 10000
|  | Travel business | 5000
|  | Team building | 5000
| Risk management expense |  | 60000
| Change management expense |  | 60000
| Equipment (Hardware & Software) |  | 20000
| Facility expense |  | 20000
| Contingency expense |  | 70000
2nd and 3rd year | Maintenance | Team Maintenance | 54000 | 121500
| Training customer | 5 company * 1 month * 3 members * 50$ | 67500
4th year | Maintenance |  | 27000 | 269170
| Developing expense | Salary | 98670
|  | Bonus | 500
|  | Travel business | 1000
|  | Team building | 2000
| Risk management expense |  | 20000
| Change management expense |  | 20000
| Equipment (Hardware & Software) |  | 20000
| Facility expense |  | 20000
| Contingency expense |  | 60000

## Salary Table
Salary Table
| Position | Work Hour | Hour Rate | Total Hour | Total Cost | From (month) | To (month)
Year 1 | PM | 2 | 100 | 396 | 39600 | 4 | 12
| Developer 1 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 2 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 3 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 4 | 4 | 60 | 528 | 31680 | 6 | 11
| Architect | 3 | 150 | 132 | 19800 | 2 | 3
| Risk Manager | 2 | 75 | 88 | 6600 | 5 | 6
| Change manager | 2 | 75 | 88 | 6600 | 5 | 6
| Requirement Engineer 1 | 6 | 75 | 264 | 19800 | 4 | 5
| Requirement Engineer 2 | 6 | 75 | 264 | 19800 | 4 | 5
| Tester | 3 | 75 | 132 | 9900 | 11 | 12
| Tester | 3 | 75 | 66 | 4950 | 12 | 12
| QA | 2 | 100 | 308 | 30800 | 4 | 10
Total |  |  |  |  | 284570
Year 4 | PM | 2 | 100 | 132 | 13200 | 4 | 9
| Developer 1 | 4 | 60 | 352 | 21120 | 5 | 8
| Developer 2 | 4 | 75 | 352 | 26400 | 5 | 8
| Risk Manager | 2 | 75 | 44 | 3300 | 4 | 4
| Change manager | 2 | 75 | 44 | 3300 | 4 | 4
| Requirement Engineer | 6 | 75 | 66 | 4950 | 4 | 4
| Tester | 3 | 75 | 132 | 9900 | 9 | 9
| Tester | 3 | 75 | 132 | 9900 | 9 | 9
| Designer | 3 | 100 | 66 | 6600 | 4 | 4
Total |  |  |  |  | 98670