## SAD_TimeLog
Time Recording Log For: POS Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Thanh Giang |  |  |  | Date: | 14/5
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Inter. Time | Delta Time | Activity | Artifact | C | U | Team Meeting
1 | 2012-05-14 | 22:30 | 12:00 | 0 | 1.5 | Kick off Team meeting |  |  |  | Planning and controlling
| 2012-05-14 | 21:00 | 23:00 | 0 | 2 | Research document: Project Plan |  |  |  | Architecture Drivers
| 2012-05-15 | 20:00 | 23:00 | 0.5 | 2.5 | Write Project Plan |  |  |  | Architect Design Document
| 2012-05-16 | 20:30 | 12:00 | 0 | 3.5 | Team Meeting | Final_Project_Guidelines
| 2012-05-16 | 20:00 | 23:00 | 0.5 | 2.5 | Write Project Plan -Work Breakdown Structure
| 2012-05-17 | 20:00 | 23:00 | 0.5 | 2.5 | Draw Allocation View |  |  |  | Total: | 183.5
| 2012-05-18 | 20:30 | 12:00 | 0 | 3.5 | Team Meeting
| 2012-05-19 | 20:00 | 23:00 | 0.5 | 2.5 | Data Model
| 2012-05-20 | 20:00 | 23:00 | 0.5 | 2.5 | Context Diagrams
2 | 2012-05-21 | 9:00 | 11:00 | 0 | 2 | Team Meeting
| 2012-05-22 | 21:00 | 12:00 | 0 | 3 | Research ACDM - Project plan
| 2012-05-23 | 9:30 | 0:00 | 0 | 2.5 | Team Meeting
| 2012-05-23 | 18:00 | 23:00 | 1 | 4 | Research ACDM - Project plan
| 2012-05-24 | 13:00 | 15:30 | 0 | 2.5 | Team Meeting
| 2012-05-24 | 20:00 | 12:00 | 0 | 4 | WBS
| 2012-05-26 | 9:00 | 11:00 | 0 | 2 | Schedule
| 2012-05-27 | 19:00 | 22:30 | 0 | 3.5 | Schedule
3 | 2012-05-28 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-05-28 | 18:00 | 23:00 | 1 | 4 | Change Allocation View and description
| 2012-05-29 | 8:00 | 0:00 | 0 | 4 | Change Allocation View and description
| 2012-05-29 | 20:00 | 23:00 | 0.5 | 2.5 | Change data model and introducion to project
| 2012-05-30 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-05-31 | 21:00 | 23:00 | 0 | 3 | Write usecase
| 2012-06-01 | 9:00 | 11:00 | 0 | 2 | Write usecase
| 2012-06-01 | 21:30 | 23:00 | 0 | 2.5 | Write usecase
4 | 2012-06-04 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-06-07 | 20:00 | 23:00 | 0.5 | 2.5 | Quality Attributes
| 2012-06-08 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-06-09 | 19:00 | 21:00 | 0.5 | 1.5 | Quality Attributes
5 | 2012-06-12 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-06-12 | 20:00 | 23:00 | 0.5 | 2.5 | Read and Research ACDM
| 2012-06-14 | 13:00 | 18:00 | 1 | 5 | Read and Research ACDM
| 2012-06-14 | 20:00 | 12:00 | 0.5 | 3.5 | Read and Research ACDM
| 2012-06-15 | 20:00 | 23:00 | 0.5 | 2.5 | Team Meeting
| 2012-06-16 | 20:00 | 23:00 | 0.5 | 2.5 | Review and fix Quality Attributes
| 2012-06-17 | 20:00 | 23:00 | 0.5 | 2.5 | Review and fix Quality Attributes
6 | 2012-06-18 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-06-18 | 18:00 | 23:00 | 1 | 4 | Review and fix Use-case
| 2012-06-19 | 8:00 | 0:00 | 0 | 4 | Review and fix Use-case
| 2012-06-20 | 20:00 | 23:00 | 0.5 | 2.5 | Review and fix Use-case
| 2012-06-21 | 9:00 | 0:00 | 0 | 3 | Review and fix 3 View
| 2012-06-22 | 21:00 | 23:00 | 0 | 3 | Review Sequence
| 2012-06-23 | 9:00 | 11:00 | 0 | 2 | Draw Mapping View
7 | 2012-06-24 | 20:00 | 12:00 | 0.5 | 3.5 | Review Team Work
6 | 2012-06-25 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-06-27 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-06-27 | 13:00 | 18:00 | 1 | 5 | Review Coding
| 2012-06-28 | 20:00 | 12:00 | 0.5 | 3.5 | Review Coding
8 | 2012-06-29 | 8:00 | 0:00 | 0 | 4 | Read comments, Assign tasks
| 2012-06-30 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-06-30 | 18:00 | 23:00 | 1 | 4 | Fix Deployment View
| 2012-07-01 | 13:00 | 18:00 | 1 | 5 | Write BC, TC, QA Prioritize
7 | 2012-07-02 | 9:00 | 0:00 | 0 | 3 | Write BC, TC, QA Prioritize
| 2012-07-03 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-07-03 | 20:00 | 12:00 | 0.5 | 3.5 | Write Entity Scenarios
9 | 2012-07-04 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-07-04 | 20:00 | 12:00 | 0.5 | 3.5 | Write Entity Scenarios
| 2012-07-05 | 9:00 | 0:00 | 0 | 3 | Team Meeting
| 2012-07-05 | 16:00 | 23:00 | 1 | 7 | Review and consume, PP slide