## Task_Table
ID | Task Mode | Name | Duration | Start | Finish
1 | Manually Scheduled | Planning | 21 days | 02/04/07 8:00 SA | 29/04/07 5:00 CH
2 | Manually Scheduled | Train Team | 14 days | 02/04/07 8:00 SA | 19/04/07 5:00 CH
3 | Manually Scheduled | Produce basic schedule | 5 days | 20/04/07 8:00 SA | 26/04/07 5:00 CH
4 | Manually Scheduled | Conduct Team Meeting | 2 days | 20/04/07 8:00 SA | 23/04/07 5:00 CH
5 | Manually Scheduled | Kick - Off | 9 days | 26/04/07 8:00 SA | 08/05/07 5:00 CH
6 | Manually Scheduled | Develop Strategy for Viking project | 6 days | 27/04/07 8:00 SA | 04/05/07 5:00 CH
7 | Manually Scheduled | Review RE with customer | 3 days | 27/04/07 8:00 SA | 01/05/07 5:00 CH
8 | Auto Scheduled | Inception & Elaboration | 15 days | 07/05/07 8:00 SA | 25/05/07 5:00 CH
9 | Manually Scheduled | Produce User Requirement | 6 days | 07/05/07 8:00 SA | 14/05/07 5:00 CH
10 | Manually Scheduled | Produce Viking Architecture Document | 5 days | 15/05/07 8:00 SA | 21/05/07 5:00 CH
11 | Manually Scheduled | Produce Project Charter | 4 days | 07/05/07 8:00 SA | 10/05/07 5:00 CH
12 | Manually Scheduled | Produce Project Plan | 10 days | 07/05/07 8:00 SA | 18/05/07 5:00 CH
13 | Manually Scheduled | Develop High Level Design Document | 5 days | 15/05/07 8:00 SA | 21/05/07 5:00 CH
14 | Manually Scheduled | Develop Detailed Level Design Document | 4 days | 22/05/07 8:00 SA | 25/05/07 5:00 CH
15 | Manually Scheduled | Produce Test Plan (Unit Test and Integration Test) | 4 days | 22/05/07 8:00 SA | 25/05/07 5:00 CH
16 | Manually Scheduled | Construction | 142 days | 28/05/07 8:00 SA | 11/12/07 5:00 CH
17 | Auto Scheduled | Produce Viking Module Construction | 120 days | 28/05/07 8:00 SA | 09/11/07 5:00 CH
18 | Manually Scheduled | Adding functionality in each subsequent work package | 20 days | 28/05/07 8:00 SA | 22/06/07 5:00 CH
19 | Manually Scheduled | Address the work package | 6 days | 25/06/07 8:00 SA | 02/07/07 5:00 CH
20 | Manually Scheduled | Package the deliverables | 8 days | 03/07/07 8:00 SA | 12/07/07 5:00 CH
21 | Manually Scheduled | Test work package | 14 days | 12/11/07 8:00 SA | 29/11/07 5:00 CH
22 | Manually Scheduled | Transition | 13 days | 30/11/07 8:00 SA | 18/12/07 5:00 CH
23 | Manually Scheduled | Produce Viking Material | 2 days | 30/11/07 8:00 SA | 03/12/07 5:00 CH
24 | Manually Scheduled | Perform acceptance testing | 12 days | 30/11/07 8:00 SA | 17/12/07 5:00 CH
25 | Manually Scheduled | Produce Viking Product Document | 3 days | 30/11/07 8:00 SA | 04/12/07 5:00 CH
26 | Manually Scheduled | Close - Out | 5 days | 18/12/07 8:00 SA | 24/12/07 5:00 CH
27 | Manually Scheduled | Final review | 5 days | 18/12/07 8:00 SA | 24/12/07 5:00 CH
28 | Manually Scheduled | Consume Lessons Learned | 5 days | 18/12/07 8:00 SA | 24/12/07 5:00 CH
29 | Manually Scheduled | Produce Project Close out Document | 2 days | 18/12/07 8:00 SA | 19/12/07 5:00 CH

## Resource_Table
ID | Initials | Type | Material Label | Group | Email Address | Cost Per Use | Notes
1 | V | Work |  |  |  | 0
2 | V | Work |  |  |  | 0
3 | V | Work |  |  |  | 0
4 | A | Work |  |  |  | 0
5 | P | Work |  |  |  | 0

## Assignment_Table
Task Name | % Work Complete | Work | Units
Produce basic schedule | 0 | 10h | 100%
Develop Strategy for Viking project | 0 | 36h | 100%
Review RE with customer | 0 | 9h | 100%
Produce User Requirement | 0 | 36h | 100%
Produce Viking Architecture Document | 0 | 30h | 100%
Produce Project Charter | 0 | 24h | 100%
Produce Project Plan | 0 | 60h | 100%
Develop High Level Design Document | 0 | 30h | 100%
Develop Detailed Level Design Document | 0 | 24h | 100%
Produce Test Plan (Unit Test and Integration Test) | 0 | 24h | 100%
Produce Viking Module Construction | 0 | 720h | 75%
Adding functionality in each subsequent work package | 0 | 120h | 100%
Address the work package | 0 | 36h | 100%
Package the deliverables | 0 | 48h | 100%
Test work package | 0 | 84h | 100%
Perform acceptance testing | 0 | 72h | 100%
Produce Viking Product Document | 0 | 18h | 100%
Final review | 0 | 30h | 100%
Consume Lessons Learned | 0 | 30h | 100%
Produce Project Close out Document | 0 | 12h | 100%