## Planned Weekly Effort W#1
Planned Weekly Effort W#1
Name: | Thanh Giang | Starting Date: |  | 2012-05-21
Course: | SEP | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27 | Total
| Task | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27
| Team Meetings | 2012-05-21: 3; 2012-05-23: 3; 2012-05-25: 3 | 9
| Research Document | [7 empty] | 5 | bar: 2012-05-21 to 2012-05-25
| Team Home Work | 2 | 2 |  | 2 |  | 2 | 1 | 9
| Meetings with Mentor | 2012-05-21: 2 | 2
| Total | 8 | 3 | 4 | 3 | 4 | 2 | 1 | 25

## SEP_TimeLog
Time Recording Log For: SRM Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Thanh Giang |  |  |  | Date: | 14/5
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Inter. Time | Delta Time | Activity | Artifact | C | U | Plan and Schedule | #REF!
| 2012-05-18 | 10:30 | 0:00 | 0 | 1.5 | Kick off Project with Mentor |  |  |  | Architecture drivers | #REF!
1 | 2012-05-23 | 9:00 | 11:00 | 0 | 2 | Team Meeting with Mentor |  |  |  | Architecture & Design | #REF!
| 2012-05-22 | 21:00 | 23:00 | 0 | 2 | Lên danh sách câu hỏi gửi mail cho khách hàng
| 2012-05-23 | 9:30 | 0:00 | 0 | 2.5 | Team Meeting | Phân tích danh sách trả lời câu hỏi của customer Xác định actor Đưa ra các chức năng chính Đưa QA cho khách hàng chọn lựa
| 2012-05-23 | 18:00 | 23:00 | 1 | 4 | Vẽ Usecase Vẽ Context Diagram Vẽ Physic Perspective | SRS Architect Document

## Planned Weekly Effort W#2
Planned Weekly Effort W#2
Name: | Thanh Giang | Starting Date: |  | 2012-05-28
Course: | SEP | 2012-05-28 | 2012-05-29 | 2012-05-30 | 2012-05-31 | 2012-06-01 | 2012-06-02 | 2012-06-03 | Total
| Task | 2012-05-28 | 2012-05-29 | 2012-05-30 | 2012-05-31 | 2012-06-01 | 2012-06-02 | 2012-06-03
| Team Meetings | 2012-05-28: 3; 2012-05-30: 3; 2012-06-01: 3 | 9
| Research Document | [7 empty] | 2 | bar: 2012-05-29; 2012-06-01
| Team Home Work | 2 | 2 |  | 2 | 3 | 1 | 2 | 12
| Meetings with Mentor | 2012-05-28: 3 | 3
| Total | 8 | 3 | 3 | 2 | 7 | 1 | 2 | 26

## Planned Weekly Effort W#3
Planned Weekly Effort W#2
Name: | Thanh Giang | Starting Date: |  | 2012-06-04
Course: | SEP | 2012-06-04 | 2012-06-05 | 2012-06-06 | 2012-06-07 | 2012-06-08 | 2012-06-09 | 2012-06-10 | Total
| Task | 2012-06-04 | 2012-06-05 | 2012-06-06 | 2012-06-07 | 2012-06-08 | 2012-06-09 | 2012-06-10
| Team Meetings | 2012-06-04: 3; 2012-06-08: 3; 2012-06-09: 3 | 9
| Research Document | [7 empty] | 2 | bar: 2012-06-05; 2012-06-07
| Team Home Work | 3 | 2 |  | 3 |  | 3 | 2 | 13
| Meetings with Mentor | 2012-06-04: 2 | 2
| Total | 8 | 3 | 0 | 4 | 3 | 6 | 2 | 26