## EVM
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
Setup and Project Management
BCWS | 364 | 596 | 620 | 640 | 660 | 680 | 700 | 720 | 740 | 760 | 780 | 800 | 820 | 840 | 860 | 880 | 900 | 920 | 940 | 960 | 980 | 1000 | 1020 | 1040 | 1060 | 1080 | 1100 | 1120 | 1140 | 1160 | 1180 | 1200 | 1220 | 1240 | 1260 | 1280 | 1300 | 1320 | 1340 | 1360 | 1380 | 1400 | 1420 | 1440 | 1460 | 1480 | 1480 | 1480
BCWP | 311.98 | 596 | 620 | 640 | 660 | 680 | 700 | 720 | 740 | 760 | 780 | 800 | 820 | 840 | 860 | 880 | 900 | 920 | 940 | 960 | 980 | 1000 | 1020 | 1040 | 1060 | 1080 | 1100 | 1120
ACWP | 364 | 564 | 588 | 608 | 628 | 648 | 668 | 688 | 708 | 728 | 748 | 768 | 788 | 808 | 828 | 848 | 868 | 888 | 904 | 924 | 944 | 964 | 984 | 1004 | 1024 | 1044 | 1064 | 1084
Release 1 - Deliver GUI & User Documentation
BCWS |  |  | 136 | 216 | 344 | 488 | 664 | 784 | 868 | 972 | 1092 | 1140 | 1180 | 1316 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332
BCWP |  |  | 104 | 184 | 312 | 444.28 | 568.7617 | 718.2183 | 819.8767 | 936 | 1064.8 | 1136.8 | 1151.345 | 1248.8 | 1320.35 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332
ACWP |  |  | 104 | 184 | 312 | 448 | 528 | 648 | 776 | 900 | 1024 | 1096 | 1108 | 1212 | 1280 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292
Release 2 - Deliver Online Product
BCWS |  |  | 144 | 346.6667 | 501.3334 | 589.3334 | 613.3334 | 693.3335 | 784.0002 | 981.5285 | 1141.5285 | 1280.1952 | 1360.1952 | 1440.1952 | 1536.1952 | 1616.1952 | 1696.1952 | 1856.1952 | 2056.1952 | 2256.1952 | 2408.1952 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619
BCWP |  |  | 51.5533 | 151.11 | 224 | 312 | 328 | 722.8619 | 722.8619 | 735.5835 | 759.6802 | 890.8619 | 972.9335 | 1146.8619 | 1272.1952 | 1349.5285 | 1429.5285 | 1509.5285 | 1589.5285 | 1669.5285 | 1869.5285 | 2069.5285 | 2245.5285 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619
ACWP |  |  | 48 | 152 | 224 | 312 | 328 | 428 | 428 | 460 | 500 | 636 | 712 | 876 | 1004 | 1080 | 1160 | 1240 | 1320 | 1400 | 1600 | 1800 | 1976 | 2164 | 2164 | 2164 | 2164 | 2164
Release 3 - Deliver Offline Product
BCWS |  |  | 31.1 | 45.3333 | 58.6667 | 58.6667 | 58.6667 | 58.6667 | 58.6667 | 98.4717 | 148.9433 | 252.8867 | 274.61 | 357.44 | 448.1633 | 528.1633 | 608.1633 | 688.1633 | 768.1633 | 848.1633 | 928.1633 | 1250.83 | 1520.1633 | 1685.4967 | 1840.4083 | 2005.0883 | 2116.4083 | 2556.4083 | 2974.7483 | 3154.7483 | 3421.3333 | 3861.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333
BCWP |  |  | 0 | 26.6667 | 53.3333 | 53.3333 | 53.3333 | 53.3333 | 53.3333 | 53.3333 | 108.5483 | 124.7567 | 163.8067 | 219.68 | 275.0467 | 384.2567 | 464.22 | 544.22 | 626.1567 | 700.1867 | 789.62 | 862.38 | 944.1033 | 1071.0633 | 1432.38 | 1632.38 | 1826.6883 | 1953.7583
ACWP |  |  | 0 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 104 | 128 | 160 | 218 | 278 | 386 | 466 | 546 | 626 | 706 | 788 | 866 | 946 | 1082 | 1435 | 1628 | 1784 | 1880
Release 4 - Deliver Final Product
BCWS | [35 empty] | 1264 | 1312 | 1448 | 1648 | 1848 | 2048 | 2248 | 2448 | 2648 | 2856 | 2864 | 2864 | 2864
BCWP | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACWP | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.09 | 253.09 | 253.09 | 253.09 | 57.94
Total
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
BCWS | 364 | 596 | 931.1 | 1248 | 1564 | 1816.0001 | 2036.0001 | 2256.0002 | 2450.6669 | 2812.0002 | 3162.4718 | 3473.0819 | 3634.8052 | 3953.6352 | 4176.3585 | 4356.3585 | 4536.3585 | 4796.3585 | 5096.3585 | 5396.3585 | 5648.3585 | 6017.6919 | 6307.0252 | 6492.3585 | 6667.2702 | 6851.9502 | 6983.2702 | 7443.2702 | 7881.6102 | 8081.6102 | 8368.1952 | 8828.1952 | 9024.1952 | 9044.1952 | 9064.1952 | 10348.1952 | 10416.1952 | 10572.1952 | 10792.1952 | 11012.1952 | 11232.1952 | 11452.1952 | 11672.1952 | 11892.1952 | 12120.1952 | 12148.1952 | 12148.1952 | 12148.1952
BCWP | 311.98 | 596 | 775.5533 | 1001.7767 | 1249.3333 | 1489.6133 | 1650.095 | 2214.4135 | 2336.0718 | 2484.9169 | 2713.0285 | 2952.4185 | 3108.0852 | 3455.3419 | 3727.5919 | 3945.7852 | 4125.7485 | 4305.7485 | 4487.6852 | 4661.7152 | 4971.1485 | 5263.9085 | 5541.6319 | 5877.9252 | 6259.2419 | 6479.2419 | 6693.5502 | 6840.6202
ACWP | 364 | 564 | 740 | 964 | 1204 | 1448 | 1564 | 1804 | 1952 | 2128 | 2376 | 2628 | 2768 | 3114 | 3390 | 3606 | 3786 | 3966 | 4142 | 4322 | 4624 | 4922 | 5198 | 5542 | 5915 | 6128 | 6304 | 6420
CV | -52.02 | 32 | 35.5533 | 37.7767 | 45.3333 | 41.6133 | 86.095 | 410.4135 | 384.0718 | 356.9169 | 337.0285 | 324.4185 | 340.0852 | 341.3419 | 337.5919 | 339.7852 | 339.7485 | 339.7485 | 345.6852 | 339.7152 | 347.1485 | 341.9085 | 343.6319 | 335.9252 | 344.2419 | 351.2419 | 389.5502 | 420.6202
SV | -52.02 | 0 | -155.5467 | -246.2233 | -314.6667 | -326.3868 | -385.9051 | -41.5867 | -114.595 | -327.0833 | -449.4433 | -520.6633 | -526.72 | -498.2933 | -448.7667 | -410.5733 | -410.61 | -490.61 | -608.6733 | -734.6433 | -677.21 | -753.7833 | -765.3933 | -614.4333 | -408.0283 | -372.7083 | -289.72 | -602.65
CPI | 0.85709 | 1 | 0.83294 | 0.80271 | 0.79881 | 0.82027 | 0.81046 | 0.98157 | 0.95324 | 0.88368 | 0.85788 | 0.85009 | 0.85509 | 0.87397 | 0.89255 | 0.90575 | 0.90948 | 0.89771 | 0.88057 | 0.86386 | 0.8801 | 0.87474 | 0.87864 | 0.90536 | 0.9388 | 0.94561 | 0.95851 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903
SPI | 0.85709 | 1.0567 | 1.048 | 1.0392 | 1.0377 | 1.0287 | 1.055 | 1.2275 | 1.1968 | 1.1677 | 1.1418 | 1.1234 | 1.1229 | 1.1096 | 1.0996 | 1.0942 | 1.0897 | 1.0857 | 1.0835 | 1.0786 | 1.0751 | 1.0695 | 1.0661 | 1.0606 | 1.0582 | 1.0573 | 1.0618 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655
ETC | [27 empty] | 6420 | 7396.9821 | 7584.6844 | 7853.6478 | 8285.3631 | 8469.3113 | 8488.0816 | 8506.8518 | 9711.9006 | 9775.7194 | 9922.1272 | 10128.5997 | 10335.0723 | 10541.5448 | 10748.0173 | 10954.4899 | 11160.9624 | 11374.943 | 11401.2214 | 11401.2214 | 11401.2214 | 11638.7493 | 11876.2771 | 12113.805 | 12351.3329 | 12405.7103
Projected Program Delay | [27 empty] | 6840.62 | 8575.9724 | 8793.5922 | 9105.425 | 9605.9506 | 9819.218 | 9840.98 | 9862.742 | 11259.8611 | 11333.8518 | 11503.5953 | 11742.9771 | 11982.3589 | 12221.7406 | 12461.1224 | 12700.5042 | 12939.886 | 13187.9726 | 13218.4394 | 13218.4394 | 13218.4394
BAC | 12148.2
VAC | -257.49
ISAC | 52.2287
IEAC | 11401.2241

## Project Budget Summary
Project Budget Summary
Year | Category | Detail | Total
1st year | Developing expense | 323760 | 553760
| Risk management expense | 60000
| Change management expense | 60000
| Equipment (Hardware & Software) | 20000
| Facility expense | 20000
| Contingency expense | 70000
2nd and 3rd year | Maintenance | 54000 | 121500
| Training customer | 67500
4th year | Maintenance | 27000 | 269170
| Developing expense | 102170
| Risk management expense | 20000
| Change management expense | 20000
| Equipment (Hardware & Software) | 20000
| Facility expense | 20000
| Contingency expense | 60000

## Team Morale
Team Morale compare between 2009 and 2010
| Physical Environment | System, Tools and Processes | Motivation | Emotional Environment | Management | Looking for another job
2009 | 7.4 | 5.65 | 4.75 | 16.1 | 4.27 | 0.4
2010 | 5.2 | 2.3 | 3.1 | 12.27 | 2.4 | 0.27
Click on each environment for more detail
As you can see from the graph, the physical environment decreased from 7.4 in 2009 to a number of 5.2 in 2010, that proves the team doesn't
more satisfier the physical environment in 2010 than 2009. System, tools and processes that fall sharply throughout from 2009 - 2010 (from 5.65
in 2009 fall to 2.3 in 2010). That is the same for motivation, compared to 2010, the point in 2009 is higher, in specific, 4.75 in 2009 and 3.1 in 2010
For emotional environment that is the highest point of all group in both 2009 and 2010, but the point in 2009 also higher than the point in 2010 (from 16.1 drop to 12.27)
Besides, the management looks like similar to all of the before comparision, that decreased from 2009 with 4.27 point to 2010 with 2.4 point
All of figures to prove that, the team morale in 2009 is higher than 2010. However, the people looking for another job in 2010 is rose slightly for 2009 but this rate is very low.

## Physical Enviroment
2009 | [6 empty] | 2010
# | Physical Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Physical Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
4 | My department is a great place to work | 11 | 17 | 14 | 36 | 22 | 4 | My department is a great place to work | 20 | 26 | 26 | 47 | 31
5 | ABC Systems is a great place to work | 12 | 18 | 17 | 31 | 22 | 5 | ABC Systems is a great place to work | 19 | 27 | 34 | 40 | 30
| TOTAL | 23 | 35 | 31 | 67 | 44 |  | TOTAL | 39 | 53 | 60 | 87 | 61
| Rate (%) | 11.5 | 17.5 | 15.5 | 33.5 | 22 |  | Rate (%) | 13 | 17.6667 | 20 | 29 | 20.3333
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 11.5 | 17.5 | 15.5 | 33.5 | 22 | 7.4
2010 | 13 | 17.6667 | 20 | 29 | 20.3333 | 5.2
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## System, Tools and Process
2009 | [6 empty] | 2010
# | Systems, Tools and Processes | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Systems, Tools and Processes | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
6 | My project is a great place to work | 8 | 13 | 28 | 25 | 26 | 6 | My project is a great place to work | 16 | 24 | 40 | 36 | 34
9 | There is cooperation between the departments in the company | 26 | 22 | 18 | 19 | 15 | 9 | There is cooperation between the departments in the company | 40 | 34 | 24 | 27 | 25
10 | I have the tools and resources that I need to get my job done | 7 | 12 | 21 | 32 | 28 | 10 | I have the tools and resources that I need to get my job done | 15 | 25 | 32 | 42 | 36
13 | I have access to the information that I need to do my job well | 12 | 15 | 28 | 23 | 22 | 13 | I have access to the information that I need to do my job well | 22 | 27 | 40 | 33 | 28
| TOTAL | 53 | 62 | 95 | 99 | 91 |  | TOTAL | 93 | 110 | 136 | 138 | 123
| RATE (%) | 13.25 | 15.5 | 23.75 | 24.75 | 22.75 |  | RATE (%) | 15.5 | 18.3333 | 22.6667 | 23 | 20.5
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 13.25 | 15.5 | 23.75 | 24.75 | 22.75 | 5.65
2010 | 15.5 | 18.3333 | 22.6667 | 23 | 20.5 | 2.9333
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Motivation
2009 | [6 empty] | 2010
# | Motivation | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Motivation | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
3 | I am provided with opportunities to broaden my skills and knowledge | 22 | 20 | 32 | 12 | 14 | 3 | I am provided with opportunities to broaden my skills and knowledge | 28 | 34 | 42 | 24 | 22
8 | I am empowered to make decisions | 18 | 21 | 19 | 18 | 24 | 8 | I am empowered to make decisions | 28 | 30 | 30 | 32 | 30
14 | My opinions are valued by my project team | 6 | 7 | 40 | 24 | 23 | 14 | My opinions are valued by my project team | 14 | 15 | 55 | 34 | 32
15 | I know how my work contributes to the success of ABC Systems | 8 | 13 | 17 | 36 | 26 | 15 | I know how my work contributes to the success of ABC Systems | 13 | 28 | 33 | 44 | 32
| TOTAL | 54 | 61 | 108 | 90 | 87 |  | TOTAL | 83 | 107 | 160 | 134 | 116
| RATE (%) | 13.5 | 15.25 | 27 | 22.5 | 21.75 |  | RATE (%) | 13.8333 | 17.8333 | 26.6667 | 22.3333 | 19.3333
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 13.5 | 15.25 | 27 | 22.5 | 21.75 | 4.75
2010 | 13.8333 | 17.8333 | 26.6667 | 22.3333 | 19.3333 | 3.1
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Emotional Environment
2009 | [6 empty] | 2010
# | Emotional Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Emotional Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
12 | I would recommend ABC Systems to friends as a great place to work | 10 | 23 | 21 | 28 | 18 | 12 | I would recommend ABC Systems to friends as a great place to work | 18 | 35 | 34 | 40 | 23
16 | I take pride in my work | 0 | 5 | 15 | 15 | 65 | 16 | I take pride in my work | 0 | 12 | 30 | 35 | 73
| TOTAL | 10 | 28 | 36 | 43 | 83 |  | TOTAL | 18 | 47 | 64 | 75 | 96
| RATE (%) | 5 | 14 | 18 | 21.5 | 41.5 |  | RATE (%) | 6 | 15.6667 | 21.3333 | 25 | 32
| Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | Point
2009 | 5 | 14 | 18 | 21.5 | 41.5 | 16.1
2010 | 6 | 15.6667 | 21.3333 | 25 | 32 | 12.2667
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Management
2009 | [6 empty] | 2010
# | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
1 | I see career growth and advancement opportunities for myself at ABC Systems | 12 | 25 | 20 | 26 | 17 | 1 | I see career growth and advancement opportunities for myself at ABC Systems | 18 | 35 | 28 | 38 | 31
2 | I feel informed about changes that affect me | 14 | 18 | 28 | 24 | 16 | 2 | I feel informed about changes that affect me | 26 | 28 | 40 | 36 | 20
11 | I have had the training I need to get the job done | 12 | 16 | 14 | 33 | 25 | 11 | I have had the training I need to get the job done | 22 | 30 | 25 | 43 | 30
| TOTAL | 38 | 59 | 62 | 83 | 58 |  | TOTAL | 66 | 93 | 93 | 117 | 81
| RATE (%) | 12.6667 | 19.6667 | 20.6667 | 27.6667 | 19.3333 |  | RATE (%) | 14.6667 | 20.6667 | 20.6667 | 26 | 18
| Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | Point
2009 | 12.6667 | 19.6667 | 20.6667 | 27.6667 | 19.3333 | 4.2667
2010 | 14.6667 | 20.6667 | 20.6667 | 26 | 18 | 2.4
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Looking for another job
2009 | [6 empty] | 2010
# | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
7 | I am currently looking for another job outside of ABC Systems | 20 | 25 | 7 | 33 | 15 | 7 | I am currently looking for another job outside of ABC Systems | 31 | 34 | 15 | 46 | 24
| TOTAL | 20 | 25 | 7 | 33 | 15 |  | TOTAL | 31 | 34 | 15 | 46 | 24
| RATE (%) | 20 | 25 | 7 | 33 | 15 |  | RATE (%) | 20.6667 | 22.6667 | 10 | 30.6667 | 16
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 20 | 25 | 7 | 33 | 15 | 0.4
2010 | 20.6667 | 22.6667 | 10 | 30.6667 | 16 | 0.26667
Strongly Disagree | 2
Disagree | 1
Neutral | 0
Agree | -1
Strongly Agree | -2

## Sheet1
Viking Estimated Resource Allocation
No. | Role | Allocation
Year 01
1 | PM | 1
2 | Developer | 4
3 | Architect | 1
4 | Risk Manager | 1
5 | Change manager | 1
6 | Requirement Engineer | 2
7 | Tester | 2
8 | Quality Assurance Manager | 1
Year 2
1 | Mantaining Member | 3
2 | Training Member | 3
Year 03
1 | Mantaining Member | 1
2 | Training Member | 1
Year 04
1 | PM | 1
2 | Developer | 2
3 | Risk Manager | 1
4 | Change manager | 1
5 | Requirement Engineer | 1
6 | Tester | 2
7 | Designer | 1