## planning
|  | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13
|  | Week 01 | Week 02 | Week 03 | Week 04 | Week 05 | Week 06 | Week 07 | Week 08 | Week 09 | Week 10 | Week 11 | Week 12 | Week 13
Phases | Process optimization | 2012-05-21: N/A
Busines Operation
Requirment | bar: 2012-05-21 to 2012-06-11
Analisys & Design | bar: 2012-05-28 to 2012-06-25
Development | bar: 2012-06-25 to 2012-07-23
Testing | bar: 2012-07-23 to 2012-07-30
Packaging & deploying | bar: 2012-07-30 to 2012-08-06
| Planing+ PM | 2012-08-13: mon
| CM | 2012-08-13: tue
Milestones | Official Review by Department
Process review
Project Review
Deliverable | Process guide+ project convention | 2012-05-21: N/A
Concept-operation
SRS | bar: 2012-05-28 to 2012-06-11
SAD+ SDS | bar: 2012-06-25
Testing Plan | bar: 2012-07-16 to 2012-07-23
Source Code | bar: 2012-08-06
UserGuide
| ProjectPlan | 2012-05-28: v1; 2012-06-25: v2; 2012-07-16: v3; 2012-08-06: vf
| Meeting Minutes | w01 | w02 |  |  | w03 | w04 | w05 | w06 | w07 | w08 | w09 | w10
|  |  | vF |  |  | w03: Final Version
Note on B8: vnam: Not important

## evaluation
Evaluation Plan |  | Team evaluation |  | Individual Evaluation
|  | 60% |  | 40%
|  |  |  | Contribution | Attitude | 360 - evaluation
Phases | Process optimization | N/A | 40% | 40% | 30% | 30%
| Busines Operation | N/A
| Requirment | 10%
| Analisys & Design | 10%
| Development | 10%
| Testing | 5%
| Packaging & deploying | 0%
| Planing+ PM | 0%
| CM | 5%
Deliverable | Process guide+ project convention | N/A | 60%
| Concept-operation | N/A
| SRS | 10%
| SAD+ SDS | 10%
| Testing Plan | 5%
| Source Code | 10%
| UserGuide | 5%
| ProjectPlan | 10%
Meeting Minutes
Lưu ý: nên sử dụng thang điểm 100
Note on G4: vnam: - Mỗi thành viên cho điểm các thành viên trong nhóm (không cho điểm bản thân mình). Điểm của cột F là trung bình cộng của điểm các thành viên. - Nội dung của 360-evaluation cũng gồm: + Nhận xét về contribution và attitude + cho điểm cho 2 cột trên theo thang điểm 100 + Điểm tổng hợp là trung bình cộng của 2 cột điểm trện - Thành viên nào không nộp bản 360-evaluation => F=0, E=0
Note on B9: vnam: Not important

## teamsAndProjects
| n1 | n2 | n3
DT 01 | T2_06 | T1_05 | T2_02
Dt 02 | T1_02 | T2_07 | T2_05
DT 03 | T2_04 | T1_07 | T1_08
DT 04 | T1_03 | T2_01 | T1_04
DT 05 | T2_03 | T1_01 | T1_06