## SAD_TimeLog
Time Recording Log For: POS Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Thanh Giang |  |  |  | Date: | 14/5
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Inter. Time | Delta Time | Activity | Artifact | C | U | Plan and Schedule | 10
| 2012-05-14 | 22:30 | 12:00 | 0 | 1.5 | Kick off Team meeting |  |  |  | Architecture drivers | 21.5
1 | 2012-05-14 | 21:00 | 23:00 | 0 | 2 | Research document: Project Plan |  |  |  | Architecture & Design | 47
| 2012-05-15 | 20:00 | 23:00 | 0.5 | 2.5 | Write Project Plan
| 2012-05-16 | 20:30 | 12:00 | 0 | 3.5 | Team Meeting | Final_Project_Guidelines
| 2012-05-16 | 20:00 | 23:00 | 0.5 | 2.5 | Write Project Plan -Work Breakdown Structure
| 2012-05-17 | 20:00 | 23:00 | 0.5 | 2.5 | Draw Allocation View
| 2012-05-18 | 20:30 | 12:00 | 0 | 3.5 | Team Meeting
| 2012-05-19 | 20:00 | 23:00 | 0.5 | 2.5 | Data Model
| 2012-05-20 | 20:00 | 23:00 | 0.5 | 2.5 | Context Diagrams
[10 empty] | Class diagram and Database | 23
| 2010-06-14 | 21:00 | 23:00 | 0 | 2 | Analyze requirement | Use case diagram |  |  | Coding | 27
| 2010-06-15 | 21:00 | 23:00 | 0 | 2 | Team Review | Master Plan V 1.1 |  |  | TOTAL | 128.5
[7 empty] | Use case diagram |  |  | ON AVERAGE (hours/week) | 16.0625
2 | 2010-06-16 | 3.5 PM | 17:00 | 0 | 1.5 | Meeting with mentor | Master Plan V 1.1 |  | Missing Schedule
Use case diagram
| 2010-06-17 | 21:00 | 12:00 | 0 | 3 | Analyze Requirement | Use case diagram
Architecture driver 1.0
| 2010-06-18 | 21:00 | 12:00 | 0 | 3 | Document | Architecture driver 1.0
Initial Project Schedule
| 2010-06-19 | 21:00 | 12:00 | 0 | 3 | Document | Architecture driver 1.0
| 2010-06-20 | 21:00 | 23:00 | 0 | 2 | Team review | Architecture driver 1.0
| 2010-06-21 | 15:00 | 17:00 | 0 | 2 | Meeting with mentor | Initial Project Schedule
Architecture driver 1.0
| 2010-06-22 | 23:00 | 12:00 | 0 | 1 | Review | Requirement spec 1.5 | C
| 2010-06-23 | 0:00 | 2:00 | 0 | 2 | Document | Initial Architecture Design 1.0 |  | 4
Requirement spec 2.0
|  | 21:00 | 23:00 | 0 | 2 | Team Review | Architecture design 1.0 assigned to member | C
Assign works
| 2010-06-24 | 15:00 | 18:00 | 0 | 3 | Study MySQL and Netbeans | Install & configure | C
|  | 20:00 | 23:00 | 0 | 3
| 2010-06-25 | 20:00 | 23:00 | 0 | 3 | Study MySQL and Netbeans | Connect to MySQL | C
| 2010-06-26 | 6:00 | 8:00 | 0 | 2 | Java course
|  | 13:00 | 15:00 | 0 | 2 | Update | Arch. Design V 1.0 |  | 1
|  | 22:00 | 12:00 | 0 | 2 | Update | Arch. Design V 1.0 |  | 1
| 2010-06-27 | 21:00 | 23:00 | 0 | 2 | Team Review | Test Plan
[7 empty] | Arch. Design V1.1 |  | 6
|  | 12:00 | 13 PM | 0 | 1 | Update | Arch. Design V1.1 |  | 3
| 2010-06-28 | 13:00 | 14:00 | 0 | 1 | Review & Update | Arch. Design V1.2 |  | 6
Master Plan 1.3
4 |  | 21:00 | 23:00 | 0 | 2 | Update | Arch. Design V1.2 |  | 6
| 2010-06-29 | O AM | 2:00 | 0 | 2 | Add | Arch. Design V1.3 |  | 1
|  | 6:00 | 7:00 | 0 | 1 | Update | Arch. Design V1.3 |  | 1
|  | 8.5 AM | 10.5 AM | 0 | 2 | Add | Arch. Design V1.3 |  | 4
|  | 22:00 | 12:00 | 0 | 2 | Review | Arch. Design V1.3 |  | 12
| 2010-06-30 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Connect to Database MYSQL “Jukebox” |  | 1
| 2010-07-01 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Create form to display data from Jukebox Database |  | 1
| 2010-07-02 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Update form to input user data (Datetime style…) |  | 1
| 2010-07-03 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Create stored procedure for Jukebox database |  | 1
| 2010-07-04 | 9:00 | 11:00 | 0 | 2 | Coding in Java | Call and execute stored procedure from Java form |  | 1
| 2010-07-05 | 21:00 | 23:00 | 0 | 2 | Team review | Screen UI
Physical Database
Master Plan
5 | [6 empty] | Test Plan
| 2010-07-06 | 17:00 | 19:00 | 0 | 2 | Restore drive C
|  | 21:00 | 23:00 | 0 | 2 | Coding in Java AND input data in Database Jukebox to test | Testing data in Database and Prototype of List Statistic (UI and control)
| 2010-07-07 | 17:00 | 19:00 | 0 | 2 | Coding | Prototype Configure volume (UI and control)
| 2010-07-08 | 21:00 | 22:00 | 0 | 1 | Coding | Prototype Adjust volume UI
|  | 22:00 | 23:00 | 0 | 1 | Document | Architecture Design 1.3
|  | 16:00 | 17:00 | 0 | 1 | Review with mentor | Architecture Design 1.3 |  | Missing:
-Design rationale according with Quality attributes
- Style of connectors in C&C view packets
[7 empty] | Test plan, project plan |  | Missing: test plan, risk management, estimate….
| 2010-07-09 | 15:00 | 17:00 | 0 | 2 | Interface (GUI) | Should change the project type |  | Difficult to manage this kind of project
| 2010-07-10 | 20:00 | 23:00 | 0 | 3 | Update Document | Architecture & Design Document 2.0
| 2010-07-11 | 7:00 | 10:00 | 0 | 3 | Update Document | Architecture & Design Document 2.0
Configure clients Volume control(UI and Control)
|  | 12:00 | 14:00 | 0 | 2 | Coding | Adjust Clients Volume (UI and control) | C
[7 empty] | List statistic (UI and control) | C
[7 empty] | Adjust Volume | C
| 2010-07-12 | 20:00 | 23:00 | 0 | 3 | Update | Architecture & Design Document 2.0
| 2010-07-13 | 6:00 | 9:00 | 0 | 3 | Update | Architecture & Design Document 2.0 | C | 4
6 | [6 empty] | Architecture & Design Document 2.0
|  | 21:00 | 23:00 | 0 | 2 | Team review | Class diagram |  | Continue to complete by Nam and Duy
[7 empty] | Testing Plan |  | Continue to complete by Nhung
[7 empty] | Master Plan |  | Continue to complete by Viet
| 2010-07-14 | 11:00 | 0:00 | 0 | 1 | Review | Class Diagram |  | Continue to complete by Duy
| 2010-07-15 | 14:00 | 15:00 | 0 | 1 | Review | Class Diagram
|  | 3.5PM | 17:00 | 0 | 1.5 | Meeting with mentor | Test Plan, Test cases 1.0 |  | Should improve in detail
Master Plan 3.0
Architecture & Design Document 2.0
Requirement Traceability Matrix 1.1
|  | 23:00 | 12:00 | 0 | 1 | Document | Configuration Management 1.0 |  | Initial draft
| 2010-07-16 | 20:00 | 23:00 | 0 | 3 | Document | Class diagram 1.2
| 2010-07-17 | 8:00 | 0:00 | 1 | 3 | Document | Class diagram 1.3
| 2010-07-18 | 20:00 | 22:00 | 0 | 2 | Reading | Java course
| 2010-07-19 | 20:00 | 22:00 | 0 | 2 | Reading | Java course
| 2010-07-20 | 10:00 | 0:00 | 0 | 2 | Coding Review
|  | 21:00 | 23:00 | 0 | 2 | Team Review | Class diagram |  | Duy and Name continue to complete
7 | 2010-07-21 | 21:00 | 23:00 | 0 | 2 | Reading | Java course
| 2010-07-22 | 8:00 | 0:00 | 1 | 3 | Document | Architecture & Design Document 2.3
| 2010-07-23 | 9:00 | 10:00 | 0 | 2 | Document | Architecture & Design Document 2.3
2010-07-24
2010-07-25
| 2010-07-26 | 21:00 | 23:00 | 0 | 2 | Team Review | Architecture & Design Document 2.4
Test cases
8 | 2010-07-26 | 10:00 | 11:00 | 0 | 1 | Document | Architecture & Design Document 2.5
| 2010-07-28 | 16:00 | 17:00 | 0 | 1 | Meeting with mentor | Architecture & Design Document 2.5 |  | Require to complete rationale for Design
| 2010-07-29 | 14:00 | 17:00 | 0 | 3 | Reading reference
| 2010-07-30 | 1:00 | 3:00 | 0 | 2 | Document | Architecture & Design Document 2.6 | C
| 2010-07-31 | 8:00 | 0:00 | 0 | 4 | Testing | System Test (Admin functions) | C
2010-08-01
2010-07-02
2010-07-03
2010-07-04
9 | 2010-07-05
2010-07-06
2010-07-07
| 2010-07-08 | COME BACK VIET NAM

## SEP_TimeLog
Time Recording Log For: POS Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Thanh Giang |  |  |  | Date: | 14/5
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Inter. Time | Delta Time | Activity | Artifact | C | U | Plan and Schedule | 7.5
| 2012-05-18 | 22:30 | 12:00 | 0 | 1.5 | Kick off Project with Mentor |  |  |  | Architecture drivers | 21.5
1 | 2012-05-21 | 21:00 | 11:00 | 0 | 2 | Team Meeting with Mentor |  |  |  | Architecture & Design | 47
[10 empty] | Class diagram and Database | 23
| 2010-06-14 | 21:00 | 23:00 | 0 | 2 | Analyze requirement | Use case diagram |  |  | Coding | 27
| 2010-06-15 | 21:00 | 23:00 | 0 | 2 | Team Review | Master Plan V 1.1 |  |  | TOTAL | 126
[7 empty] | Use case diagram |  |  | ON AVERAGE (hours/week) | 15.75
2 | 2010-06-16 | 3.5 PM | 17:00 | 0 | 1.5 | Meeting with mentor | Master Plan V 1.1 |  | Missing Schedule
Use case diagram
| 2010-06-17 | 21:00 | 12:00 | 0 | 3 | Analyze Requirement | Use case diagram
Architecture driver 1.0
| 2010-06-18 | 21:00 | 12:00 | 0 | 3 | Document | Architecture driver 1.0
Initial Project Schedule
| 2010-06-19 | 21:00 | 12:00 | 0 | 3 | Document | Architecture driver 1.0
| 2010-06-20 | 21:00 | 23:00 | 0 | 2 | Team review | Architecture driver 1.0
| 2010-06-21 | 15:00 | 17:00 | 0 | 2 | Meeting with mentor | Initial Project Schedule
Architecture driver 1.0
| 2010-06-22 | 23:00 | 12:00 | 0 | 1 | Review | Requirement spec 1.5 | C
| 2010-06-23 | 0:00 | 2:00 | 0 | 2 | Document | Initial Architecture Design 1.0 |  | 4
Requirement spec 2.0
|  | 21:00 | 23:00 | 0 | 2 | Team Review | Architecture design 1.0 assigned to member | C
Assign works
| 2010-06-24 | 15:00 | 18:00 | 0 | 3 | Study MySQL and Netbeans | Install & configure | C
|  | 20:00 | 23:00 | 0 | 3
| 2010-06-25 | 20:00 | 23:00 | 0 | 3 | Study MySQL and Netbeans | Connect to MySQL | C
| 2010-06-26 | 6:00 | 8:00 | 0 | 2 | Java course
|  | 13:00 | 15:00 | 0 | 2 | Update | Arch. Design V 1.0 |  | 1
|  | 22:00 | 12:00 | 0 | 2 | Update | Arch. Design V 1.0 |  | 1
| 2010-06-27 | 21:00 | 23:00 | 0 | 2 | Team Review | Test Plan
[7 empty] | Arch. Design V1.1 |  | 6
|  | 12:00 | 13 PM | 0 | 1 | Update | Arch. Design V1.1 |  | 3
| 2010-06-28 | 13:00 | 14:00 | 0 | 1 | Review & Update | Arch. Design V1.2 |  | 6
Master Plan 1.3
4 |  | 21:00 | 23:00 | 0 | 2 | Update | Arch. Design V1.2 |  | 6
| 2010-06-29 | O AM | 2:00 | 0 | 2 | Add | Arch. Design V1.3 |  | 1
|  | 6:00 | 7:00 | 0 | 1 | Update | Arch. Design V1.3 |  | 1
|  | 8.5 AM | 10.5 AM | 0 | 2 | Add | Arch. Design V1.3 |  | 4
|  | 22:00 | 12:00 | 0 | 2 | Review | Arch. Design V1.3 |  | 12
| 2010-06-30 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Connect to Database MYSQL “Jukebox” |  | 1
| 2010-07-01 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Create form to display data from Jukebox Database |  | 1
| 2010-07-02 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Update form to input user data (Datetime style…) |  | 1
| 2010-07-03 | 22:00 | 12:00 | 0 | 2 | Coding in Java | Create stored procedure for Jukebox database |  | 1
| 2010-07-04 | 9:00 | 11:00 | 0 | 2 | Coding in Java | Call and execute stored procedure from Java form |  | 1
| 2010-07-05 | 21:00 | 23:00 | 0 | 2 | Team review | Screen UI
Physical Database
Master Plan
5 | [6 empty] | Test Plan
| 2010-07-06 | 17:00 | 19:00 | 0 | 2 | Restore drive C
|  | 21:00 | 23:00 | 0 | 2 | Coding in Java AND input data in Database Jukebox to test | Testing data in Database and Prototype of List Statistic (UI and control)
| 2010-07-07 | 17:00 | 19:00 | 0 | 2 | Coding | Prototype Configure volume (UI and control)
| 2010-07-08 | 21:00 | 22:00 | 0 | 1 | Coding | Prototype Adjust volume UI
|  | 22:00 | 23:00 | 0 | 1 | Document | Architecture Design 1.3
|  | 16:00 | 17:00 | 0 | 1 | Review with mentor | Architecture Design 1.3 |  | Missing:
-Design rationale according with Quality attributes
- Style of connectors in C&C view packets
[7 empty] | Test plan, project plan |  | Missing: test plan, risk management, estimate….
| 2010-07-09 | 15:00 | 17:00 | 0 | 2 | Interface (GUI) | Should change the project type |  | Difficult to manage this kind of project
| 2010-07-10 | 20:00 | 23:00 | 0 | 3 | Update Document | Architecture & Design Document 2.0
| 2010-07-11 | 7:00 | 10:00 | 0 | 3 | Update Document | Architecture & Design Document 2.0
Configure clients Volume control(UI and Control)
|  | 12:00 | 14:00 | 0 | 2 | Coding | Adjust Clients Volume (UI and control) | C
[7 empty] | List statistic (UI and control) | C
[7 empty] | Adjust Volume | C
| 2010-07-12 | 20:00 | 23:00 | 0 | 3 | Update | Architecture & Design Document 2.0
| 2010-07-13 | 6:00 | 9:00 | 0 | 3 | Update | Architecture & Design Document 2.0 | C | 4
6 | [6 empty] | Architecture & Design Document 2.0
|  | 21:00 | 23:00 | 0 | 2 | Team review | Class diagram |  | Continue to complete by Nam and Duy
[7 empty] | Testing Plan |  | Continue to complete by Nhung
[7 empty] | Master Plan |  | Continue to complete by Viet
| 2010-07-14 | 11:00 | 0:00 | 0 | 1 | Review | Class Diagram |  | Continue to complete by Duy
| 2010-07-15 | 14:00 | 15:00 | 0 | 1 | Review | Class Diagram
|  | 3.5PM | 17:00 | 0 | 1.5 | Meeting with mentor | Test Plan, Test cases 1.0 |  | Should improve in detail
Master Plan 3.0
Architecture & Design Document 2.0
Requirement Traceability Matrix 1.1
|  | 23:00 | 12:00 | 0 | 1 | Document | Configuration Management 1.0 |  | Initial draft
| 2010-07-16 | 20:00 | 23:00 | 0 | 3 | Document | Class diagram 1.2
| 2010-07-17 | 8:00 | 0:00 | 1 | 3 | Document | Class diagram 1.3
| 2010-07-18 | 20:00 | 22:00 | 0 | 2 | Reading | Java course
| 2010-07-19 | 20:00 | 22:00 | 0 | 2 | Reading | Java course
| 2010-07-20 | 10:00 | 0:00 | 0 | 2 | Coding Review
|  | 21:00 | 23:00 | 0 | 2 | Team Review | Class diagram |  | Duy and Name continue to complete
7 | 2010-07-21 | 21:00 | 23:00 | 0 | 2 | Reading | Java course
| 2010-07-22 | 8:00 | 0:00 | 1 | 3 | Document | Architecture & Design Document 2.3
| 2010-07-23 | 9:00 | 10:00 | 0 | 2 | Document | Architecture & Design Document 2.3
2010-07-24
2010-07-25
| 2010-07-26 | 21:00 | 23:00 | 0 | 2 | Team Review | Architecture & Design Document 2.4
Test cases
8 | 2010-07-26 | 10:00 | 11:00 | 0 | 1 | Document | Architecture & Design Document 2.5
| 2010-07-28 | 16:00 | 17:00 | 0 | 1 | Meeting with mentor | Architecture & Design Document 2.5 |  | Require to complete rationale for Design
| 2010-07-29 | 14:00 | 17:00 | 0 | 3 | Reading reference
| 2010-07-30 | 1:00 | 3:00 | 0 | 2 | Document | Architecture & Design Document 2.6 | C
| 2010-07-31 | 8:00 | 0:00 | 0 | 4 | Testing | System Test (Admin functions) | C
2010-08-01
2010-07-02
2010-07-03
2010-07-04
9 | 2010-07-05
2010-07-06
2010-07-07
| 2010-07-08 | COME BACK VIET NAM