## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Manually Scheduled | Planning | 21 days | 02/04/07 8:00 SA | 29/04/07 5:00 CH |  | 1
2 | Yes | Manually Scheduled | Train Team | 14 days | 02/04/07 8:00 SA | 19/04/07 5:00 CH |  | 2
3 | Yes | Manually Scheduled | Produce basic schedule | 5 days | 19/04/07 8:00 SA | 25/04/07 5:00 CH |  | 2
4 | Yes | Manually Scheduled | Conduct Team Meeting | 2 days | 25/04/07 8:00 SA | 26/04/07 5:00 CH |  | 2
5 | Yes | Manually Scheduled | Kick - Off | 9 days | 26/04/07 8:00 SA | 08/05/07 5:00 CH |  | 1
6 | Yes | Manually Scheduled | Develop Strategy for Viking project | 6 days | 26/04/07 8:00 SA | 03/05/07 5:00 CH |  | 2
7 | Yes | Manually Scheduled | Review RE with customer | 3 days | 03/05/07 8:00 SA | 07/05/07 5:00 CH |  | 2
8 | Yes | Auto Scheduled | Inception & Elaboration | 14 days | 11/05/07 8:00 SA | 30/05/07 5:00 CH |  | 1
9 | Yes | Manually Scheduled | Produce User Requirement | 6 days | 11/05/07 8:00 SA | 18/05/07 5:00 CH |  | 2
10 | Yes | Manually Scheduled | Produce Viking Architecture Document | 5 days | 19/05/07 8:00 SA | 24/05/07 5:00 CH |  | 2
11 | Yes | Manually Scheduled | Produce Project Charter | 4 days | 11/05/07 8:00 SA | 16/05/07 5:00 CH |  | 2
12 | Yes | Manually Scheduled | Produce Project Plan | 10 days | 11/05/07 8:00 SA | 24/05/07 5:00 CH |  | 2
13 | Yes | Manually Scheduled | Develop High Level Design Document | 5 days | 19/05/07 8:00 SA | 24/05/07 5:00 CH |  | 2
14 | Yes | Manually Scheduled | Develop Detailed Level Design Document | 4 days | 25/05/07 8:00 SA | 30/05/07 5:00 CH |  | 2
15 | Yes | Manually Scheduled | Produce Test Plan (Unit Test and Integration Test) | 4 days | 25/05/07 8:00 SA | 30/05/07 5:00 CH |  | 2
16 | Yes | Manually Scheduled | Construction | 142 days | 28/05/07 8:00 SA | 11/12/07 5:00 CH |  | 1
17 | Yes | Auto Scheduled | Produce Viking Module Construction | 120 days | 28/05/07 8:00 SA | 09/11/07 5:00 CH |  | 2
18 | Yes | Manually Scheduled | Adding functionality in each subsequent work package | 20 days | 15/10/07 8:00 SA | 09/11/07 5:00 CH |  | 2
19 | Yes | Manually Scheduled | Address the work package | 6 days | 01/11/07 8:00 SA | 08/11/07 5:00 CH |  | 2
20 | Yes | Manually Scheduled | Package the deliverables | 8 days | 01/11/07 8:00 SA | 12/11/07 5:00 CH |  | 2
21 | Yes | Manually Scheduled | Test work package | 14 days | 22/11/07 8:00 SA | 11/12/07 5:00 CH |  | 2
22 | Yes | Manually Scheduled | Transition | 13 days | 30/11/07 8:00 SA | 18/12/07 5:00 CH |  | 1
23 | Yes | Manually Scheduled | Produce Viking Material | 2 days | 30/11/07 8:00 SA | 03/12/07 5:00 CH |  | 2
24 | Yes | Manually Scheduled | Perform acceptance testing | 12 days | 03/12/07 8:00 SA | 18/12/07 5:00 CH |  | 2
25 | Yes | Manually Scheduled | Produce Viking Product Document | 3 days | 09/12/07 8:00 SA | 11/12/07 5:00 CH |  | 2
26 | Yes | Manually Scheduled | Close - Out | 5 days | 18/12/07 8:00 SA | 24/12/07 5:00 CH |  | 1
27 | Yes | Manually Scheduled | Final review | 5 days | 18/12/07 8:00 SA | 24/12/07 5:00 CH |  | 2
28 | Yes | Manually Scheduled | Consume Lessons Learned | 5 days | 18/12/07 8:00 SA | 24/12/07 5:00 CH |  | 2
29 | Yes | Manually Scheduled | Produce Project Close out Document | 2 days | 21/12/07 8:00 SA | 24/12/07 5:00 CH |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Viking Architecture Team | V | Work |  |  |  |  | 100% | $0,00/h | 0
2 | Viking Development Team and Testing Team | V | Work |  |  |  |  | 100% | $0,00/h | 0
3 | Viking Development Team | V | Work |  |  |  |  | 100% | $0,00/h | 0
4 | ABC System testing team | A | Work |  |  |  |  | 100% | $0,00/h | 0
5 | Project Management Team | P | Work |  |  |  |  | 100% | $0,00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Produce basic schedule | Project Management Team | 0 | 10h | 100%
Develop Strategy for Viking project | Project Management Team | 0 | 36h | 100%
Review RE with customer | Project Management Team | 0 | 9h | 100%
Produce User Requirement | Project Management Team | 0 | 36h | 100%
Produce Viking Architecture Document | Viking Architecture Team | 0 | 30h | 100%
Produce Project Charter | Project Management Team | 0 | 24h | 100%
Produce Project Plan | Project Management Team | 0 | 60h | 100%
Develop High Level Design Document | Viking Architecture Team | 0 | 30h | 100%
Develop Detailed Level Design Document | Viking Architecture Team | 0 | 24h | 100%
Produce Test Plan (Unit Test and Integration Test) | Viking Development Team and Testing Team | 0 | 24h | 100%
Produce Viking Module Construction | Viking Development Team | 0 | 720h | 75%
Adding functionality in each subsequent work package | Viking Development Team | 0 | 120h | 100%
Address the work package | Viking Development Team | 0 | 36h | 100%
Package the deliverables | Viking Development Team | 0 | 48h | 100%
Test work package | Viking Development Team | 0 | 84h | 100%
Perform acceptance testing | ABC System testing team | 0 | 72h | 100%
Produce Viking Product Document | Viking Development Team | 0 | 18h | 100%
Final review | ABC System testing team | 0 | 30h | 100%
Consume Lessons Learned | Project Management Team | 0 | 30h | 100%
Produce Project Close out Document | Project Management Team | 0 | 12h | 100%