## Risk List
Risk List
Date Open | 18/4/2012
By: | Giang Nguyen, HIT Team member
Risk Analysis
Risk ID | Risk Title | Risk Description | Identified Date | Earliest Impact Date | Latest Impact Date | Risk Category | Risk Source | Impact to |  |  |  | Probability | Level | Exposure | Priority | Status | Mitigation Plan | Contigency Plan | Owner | Relevant Stakeholders | Become Issue? | Date Occurred
[8 empty] | Scope | Budget | Schedule | Quality
R-001 | Risk of Schedule | Estimate the time is too far from real |  |  |  | Process risks | Schedule | None | None | Catastrophic | None | 70% | High | 3.5 |  | Monitor | Negotiate with customer for the contribute budget for the project |  |  | Mr Hieu To | No
R-002 | Risk of Requirements | Change requirements or addition requirement |  |  |  | Customer risks | Requirement | Critical | Marginal | Marginal | Negligible | 90% | High | 3.6 |  | Control | Product owner re-analyze and re-priority the requirement. If the requirement have big impact to sprint then the sprint will be canceled and make new sprint |  |  | Mr Hieu To | No
R-003 | Risk of Schedule | Delayed schedule |  |  |  | Process risks | Schedule | Negligible | Significant | Catastrophic | None | 50% | High | 2.5 |  | Retired | Solve conflict |  |  | Mr Hieu To | No
R-004 | Risk of Budget | Estimated cost is failed |  |  |  | Others | Budget | Negligible | Catastrophic | None | None | 50% | High | 2.5 |  | Avoid | Analyze and calculate all estimation carefully Collecting historical data |  |  | Mr Hieu To | Yes
R-005 | Risk of Schedule | One developer delays his or her task |  |  |  | Process risks | Schedule | Marginal | Negligible | Critical | Negligible | 30% | Medium | 1.2 |  | Occur | Rework for time schedule estimation to ensure excuting project within time and budet |  |  | Mr Hieu To | Yes
R-006 | Risk of Development Team | Add or lack member to the team. |  |  |  | Process risks | Development Process | None | Negligible | Significant | None | 30% | Medium | 0.9 |  | Acknowledgment | Re-assign roles and responsibilities for project |  |  | Mr Hieu To | No
R-007 | Risk of Schedule | The release of specification is delayed |  |  |  | Process risks | Schedule | Critical | Critical | Critical | None | 30% | Medium | 1.2 |  | Control | Get requirements about the user interface of program from customer and re-design |  |  | Mr Hieu To | No
R-008 | Risk of Technology | Our chosen technology for client interaction might lead to miscommunication. |  |  |  | Technical risk | Work Environment | Critical | Negligible | Significant | Significant | 30% | Medium | 1.2 |  | Acknowledgment | Modify the process for appropriate of team and assign roles and responsibilities |  |  | Mr Hieu To | No
R-009 | Risk of Development Team | Team does not have a clear idea of individual productivity levels |  |  |  | Others | Development Process | Catastrophic | Critical | Critical | Critical | 30% | Medium | 1.5 |  | Monitor | Meet customer again to commit clearly requirements |  |  | Mr Hieu To | Yes
R-010 | Risk of Development Team | Team does not have clear sense of project big picture. |  |  |  | Others | Development Process | Catastrophic | Critical | Critical | Critical | 10% | Low | 0.5 | [5 empty] | Mr Hieu To
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
Note on Q7: Hieu To: 1. Acceptance: Acknowledgment of risk but not taking any action 2. Monitor: Watching and periodically re-evaluating the risk 3. Control: Taking active action to mitigate risk 4. Transfer: Reallocating risk to other entity. Do not consider it any more 5. Avoid: Changing or lowering requirements while still meeting the user's needs 6. Retired: The time to impact is passed. Do not consider it any more 7. Occur: Risk occured

## Risk Glossary
Risk Taxonomy
| Risk Category | Risk Source
| Technical risk | Requirement
| Resource risks | Design
| Process risks | Code & Unit Test
| Business risks | Integration & Test
| Customer risks | Engineering Specialties
| Others | Development Process
Development System
Management Process
Management Methods
Work Environment
Resources
Contract
Schedule
Budget
Marketing
Program Interfaces
Status | Name | Description
A | Acknowledgment | Acknowledgment of risk but not taking any action
M | Monitor | Watching and periodically re-evaluating the risk
C | Control | Taking active action to mitigate risk
T | Transfer | Reallocating risk to other entity. Do not consider it any more
V | Avoid | Changing or lowering requirements while still meeting the user's needs
R | Retired | The time to impact is passed. Do not consider it any more
O | Occur | Risk occured
# | Probability | Meaning
1 | 10% | Remote
2 | 30% | Unlikely
3 | 50% | Likely
4 | 70% | High Likely
5 | 90% | Near certainty
| Consequence | Value
| None | 0
| Negligible | 1
| Marginal | 2
| Significant | 3
| Critical | 4
| Catastrophic | 5
| Probability | Consequence
|  | 1 | 2 | 3 | 4 | 5
| 10% | Low | Low | Low | Low | Low
| 30% | Low | Low | Medium | Medium | Medium
| 50% | Low | Medium | Medium | Medium | High
| 70% | Low | Medium | Medium | High | High
| 90% | Medium | Medium | High | High | High