## Project Schedule
Project Schedule
Update 30/3/2012
Year | Task Name | Work | Duration | Start | Finish | Resource Names
1 | Planning | 54 hrs | 21 days | Mon 4/2/07 | Sun 4/29/07
| Train Team | 40 hrs | 14 days | Mon 4/2/07 | Thu 4/19/07
| Produce basic schedule | 10 hrs | 5 days | Fri 4/20/07 | Thu 4/26/07 | Project Management Team
| Project Management Team | 10 hrs |  | Fri 4/20/07 | Thu 4/26/07
| Conduct Team Meeting | 4 hrs | 2 days | Fri 4/20/07 | Mon 4/23/07
| Kick - Off | 45 hrs | 9 days | Thu 4/26/07 | Tue 5/8/07 | Project Management Team
| Develop Strategy for Viking project | 36 hrs | 6 days | Fri 4/27/07 | Fri 5/4/07 | Project Management Team
| Project Management Team | 36 hrs |  | Fri 4/27/07 | Fri 5/4/07
| Review RE with customer | 9 hrs | 3 days | Fri 4/27/07 | Tue 5/1/07 | Project Management Team
| Project Management Team | 9 hrs |  | Fri 4/27/07 | Tue 5/1/07 | Viking Architecture Team
| Inception & Elaboration | 228 hrs | 15 days | Mon 5/7/07 | Fri 5/25/07 | Project Management Team
| Produce User Requirement | 36 hrs | 6 days | Mon 5/7/07 | Mon 5/14/07 | Project Management Team
| Project Management Team | 36 hrs |  | Mon 5/7/07 | Mon 5/14/07 | Viking Architecture Team
| Produce Viking Architecture Document | 30 hrs | 5 days | Tue 5/15/07 | Mon 5/21/07 | Viking Architecture Team
| Viking Architecture Team | 30 hrs |  | Tue 5/15/07 | Mon 5/21/07 | Viking Development Team and Testing Team
| Produce Project Charter | 24 hrs | 4 days | Mon 5/7/07 | Thu 5/10/07
| Project Management Team | 24 hrs |  | Mon 5/7/07 | Thu 5/10/07 | Viking Development Team[75%]
| Produce Project Plan | 60 hrs | 10 days | Mon 5/7/07 | Fri 5/18/07 | Viking Development Team
| Project Management Team | 60 hrs |  | Mon 5/7/07 | Fri 5/18/07 | Viking Development Team
| Develop High Level Design Document | 30 hrs | 5 days | Tue 5/15/07 | Mon 5/21/07 | Viking Development Team
| Viking Architecture Team | 30 hrs |  | Tue 5/15/07 | Mon 5/21/07 | Viking Development Team
| Develop Detailed Level Design Document | 24 hrs | 4 days | Tue 5/22/07 | Fri 5/25/07
| Viking Architecture Team | 24 hrs |  | Tue 5/22/07 | Fri 5/25/07
| Produce Test Plan (Unit Test and Integration Test) | 24 hrs | 4 days | Tue 5/22/07 | Fri 5/25/07 | ABC System testing team
| Viking Development Team and Testing Team | 24 hrs |  | Tue 5/22/07 | Fri 5/25/07 | Viking Development Team
| Construction | 1,008 hrs | 142 days | Mon 5/28/07 | Tue 12/11/07
| Produce Viking Module Construction | 720 hrs | 120 days | Mon 5/28/07 | Fri 11/9/07 | ABC System testing team
| Viking Development Team | 720 hrs |  | Mon 5/28/07 | Fri 11/9/07 | Project Management Team
| Adding functionality in each subsequent work package | 120 hrs | 20 days | Mon 5/28/07 | Fri 6/22/07 | Project Management Team
| Viking Development Team | 120 hrs |  | Mon 5/28/07 | Fri 6/22/07
| Address the work package | 36 hrs | 6 days | Mon 6/25/07 | Mon 7/2/07
| Viking Development Team | 36 hrs |  | Mon 6/25/07 | Mon 7/2/07
| Package the deliverables | 48 hrs | 8 days | Tue 7/3/07 | Thu 7/12/07
| Viking Development Team | 48 hrs |  | Tue 7/3/07 | Thu 7/12/07
| Test work package | 84 hrs | 14 days | Mon 11/12/07 | Thu 11/29/07
| Viking Development Team | 84 hrs |  | Mon 11/12/07 | Thu 11/29/07
| Transition | 102 hrs | 13 days | Fri 11/30/07 | Tue 12/18/07
| Produce Viking Material | 12 hrs | 2 days | Fri 11/30/07 | Mon 12/3/07
| Perform acceptance testing | 72 hrs | 12 days | Fri 11/30/07 | Mon 12/17/07
| ABC System testing team | 72 hrs |  | Fri 11/30/07 | Mon 12/17/07
| Produce Viking Product Document | 18 hrs | 3 days | Fri 11/30/07 | Tue 12/4/07
| Viking Development Team | 18 hrs |  | Fri 11/30/07 | Tue 12/4/07
| Close - Out | 72 hrs | 5 days | Tue 12/18/07 | Mon 12/24/07
| Final review | 30 hrs | 5 days | Tue 12/18/07 | Mon 12/24/07
| ABC System testing team | 30 hrs |  | Tue 12/18/07 | Mon 12/24/07
| Consume Lessons Learned | 30 hrs | 5 days | Tue 12/18/07 | Mon 12/24/07
| Project Management Team | 30 hrs |  | Tue 12/18/07 | Mon 12/24/07
| Produce Project Close out Document | 12 hrs | 2 days | Tue 12/18/07 | Wed 12/19/07
| Project Management Team | 12 hrs |  | Tue 12/18/07 | Wed 12/19/07
2 & 3 | Support and Train for Customer | 1,080 hrs | 522 days | Tue 1/1/13 | Wed 12/31/14
| Maitain the system | 2,700 hrs | 522 days | Tue 1/1/13 | Wed 12/31/14
| Testing and Maitain before develop | 0 hrs | 64 days | Thu 1/1/15 | Tue 3/31/15
4 | Requirement | 0 hrs | 65 days | Fri 1/1/16 | Thu 3/31/16
| Tìm hiểu nhu cầu thị trường | 0 hrs | 14 days | Fri 1/1/16 | Wed 1/20/16
| Lấy yêu cầu | 0 hrs | 51 days | Thu 1/21/16 | Thu 3/31/16
| Planning | 0 hrs | 37 days | Fri 4/1/16 | Sat 5/21/16
| Train Team | 0 hrs | 22 days | Fri 4/1/16 | Sat 4/30/16
| Produce basic schedule | 0 hrs | 10 days | Tue 5/1/12 | Mon 5/14/12
| Conduct Team Meeting | 0 hrs | 7 days | Sun 5/15/16 | Sat 5/21/16
| Kick - Off | 0 hrs | 23 days | Sun 5/22/16 | Tue 6/21/16
| Develop Strategy for Viking project | 0 hrs | 13 days | Sun 5/22/16 | Tue 6/7/16
| Review RE with customer | 0 hrs | 10 days | Wed 6/8/16 | Tue 6/21/16
| Design | 0 hrs | 42 days | Wed 6/22/16 | Thu 8/18/16
| Produce User Requirement | 0 hrs | 8 days | Wed 6/22/16 | Fri 7/1/16
| Produce Viking Architecture Document | 0 hrs | 7 days | Fri 7/1/16 | Sun 7/10/16
| Viking Architecture Team | 0 hrs | 7 days | Fri 7/1/16 | Sun 7/10/16
| Produce Project Charter | 0 hrs | 5 days | Mon 7/11/16 | Fri 7/15/16
| Produce Project Plan | 0 hrs | 5 days | Sat 7/16/16 | Thu 7/21/16
| Develop High Level Design Document | 0 hrs | 8 days | Fri 7/22/16 | Tue 8/2/16
| Viking Architecture Team | 0 hrs | 8 days | Fri 7/22/16 | Tue 8/2/16
| Develop Detailed Level Design Document | 0 hrs | 10 days | Mon 8/1/16 | Fri 8/12/16
| Viking Architecture Team | 0 hrs | 10 days | Mon 8/1/16 | Fri 8/12/16
| Produce Test Plan (Unit Test and Integration Test) | 0 hrs | 5 days | Fri 8/12/16 | Thu 8/18/16
| Viking Development Team and Testing Team | 0 hrs | 5 days | Fri 8/12/16 | Thu 8/18/16
| Code | 0 hrs | 52 days | Fri 8/19/16 | Sun 10/30/16
| Produce Viking Module Construction | 0 hrs | 27 days | Fri 8/19/16 | Sun 9/25/16
| Viking Development Team | 0 hrs | 27 days | Fri 8/19/16 | Sun 9/25/16
| Adding functionality in each subsequent work package | 0 hrs | 11 days | Mon 9/26/16 | Sat 10/8/16
| Viking Development Team | 0 hrs | 11 days | Mon 9/26/16 | Sat 10/8/16
| Address the work package | 0 hrs | 11 days | Sun 10/9/16 | Fri 10/21/16
| Viking Development Team | 0 hrs | 11 days | Sun 10/9/16 | Fri 10/21/16
| Package the deliverables | 0 hrs | 7 days | Sat 10/22/16 | Sun 10/30/16
| Viking Development Team | 0 hrs | 7 days | Sat 10/22/16 | Sun 10/30/16
| Test | 0 hrs | 15 days | Tue 11/1/16 | Mon 11/21/16
| Test work package | 0 hrs | 15 days | Tue 11/1/16 | Mon 11/21/16
| Viking Development Team | 0 hrs | 15 days | Tue 11/1/16 | Mon 11/21/16
| Close - Out | 0 hrs | 15 days | Tue 11/22/16 | Sat 12/10/16
| Final review | 0 hrs | 5 days | Tue 11/22/16 | Sun 11/27/16
| ABC System testing team | 0 hrs | 5 days | Tue 11/22/16 | Sun 11/27/16
| Consume Lessons Learned | 0 hrs | 6 days | Mon 11/28/16 | Mon 12/5/16
| Project Management Team | 0 hrs | 6 days | Mon 11/28/16 | Sun 12/4/16
| Produce Project Close out Document | 0 hrs | 6 days | Mon 12/5/16 | Sat 12/10/16
| Project Management Team | 0 hrs | 6 days | Mon 12/5/16 | Sat 12/10/16

## Project Budget Summary
Project Budget Summary
Year | Category | Detail | Cost ($) | Total
1st year | Developing expense | Salary | 284570 | 536570
|  | Bonus | 2000
|  | Trainning team | 10000
|  | Travel business | 5000
|  | Team building | 5000
| Risk management expense |  | 60000
| Change management expense |  | 60000
| Equipment (Hardware & Software) |  | 20000
| Facility expense |  | 20000
| Contingency expense |  | 70000
2nd and 3rd year | Maintenance | Team Maintenance | 54000 | 121500
| Training customer | Team Training | 67500
4th year | Maintenance |  | 27000 | 269170
| Developing expense | Salary | 98670
|  | Bonus | 500
|  | Travel business | 1000
|  | Team building | 2000
| Risk management expense |  | 20000
| Change management expense |  | 20000
| Equipment (Hardware & Software) |  | 20000
| Facility expense |  | 20000
| Contingency expense |  | 60000

## Resource Allocation
Viking Estimated Resource Allocation
No. | Role | Allocation
Year 01
1 | PM | 1
2 | Developer | 4
3 | Architect | 1
4 | Risk Manager | 1
5 | Change manager | 1
6 | Requirement Engineer | 2
7 | Tester | 2
8 | Quality Assurance Manager | 1
Year 2
1 | Mantaining Member | 3
2 | Training Member | 3
Year 03
1 | Mantaining Member | 1
2 | Training Member | 1
Year 04
1 | PM | 1
2 | Developer | 2
3 | Risk Manager | 1
4 | Change manager | 1
5 | Requirement Engineer | 1
6 | Tester | 2
7 | Designer | 1

## Project Budget Data Entry
Project Budget Data Entry
| Position | Work Hour | Hour Rate | Total Hour | Total Cost | From (month) | To (month)
Year 1 | PM | 2 | 100 | 396 | 39600 | 4 | 12
| Developer 1 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 2 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 3 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 4 | 4 | 60 | 528 | 31680 | 6 | 11
| Architect | 3 | 150 | 132 | 19800 | 2 | 3
| Risk Manager | 2 | 75 | 88 | 6600 | 5 | 6
| Change manager | 2 | 75 | 88 | 6600 | 5 | 6
| Requirement Engineer 1 | 6 | 75 | 264 | 19800 | 4 | 5
| Requirement Engineer 2 | 6 | 75 | 264 | 19800 | 4 | 5
| Tester 1 | 3 | 75 | 132 | 9900 | 11 | 12
| Tester 2 | 3 | 75 | 66 | 4950 | 12 | 12
| Quality Assurance Manager | 2 | 100 | 308 | 30800 | 4 | 10
Total |  |  |  |  | 284570
Year 2 | Mantaining Member 1 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 2 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 3 | 3 | 50 | 180 | 27000 | 1 | 12
| Training Member 1 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 2 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 3 | 3 | 50 | 450 | 22500 | 1 | 12
Total |  |  |  |  | 60750
Year 3 | Mantaining Member 1 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 2 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 3 | 3 | 50 | 180 | 27000 | 1 | 12
| Training Member 1 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 2 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 3 | 3 | 50 | 450 | 22500 | 1 | 12
Total |  |  |  |  | 60750
Year 4 | PM | 2 | 100 | 132 | 13200 | 4 | 9
| Developer 1 | 4 | 60 | 352 | 21120 | 5 | 8
| Developer 2 | 4 | 75 | 352 | 26400 | 5 | 8
| Risk Manager | 2 | 75 | 44 | 3300 | 4 | 4
| Change manager | 2 | 75 | 44 | 3300 | 4 | 4
| Requirement Engineer | 6 | 75 | 66 | 4950 | 4 | 4
| Tester 1 | 3 | 75 | 132 | 9900 | 9 | 9
| Tester 2 | 3 | 75 | 132 | 9900 | 9 | 9
| Designer | 3 | 100 | 66 | 6600 | 4 | 4
Total |  |  |  |  | 98670