## Risk List
Viking Risk List
Risk ID | Specific risk | Risk Category | Likelihood | Consequence | Risk Rating | Risk Treatment Options
R-001 | The release time was delayed | Vendor | Almost certain | Major | High | Conduct a meeting to increase schedule
R-002 | Project had been over budget | Budget | Likely | Moderate | Medium
R-003 | Lack of experience in new tools | Development Team | Unlikely | Moderate | Low
R-004 | Lack of human resource in some phase | Resource | Possible | Moderate | Medium
R-005 | Change requirements or addition requirement | Requirement | Possible | Major | High
R-006 | New technology need to use for project is complex | Technology | Unlikely | Major | Medium
R-007 | Unforeseen changes in expenditure and/or income during the year | Budget | Likely | Major | High | A monthly system of budget monitoring is operated to try to identify changes as soon as possible.
R-008 | Length of time necessary to meet a milestone was stretched unexpected | Schedule | Likely | Moderate | Medium
R-009 | Sponsor reduce their funding contribution | Customer | Unlikely | Major | Medium
R-010 | Project facilities location was moved to another place | Migration | Rare | Moderate | Low
R-011 | Wrong time estimation | Schedule | Possible | Moderate | Medium
R-012 | Unexpected project scope expansions lead to stretch schedule | Schedule | Possible | Major | High
R-013 | Wrong budget estimation lead to cost overruns | Budget | Almost certain | Major | High
R-014 | Unrealistic schedules lead to frustrated members | Schedule | Likely | Moderate | Low
R-015 | Inexperience of project manager | Senior Management | Possible | Catastrophic | High
R-016 | Inexperience of team members, lack of training | Resource | Possible | Moderate | Medium
R-017 | Reorganization resulting in loss of team members | Resource | Unlikely | Moderate | Low

## Risk Priorities
Likelihood | Consequence
| Catastrophic | Major | Moderate | Minor | Insignificant
Almost certain | R-001 | R-005 | R-007 | R-011 | R-010
Likely | R-015 | R-012 | R-002 | R-014 | R-003
Possible | R-013 | R-004 | R-017
Unlikely | R-006 | R-016
Rare | R-008 | R-009

## Top 10 risk
Top 10 Risk
Risk ID | Specific risk | Risk Category | Likelihood | Consequence | Risk Rating | Risk Treatment Options
R-001 | The release time was delayed | Vendor | Almost certain | Major | High
R-002 | Project had been over budget | Budget | Likely | Moderate | Medium
R-004 | Lack of human resource in some phase | Resource | Possible | Moderate | Medium
R-005 | Change requirements or addition requirement | Requirement | Possible | Major | High
R-006 | New technology need to use for project is complex | Technology | Unlikely | Major | Medium
R-007 | Unforeseen changes in expenditure and/or income during the year | Budget | Likely | Major | High | A monthly system of budget monitoring is operated to try to identify changes as soon as possible.
R-011 | Wrong time estimation | Schedule | Possible | Moderate | Medium
R-012 | Unexpected project scope expansions lead to stretch schedule | Schedule | Possible | Major | High
R-013 | Wrong budget estimation lead to cost overruns | Budget | Almost certain | Major | High
R-015 | Inexperience of project manager | Senior Management | Possible | Catastrophic | High