## Slide 1: Software Measurement and Analysis
Team Assignment
13

## Slide 2
Assumption
Work Breakdown Structure
Wideband Delphi
Schedule, Budget and Resource Estimates
Contents

## Slide 3
These are the project team's assumptions make before give estimate for Viking
Project conducted with the participation of seven roles, including 12 members
    1 Project Manager
    1 Architect Manager
    1 Change Manager
    2 Requirement Engineer
    1 Risk Manager
    4 Developers
    2 Testers
Project assumptions

## Slide 4
Effort of members in Wideband Delphi was estimated in person hours, we will turn into person month to ease when estimate schedule
  Assume that 1 person day = 8 person hours and 1 person month = 17.5 person days. (Excluding non-productive hours e.g. sickness, holidays, maternity leave, lunch breaks etc.)
  Therefore, 1 person month = 140 person hours.
Project assumptions

## Slide 5
When calculate Deviation Calculation in Wideband Delphi, assume that divisor equal 2.6 with estimation accuracy rate is 80%. Because lack of historical data and team’s ability.
Project assumptions

## Slide 6
  Task Assumption: the assumptions of participants made on each task when estimate the effort of Viking, refer to Viking_Delphi_Estimation.xls
Task assumptions

## Slide 7
Reason to make task assumption:
  Team members make assumptions about the work to be done in order to deal with incomplete information
    Any time an estimate must be based on a decision that has not yet been made, team members can assume the answer for the sake of the estimate
    Assumptions must be written down so that if they prove to be incorrect and cause the estimate to be inaccurate, everyone understands what happened
    Assumptions bring the team together very early on in the project so they can make progress on important decisions that will affect development
Task assumptions

## Slide 8
Assumption
Work Breakdown Structure
Wideband Delphi
Schedule, Budget and Resource Estimates
Contents

## Slide 9
A work breakdown structure (WBS), in project management and systems engineering, is a deliverable oriented decomposition of a project into smaller components.
It defines and groups a project's discrete work elements in a way that helps organize and define the total work scope of the project.
Refer to Work Breakdown Structure.jpeg
Work Breakdown Structure

## Slide 10
Assumption
Work Breakdown Structure
Wideband Delphi
Schedule, Budget and Resource Estimates
Contents

## Slide 11
Wideband Delphi is a process that a team can use to generate an estimate
  The project manager chooses an estimation team, and gains consensus among that team on the results
  Wideband Delphi is a repeatable estimation process because it consists of a straightforward set of steps that can be performed the same way each time
Wideband Delphi

## Slide 12
12
Wideband Delphi
Team Steps
Choose
the team
Kickoff
Meeting
Individual
Preparation
Estimation
Session
Assemble
Tasks
Review
Results

## Slide 13
Step : Choose the team
  All members of team 22 will join to estimate team
Wideband Delphi

## Slide 14
Step : Kickoff Meeting
  Make sure that each team member understands the Delphi process
  The team brainstorms and writes down project assumptions.
  The team generates a WBS.
  The team agrees on a unit of estimation is person hours
Wideband Delphi

## Slide 15
Step : Individual Preparation
  Each team member independently generates a set of preparation results.
  For each task, the team member writes down an estimate for the effort required to complete the task, and any additional assumptions (task assumption) he needed to make in order to generate the estimate.
Wideband Delphi

## Slide 16
Step : Estimation Session
  During the estimation session, the team comes to a consensus on the effort required for each task in the WBS.
  Each team member fills out an estimation form which contains his estimates.
  The rest of the estimation session is divided into rounds during which each estimation team member revises her estimates based on a group discussion. Individual numbers are not discussed.
Wideband Delphi

## Slide 17
Step : Estimation Session
  The moderator collects the estimation forms and plots the sum of the effort from each form on a line: estimations maybe not converge.
  The team resolves any issues or disagreements that are brought up. Individual estimate times are not discussed. These disagreements are usually about the tasks themselves. Disagreements are often resolved by adding assumptions.
Wideband Delphi

## Slide 18
Step : Estimation Session
  The estimators all revise their individual estimates. The moderator updates the plot with the new total.
  The moderator leads the team through several rounds of estimates to gain consensus on the estimates. The estimation session continues until the estimates converge or the team is unwilling to revise estimates.
Wideband Delphi

## Slide 19
Step : Assemble Tasks
  The project manager works with the team to collect the estimates from the team members at the end of the meeting and compiles the final task list, estimates and assumptions.
Wideband Delphi

## Slide 20
Step : Assemble Tasks
  The project manager reviews the final task list with the estimation team.
  Wideband Delphi result please refer to Viking Delphi Estimation.xls
Wideband Delphi

## Slide 21
Assumption
Work Breakdown Structure
Wideband Delphi
Schedule, Budget and Resource Estimates
Contents

## Slide 22
  Schedule Estimate
  Based on estimations of the participants was calculated in hours and the above project assumption we can calculate the time to complete each task in month.
  Schedule can be estimated based on the total time to complete the all tasks. In sheet Resource Allocation of Viking_Delphi_Estimation.xls we were calculated that Viking will long for about 9 months.
Schedule, Budget and Resource Estimates

## Slide 23
  Resource Estimate
  After created Work Breakdown Structure and Schedule, we assigned resource for each task, including the roles and number of member need to do that task. For detail please refer to sheet Resource Allocation of Viking_Delphi_Estimation.xls
Schedule, Budget and Resource Estimates

## Slide 24
  Budget Estimate
  When resources are assigned to each task we can calculate the salary of Viking, in addition we also have another expense was described in sheet Project Budget Summary of Viking_Delphi_Estimation.xls
Schedule, Budget and Resource Estimates

## Slide 25
Thanks for your listening
THE END