## EVM
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
Setup and Project Management
BCWS | 364 | 596 | 620 | 640 | 660 | 680 | 700 | 720 | 740 | 760 | 780 | 800 | 820 | 840 | 860 | 880 | 900 | 920 | 940 | 960 | 980 | 1000 | 1020 | 1040 | 1060 | 1080 | 1100 | 1120 | 1140 | 1160 | 1180 | 1200 | 1220 | 1240 | 1260 | 1280 | 1300 | 1320 | 1340 | 1360 | 1380 | 1400 | 1420 | 1440 | 1460 | 1480 | 1480 | 1480
BCWP | 311.98 | 596 | 620 | 640 | 660 | 680 | 700 | 720 | 740 | 760 | 780 | 800 | 820 | 840 | 860 | 880 | 900 | 920 | 940 | 960 | 980 | 1000 | 1020 | 1040 | 1060 | 1080 | 1100 | 1120
ACWP | 364 | 564 | 588 | 608 | 628 | 648 | 668 | 688 | 708 | 728 | 748 | 768 | 788 | 808 | 828 | 848 | 868 | 888 | 904 | 924 | 944 | 964 | 984 | 1004 | 1024 | 1044 | 1064 | 1084
Release 1 - Deliver GUI & User Documentation
BCWS |  |  | 136 | 216 | 344 | 488 | 664 | 784 | 868 | 972 | 1092 | 1140 | 1180 | 1316 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332
BCWP |  |  | 104 | 184 | 312 | 444.28 | 568.7617 | 718.2183 | 819.8767 | 936 | 1064.8 | 1136.8 | 1151.345 | 1248.8 | 1320.35 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332 | 1332
ACWP |  |  | 104 | 184 | 312 | 448 | 528 | 648 | 776 | 900 | 1024 | 1096 | 1108 | 1212 | 1280 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292 | 1292
Release 2 - Deliver Online Product
BCWS |  |  | 144 | 346.6667 | 501.3334 | 589.3334 | 613.3334 | 693.3335 | 784.0002 | 981.5285 | 1141.5285 | 1280.1952 | 1360.1952 | 1440.1952 | 1536.1952 | 1616.1952 | 1696.1952 | 1856.1952 | 2056.1952 | 2256.1952 | 2408.1952 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619
BCWP |  |  | 51.5533 | 151.11 | 224 | 312 | 328 | 722.8619 | 722.8619 | 735.5835 | 759.6802 | 890.8619 | 972.9335 | 1146.8619 | 1272.1952 | 1349.5285 | 1429.5285 | 1509.5285 | 1589.5285 | 1669.5285 | 1869.5285 | 2069.5285 | 2245.5285 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619 | 2434.8619
ACWP |  |  | 48 | 152 | 224 | 312 | 328 | 428 | 428 | 460 | 500 | 636 | 712 | 876 | 1004 | 1080 | 1160 | 1240 | 1320 | 1400 | 1600 | 1800 | 1976 | 2164 | 2164 | 2164 | 2164 | 2164
Release 3 - Deliver Offline Product
BCWS |  |  | 31.1 | 45.3333 | 58.6667 | 58.6667 | 58.6667 | 58.6667 | 58.6667 | 98.4717 | 148.9433 | 252.8867 | 274.61 | 357.44 | 448.1633 | 528.1633 | 608.1633 | 688.1633 | 768.1633 | 848.1633 | 928.1633 | 1250.83 | 1520.1633 | 1685.4967 | 1840.4083 | 2005.0883 | 2116.4083 | 2556.4083 | 2974.7483 | 3154.7483 | 3421.3333 | 3861.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333 | 4037.3333
BCWP |  |  | 0 | 26.6667 | 53.3333 | 53.3333 | 53.3333 | 53.3333 | 53.3333 | 53.3333 | 108.5483 | 124.7567 | 163.8067 | 219.68 | 275.0467 | 384.2567 | 464.22 | 544.22 | 626.1567 | 700.1867 | 789.62 | 862.38 | 944.1033 | 1071.0633 | 1432.38 | 1632.38 | 1826.6883 | 1953.7583
ACWP |  |  | 0 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 104 | 128 | 160 | 218 | 278 | 386 | 466 | 546 | 626 | 706 | 788 | 866 | 946 | 1082 | 1435 | 1628 | 1784 | 1880
Release 4 - Deliver Final Product
BCWS | [35 empty] | 1264 | 1312 | 1448 | 1648 | 1848 | 2048 | 2248 | 2448 | 2648 | 2856 | 2864 | 2864 | 2864
BCWP | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACWP | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.09 | 253.09 | 253.09 | 253.09 | 57.94
Total
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
BCWS | 364 | 596 | 931.1 | 1248 | 1564 | 1816.0001 | 2036.0001 | 2256.0002 | 2450.6669 | 2812.0002 | 3162.4718 | 3473.0819 | 3634.8052 | 3953.6352 | 4176.3585 | 4356.3585 | 4536.3585 | 4796.3585 | 5096.3585 | 5396.3585 | 5648.3585 | 6017.6919 | 6307.0252 | 6492.3585 | 6667.2702 | 6851.9502 | 6983.2702 | 7443.2702 | 7881.6102 | 8081.6102 | 8368.1952 | 8828.1952 | 9024.1952 | 9044.1952 | 9064.1952 | 10348.1952 | 10416.1952 | 10572.1952 | 10792.1952 | 11012.1952 | 11232.1952 | 11452.1952 | 11672.1952 | 11892.1952 | 12120.1952 | 12148.1952 | 12148.1952 | 12148.1952
BCWP | 311.98 | 596 | 775.5533 | 1001.7767 | 1249.3333 | 1489.6133 | 1650.095 | 2214.4135 | 2336.0718 | 2484.9169 | 2713.0285 | 2952.4185 | 3108.0852 | 3455.3419 | 3727.5919 | 3945.7852 | 4125.7485 | 4305.7485 | 4487.6852 | 4661.7152 | 4971.1485 | 5263.9085 | 5541.6319 | 5877.9252 | 6259.2419 | 6479.2419 | 6693.5502 | 6840.6202
ACWP | 364 | 564 | 740 | 964 | 1204 | 1448 | 1564 | 1804 | 1952 | 2128 | 2376 | 2628 | 2768 | 3114 | 3390 | 3606 | 3786 | 3966 | 4142 | 4322 | 4624 | 4922 | 5198 | 5542 | 5915 | 6128 | 6304 | 6420
CV | -52.02 | 32 | 35.5533 | 37.7767 | 45.3333 | 41.6133 | 86.095 | 410.4135 | 384.0718 | 356.9169 | 337.0285 | 324.4185 | 340.0852 | 341.3419 | 337.5919 | 339.7852 | 339.7485 | 339.7485 | 345.6852 | 339.7152 | 347.1485 | 341.9085 | 343.6319 | 335.9252 | 344.2419 | 351.2419 | 389.5502 | 420.6202
SV | -52.02 | 0 | -155.5467 | -246.2233 | -314.6667 | -326.3868 | -385.9051 | -41.5867 | -114.595 | -327.0833 | -449.4433 | -520.6633 | -526.72 | -498.2933 | -448.7667 | -410.5733 | -410.61 | -490.61 | -608.6733 | -734.6433 | -677.21 | -753.7833 | -765.3933 | -614.4333 | -408.0283 | -372.7083 | -289.72 | -602.65
CPI | 0.85709 | 1 | 0.83294 | 0.80271 | 0.79881 | 0.82027 | 0.81046 | 0.98157 | 0.95324 | 0.88368 | 0.85788 | 0.85009 | 0.85509 | 0.87397 | 0.89255 | 0.90575 | 0.90948 | 0.89771 | 0.88057 | 0.86386 | 0.8801 | 0.87474 | 0.87864 | 0.90536 | 0.9388 | 0.94561 | 0.95851 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903 | 0.91903
SPI | 0.85709 | 1.0567 | 1.048 | 1.0392 | 1.0377 | 1.0287 | 1.055 | 1.2275 | 1.1968 | 1.1677 | 1.1418 | 1.1234 | 1.1229 | 1.1096 | 1.0996 | 1.0942 | 1.0897 | 1.0857 | 1.0835 | 1.0786 | 1.0751 | 1.0695 | 1.0661 | 1.0606 | 1.0582 | 1.0573 | 1.0618 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655 | 1.0655
ETC | [27 empty] | 6420 | 7396.9821 | 7584.6844 | 7853.6478 | 8285.3631 | 8469.3113 | 8488.0816 | 8506.8518 | 9711.9006 | 9775.7194 | 9922.1272 | 10128.5997 | 10335.0723 | 10541.5448 | 10748.0173 | 10954.4899 | 11160.9624 | 11374.943 | 11401.2214 | 11401.2214 | 11401.2214 | 11638.7493 | 11876.2771 | 12113.805 | 12351.3329 | 12405.7103
Projected Program Delay | [27 empty] | 6840.62 | 8575.9724 | 8793.5922 | 9105.425 | 9605.9506 | 9819.218 | 9840.98 | 9862.742 | 11259.8611 | 11333.8518 | 11503.5953 | 11742.9771 | 11982.3589 | 12221.7406 | 12461.1224 | 12700.5042 | 12939.886 | 13187.9726 | 13218.4394 | 13218.4394 | 13218.4394
BAC | 12148.2
VAC | -257.49
ISAC | 52.2287
IEAC | 11401.2241

## Project Budget Summary
Project Budget Summary
Year | Category | Detail | Total
1st year | Developing expense | 323760 | 553760
| Risk management expense | 60000
| Change management expense | 60000
| Equipment (Hardware & Software) | 20000
| Facility expense | 20000
| Contingency expense | 70000
2nd and 3rd year | Maintenance | 54000 | 121500
| Training customer | 67500
4th year | Maintenance | 27000 | 269170
| Developing expense | 102170
| Risk management expense | 20000
| Change management expense | 20000
| Equipment (Hardware & Software) | 20000
| Facility expense | 20000
| Contingency expense | 60000

## Compared 2010 vs 2009
| Physical Environment | System, Tools and Processes | Motivation | Emotional Environment | Management | Looking for another job
2009 | 7.4 | 5.65 | 4.75 | 16.1 | 4.27 | 0.4
2010 | 5.2 | 2.3 | 3.1 | 12.27 | 2.4 | 0.27
As you can see from the graph, the physical environment decreased from 7.4 in 2009 to a number of 5.2 in 2010, that proves the team doesn't
more satisfier the physical environment in 2010 than 2009. System, tools and processes that fall sharply throughout from 2009 - 2010 (from 5.65
in 2009 fall to 2.3 in 2010). That is the same for motivation, compared to 2010, the point in 2009 is higher, in specific, 4.75 in 2009 and 3.1 in 2010
For emotional environment that is the highest point of all group in both 2009 and 2010, but the point in 2009 also higher than the point in 2010 (from 16.1 drop to 12.27)
Besides, the management looks like similar to all of the before comparision, that decreased from 2009 with 4.27 point to 2010 with 2.4 point
All of figures to prove that, the team morale in 2009 is higher than 2010. However, the people looking for another job in 2010 is rose slightly for 2009 but this rate is very low.

## Defect History
# | Severity | OS | Date | Week | Assigned to | Status | Abstract
4 | 1 | Windows | 2010-07-06 | 1 |  | Open | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-13 | 1 |  | Approved | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-13 | 1 | Anjuli | Assigned | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-15 | 2 |  | Resolved | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-17 | 2 |  | Tested | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-17 | 3 |  | Closed | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-17 | 4 |  | Closed | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-17 | 5 |  | Closed | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-17 | 6 |  | Closed | opening a new window can freeze Viking
4 | 1 | Windows | 2010-07-17 | 7 |  | Closed | opening a new window can freeze Viking
6 | 1 | Windows | 2010-07-06 | 1 |  | Open | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-12 | 1 |  | Approved | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-13 | 2 | Anjuli | Assigned | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-21 | 3 |  | Resolved | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-24 | 3 |  | Tested | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-24 | 4 |  | Closed | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-24 | 5 |  | Closed | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-24 | 6 |  | Closed | lock-up when opening a new page from PDF or Windows Mail
6 | 1 | Windows | 2010-07-24 | 7 |  | Closed | lock-up when opening a new page from PDF or Windows Mail
10 | 1 | Windows | 2010-07-07 | 1 |  | Open | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-12 | 1 |  | Approved | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-14 | 2 | Bob | Assigned | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-19 | 2 |  | Resolved | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-19 | 2 |  | Tested | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-19 | 3 |  | Closed | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-19 | 4 |  | Closed | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-19 | 5 |  | Closed | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-19 | 6 |  | Closed | Viking crashes under Windows when File/Import... is clicked
10 | 1 | Windows | 2010-07-19 | 7 |  | Closed | Viking crashes under Windows when File/Import... is clicked
11 | 1 | Windows | 2010-07-07 | 1 |  | Open | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-12 | 1 |  | Approved | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-13 | 2 | Anjuli | Assigned | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-19 | 2 |  | Resolved | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-19 | 2 |  | Tested | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-19 | 3 |  | Closed | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-19 | 4 |  | Closed | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-19 | 5 |  | Closed | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-19 | 6 |  | Closed | POST data is lost when submitting a form that is embedded in a HTML email
11 | 1 | Windows | 2010-07-19 | 7 |  | Closed | POST data is lost when submitting a form that is embedded in a HTML email
12 | 1 | Windows | 2010-07-08 | 1 |  | Open | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-12 | 1 |  | Approved | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-13 | 2 | Bob | Assigned | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-19 | 2 |  | Resolved | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-19 | 2 |  | Tested | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-19 | 3 |  | Closed | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-19 | 4 |  | Closed | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-19 | 5 |  | Closed | Viking process runs, but no window opens | #REF!
12 | 1 | Windows | 2010-07-19 | 6 |  | Closed | Viking process runs, but no window opens
12 | 1 | Windows | 2010-07-19 | 7 |  | Closed | Viking process runs, but no window opens
16 | 1 | Windows | 2010-07-13 | 2 |  | Open | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-19 | 2 |  | Approved | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-21 | 3 |  | Resolved | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-24 | 3 |  | Tested | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-24 | 4 |  | Closed | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-24 | 5 |  | Closed | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-24 | 6 |  | Closed | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
16 | 1 | Windows | 2010-07-24 | 7 |  | Closed | After viewing a few web pages Viking says stopped on the status bar and I cannot resume.
17 | 1 | Windows | 2010-07-13 | 2 |  | Open | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-19 | 2 |  | Approved | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-19 | 2 | Bob | Assigned | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-21 | 3 |  | Resolved | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-24 | 3 |  | Tested | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-24 | 4 |  | Closed | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-24 | 5 |  | Closed | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-24 | 6 |  | Closed | Stack overflow; cyclic infinite recursion in .dll
17 | 1 | Windows | 2010-07-24 | 7 |  | Closed | Stack overflow; cyclic infinite recursion in .dll
21 | 1 | Windows | 2010-07-13 | 2 |  | Open | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-19 | 2 |  | Approved | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-21 | 3 |  | Resolved | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-24 | 3 |  | Tested | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-24 | 4 |  | Closed | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-24 | 5 |  | Closed | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-24 | 6 |  | Closed | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
21 | 1 | Windows | 2010-07-24 | 7 |  | Closed | Viking freezes when rendering "javaprxy.dll" COM Object Exploit
22 | 1 | Windows | 2010-07-13 | 2 |  | Open | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-19 | 2 |  | Approved | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-19 | 2 | Bob | Assigned | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-21 | 3 |  | Resolved | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-24 | 3 |  | Tested | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-24 | 4 |  | Closed | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-24 | 5 |  | Closed | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-24 | 6 |  | Closed | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
22 | 1 | Windows | 2010-07-24 | 7 |  | Closed | alert() in onFocus causes infinite loop of alerts (onfocus triggered after each alert)
36 | 1 | Windows | 2010-07-19 | 3 |  | Open | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-26 | 3 |  | Approved | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-26 | 3 | Bob | Assigned | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-27 | 3 |  | Resolved | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-29 | 3 |  | Tested | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-30 | 4 |  | Closed | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-30 | 5 |  | Closed | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-30 | 6 |  | Closed | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
36 | 1 | Windows | 2010-07-30 | 7 |  | Closed | Error: uncaught exception: [Exception... "Failure" nsresult: "0x80004005 (NS_ERROR_FAILURE)" location: "JS frame :: https://www.aaa.bbb/cccccc ::
37 | 1 | Windows | 2010-07-19 | 3 |  | Open | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-26 | 3 |  | Approved | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-26 | 3 | Bob | Assigned | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-27 | 3 |  | Resolved | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-29 | 3 |  | Tested | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-30 | 4 |  | Closed | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-30 | 5 |  | Closed | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-30 | 6 |  | Closed | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
37 | 1 | Windows | 2010-07-30 | 7 |  | Closed | crash trying to access leaderboard [@ 0x30096b42] [@ PluginWindowEvent_Handle]
38 | 1 | Windows | 2010-07-19 | 3 |  | Open | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-26 | 3 |  | Approved | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-26 | 3 | Anjuli | Assigned | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-27 | 3 |  | Resolved | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-29 | 3 |  | Tested | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-30 | 4 |  | Closed | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-30 | 5 |  | Closed | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-30 | 6 |  | Closed | Viking caused an invalid page fault
38 | 1 | Windows | 2010-07-30 | 7 |  | Closed | Viking caused an invalid page fault
44 | 1 | Windows | 2010-07-21 | 3 |  | Open | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-26 | 3 |  | Approved | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-26 | 3 | Bob | Assigned | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-27 | 3 |  | Resolved | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-29 | 3 |  | Tested | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-30 | 4 |  | Closed | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-30 | 5 |  | Closed | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-30 | 6 |  | Closed | When double-clicking on Notifier, Viking opens and freezes
44 | 1 | Windows | 2010-07-30 | 7 |  | Closed | When double-clicking on Notifier, Viking opens and freezes
48 | 1 | Windows | 2010-07-26 | 4 |  | Open | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
48 | 1 | Windows | 2010-08-02 | 4 |  | Approved | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
48 | 1 | Windows | 2010-08-02 | 4 | Anjuli | Assigned | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
48 | 1 | Windows | 2010-08-04 | 4 |  | Resolved | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
48 | 1 | Windows | 2010-08-04 | 4 |  | Tested | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
48 | 1 | Windows | 2010-08-04 | 5 |  | Closed | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
48 | 1 | Windows | 2010-08-04 | 6 |  | Closed | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
48 | 1 | Windows | 2010-08-04 | 7 |  | Closed | Illegal operation when accessing, or leaving encrypted pages, incl. Viking Support page.
50 | 1 | Windows | 2010-07-26 | 4 |  | Open | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
50 | 1 | Windows | 2010-08-02 | 4 |  | Approved | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
50 | 1 | Windows | 2010-08-02 | 4 | Anjuli | Assigned | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
50 | 1 | Windows | 2010-08-04 | 4 |  | Resolved | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
50 | 1 | Windows | 2010-08-04 | 4 |  | Tested | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
50 | 1 | Windows | 2010-08-04 | 5 |  | Closed | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
50 | 1 | Windows | 2010-08-04 | 6 |  | Closed | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
50 | 1 | Windows | 2010-08-04 | 7 |  | Closed | Simple string-doubling loop causes Vikingto take up 100% CPU and 100% RAM
63 | 1 | Windows | 2010-07-29 | 4 |  | Open | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
63 | 1 | Windows | 2010-08-02 | 4 |  | Approved | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
63 | 1 | Windows | 2010-08-02 | 4 | Bob | Assigned | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
63 | 1 | Windows | 2010-08-04 | 4 |  | Resolved | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
63 | 1 | Windows | 2010-08-04 | 4 |  | Tested | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
63 | 1 | Windows | 2010-08-04 | 5 |  | Closed | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
63 | 1 | Windows | 2010-08-04 | 6 |  | Closed | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
63 | 1 | Windows | 2010-08-04 | 7 |  | Closed | Viking does not start when I click on the icon or the .exe application - use windows vista home premium
64 | 1 | Windows | 2010-08-02 | 7 |  | Open | document.domain script causes javascript to not render css or page properly
64 | 1 | Windows | 2010-08-02 | 7 |  | Approved | document.domain script causes javascript to not render css or page properly
64 | 1 | Windows | 2010-08-02 | 7 | Anjuli | Assigned | document.domain script causes javascript to not render css or page properly
64 | 1 | Windows | 2010-08-04 | 7 |  | Resolved | document.domain script causes javascript to not render css or page properly
64 | 1 | Windows | 2010-08-04 | 7 |  | Tested | document.domain script causes javascript to not render css or page properly
64 | 1 | Windows | 2010-08-04 | 5 |  | Closed | document.domain script causes javascript to not render css or page properly
64 | 1 | Windows | 2010-08-04 | 6 |  | Closed | document.domain script causes javascript to not render css or page properly
64 | 1 | Windows | 2010-08-04 | 7 |  | Closed | document.domain script causes javascript to not render css or page properly
68 | 1 | Windows | 2010-08-04 | 5 |  | Open | Personalized items are lost and forced windows to blue screen death
68 | 1 | Windows | 2010-08-09 | 5 |  | Approved | Personalized items are lost and forced windows to blue screen death
68 | 1 | Windows | 2010-08-09 | 5 | Anjuli | Assigned | Personalized items are lost and forced windows to blue screen death
68 | 1 | Windows | 2010-08-11 | 5 |  | Resolved | Personalized items are lost and forced windows to blue screen death
68 | 1 | Windows | 2010-08-12 | 5 |  | Tested | Personalized items are lost and forced windows to blue screen death
68 | 1 | Windows | 2010-08-12 | 6 |  | Closed | Personalized items are lost and forced windows to blue screen death
68 | 1 | Windows | 2010-08-12 | 7 |  | Closed | Personalized items are lost and forced windows to blue screen death
69 | 1 | Windows | 2010-08-04 | 5 |  | Open | High CPU utilization when Viking is left idle
69 | 1 | Windows | 2010-08-09 | 5 |  | Approved | High CPU utilization when Viking is left idle
69 | 1 | Windows | 2010-08-09 | 5 | Bob | Assigned | High CPU utilization when Viking is left idle
69 | 1 | Windows | 2010-08-11 | 5 |  | Resolved | High CPU utilization when Viking is left idle
69 | 1 | Windows | 2010-08-12 | 5 |  | Tested | High CPU utilization when Viking is left idle
69 | 1 | Windows | 2010-08-12 | 6 |  | Closed | High CPU utilization when Viking is left idle
69 | 1 | Windows | 2010-08-12 | 7 |  | Closed | High CPU utilization when Viking is left idle
70 | 1 | Windows | 2010-08-05 | 5 |  | Open | Viking can't handle large files
70 | 1 | Windows | 2010-08-09 | 5 |  | Approved | Viking can't handle large files
70 | 1 | Windows | 2010-08-09 | 5 | Bob | Assigned | Viking can't handle large files
70 | 1 | Windows | 2010-08-11 | 5 |  | Resolved | Viking can't handle large files
70 | 1 | Windows | 2010-08-12 | 5 |  | Tested | Viking can't handle large files
70 | 1 | Windows | 2010-08-12 | 6 |  | Closed | Viking can't handle large files
70 | 1 | Windows | 2010-08-12 | 7 |  | Closed | Viking can't handle large files
75 | 1 | Windows | 2010-08-12 | 6 |  | Open | Malicious web site resizes Viking and calls alert(), making it seem as if Viking has crashed and offering a sketchy "solution"
75 | 1 | Windows | 2010-08-19 | 6 |  | Approved | Malicious web site resizes Viking and calls alert(), making it seem as if Viking has crashed and offering a sketchy "solution"
75 | 1 | Windows | 2010-08-19 | 7 | Bob | Assigned | Malicious web site resizes Viking and calls alert(), making it seem as if Viking has crashed and offering a sketchy "solution"
77 | 1 | Windows | 2010-08-12 | 6 |  | Open | If javascript enabled, then Viking frozen and some trojan starts running in Windows.
77 | 1 | Windows | 2010-08-19 | 6 |  | Approved | If javascript enabled, then Viking frozen and some trojan starts running in Windows.
77 | 1 | Windows | 2010-08-19 | 7 | Bob | Assigned | If javascript enabled, then Viking frozen and some trojan starts running in Windows.
80 | 1 | Windows | 2010-08-16 | 7 |  | Open | Viking 99% CPU usage
80 | 1 | Windows | 2010-08-19 | 7 |  | Approved | Viking 99% CPU usage
80 | 1 | Windows | 2010-08-19 | 7 | Bob | Assigned | Viking 99% CPU usage
84 | 1 | Windows | 2010-08-16 | 7 |  | Open | Nightly updates clobber default settings for all administrator users
84 | 1 | Windows | 2010-08-19 | 7 |  | Approved | Nightly updates clobber default settings for all administrator users
86 | 1 | Windows | 2010-08-17 | 7 |  | Open | Viking caused an invalid page fault in module XPCOM_CORE.DLL at 0187:6036179e
86 | 1 | Windows | 2010-08-19 | 7 |  | Approved | Viking caused an invalid page fault in module XPCOM_CORE.DLL at 0187:6036179e
87 | 1 | Windows | 2010-08-17 | 7 |  | Open | Viking produces a dialogue box which says Viking must close and then shuts down
87 | 1 | Windows | 2010-08-19 | 7 |  | Approved | Viking produces a dialogue box which says Viking must close and then shuts down
88 | 1 | Windows | 2010-08-17 | 7 |  | Open | Browser closes without warning
88 | 1 | Windows | 2010-08-19 | 7 |  | Approved | Browser closes without warning
89 | 1 | Windows | 2010-08-18 | 7 |  | Open | Viking shuts down for no apparent reason, after working for a while or even after I have just started Viking
89 | 1 | Windows | 2010-08-19 | 7 |  | Approved | Viking shuts down for no apparent reason, after working for a while or even after I have just started Viking
90 | 1 | Windows | 2010-08-18 | 7 |  | Open | Viking does not work properly with Java Applets
91 | 1 | Windows | 2010-08-18 | 7 |  | Open | Viking Hang with latest JRE
92 | 1 | Windows | 2010-08-18 | 7 |  | Open | Huge Viking Memory Leak Overnight…
93 | 1 | Windows | 2010-08-19 | 7 |  | Open | Print preview does not work
96 | 1 | Windows | 2010-08-19 | 7 |  | Open | Complete freeze up. Never had this happen before
97 | 1 | Windows | 2010-08-19 | 7 |  | Open | Windows update and windows live messenger are not working
99 | 1 | Windows | 2010-08-19 | 7 |  | Open | web based time sheet will not save data that has been entered
1 | 2 | Windows | 2010-07-05 | 1 |  | Open | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-12 | 1 |  | Approved | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-13 | 1 | Bob | Assigned | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-16 | 2 |  | Closed | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-19 | 2 |  | Not Resolved | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-20 | 2 | Bob | Assigned | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-23 | 2 |  | Resolved | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-23 | 3 |  | Tested | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-26 | 4 |  | Closed | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-26 | 5 |  | Closed | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-26 | 6 |  | Closed | DHTML added fields associated with incorrect form when multiple forms exist
1 | 2 | Windows | 2010-07-26 | 7 |  | Closed | DHTML added fields associated with incorrect form when multiple forms exist
2 | 2 | Windows | 2010-07-05 | 1 |  | Open | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-12 | 1 |  | Approved | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-13 | 1 | Anjuli | Assigned | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-14 | 2 |  | Resolved | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-17 | 2 |  | Tested | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-17 | 3 |  | Closed | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-17 | 4 |  | Closed | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-17 | 5 |  | Closed | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-17 | 6 |  | Closed | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
2 | 2 | Windows | 2010-07-17 | 7 |  | Closed | [Meta] Viking doesn't always exit after closing all windows; session-specific data retained
5 | 2 | Windows | 2010-07-06 | 1 |  | Open | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-07-12 | 1 |  | Approved | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-07-13 | 2 | Anjuli | Assigned | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-08-02 | 2 |  | Resolved | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-08-03 | 2 |  | Tested | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-08-04 | 3 |  | Closed | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-08-04 | 4 |  | Closed | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Viking shuts down completely when you link out
5 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Viking shuts down completely when you link out
7 | 2 | Windows | 2010-07-07 | 1 |  | Open | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-12 | 1 |  | Approved | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-13 | 1 | Bob | Assigned | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-14 | 2 |  | Resolved | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-17 | 2 |  | Tested | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-17 | 3 |  | Closed | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-17 | 4 |  | Closed | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-17 | 5 |  | Closed | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-17 | 6 |  | Closed | Viking times out, doesn't recover properly, after network error
7 | 2 | Windows | 2010-07-17 | 7 |  | Closed | Viking times out, doesn't recover properly, after network error
9 | 2 | Windows | 2010-07-07 | 1 |  | Open | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-12 | 1 |  | Approved | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-13 | 1 | Anjuli | Assigned | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-14 | 2 |  | Resolved | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-17 | 2 |  | Tested | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-17 | 3 |  | Closed | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-17 | 4 |  | Closed | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-17 | 5 |  | Closed | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-17 | 6 |  | Closed | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
9 | 2 | Windows | 2010-07-17 | 7 |  | Closed | Viking shows high CPU & mem usage for a page with 1000 dropdown-boxes each with 25 items
13 | 2 | Windows | 2010-07-08 | 1 |  | Open | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-12 | 1 |  | Approved | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-13 | 2 | Bob | Assigned | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-19 | 2 |  | Resolved | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-19 | 2 |  | Tested | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-19 | 3 |  | Closed | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-19 | 4 |  | Closed | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-19 | 5 |  | Closed | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-19 | 6 |  | Closed | Overlaying the content pane in the new preferences dialog makes the pane unusable
13 | 2 | Windows | 2010-07-19 | 7 |  | Closed | Overlaying the content pane in the new preferences dialog makes the pane unusable
14 | 2 | Windows | 2010-07-08 | 1 |  | Open | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-12 | 1 |  | Approved | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-13 | 2 | Anjuli | Assigned | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-19 | 2 |  | Resolved | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-19 | 2 |  | Tested | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-19 | 3 |  | Closed | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-19 | 4 |  | Closed | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-19 | 5 |  | Closed | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-19 | 6 |  | Closed | Dialogs cannot be dismissed when this flash has wmode="transparent"
14 | 2 | Windows | 2010-07-19 | 7 |  | Closed | Dialogs cannot be dismissed when this flash has wmode="transparent"
15 | 2 | Windows | 2010-07-12 | 7 |  | Open | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-12 | 7 |  | Approved | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-13 | 7 | Bob | Assigned | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-14 | 2 |  | Resolved | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-17 | 2 |  | Tested | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-17 | 3 |  | Closed | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-17 | 4 |  | Closed | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-17 | 5 |  | Closed | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-17 | 6 |  | Closed | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
15 | 2 | Windows | 2010-07-17 | 7 |  | Closed | The file Viking.exe is no longer a "Win32 application," ie. Viking will not open despite being fully installed.
18 | 2 | Windows | 2010-07-13 | 2 |  | Open | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-19 | 2 |  | Approved | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-21 | 3 |  | Resolved | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-24 | 3 |  | Tested | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-24 | 4 |  | Closed | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-24 | 5 |  | Closed | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-24 | 6 |  | Closed | Viking forgets all history info when i close it
18 | 2 | Windows | 2010-07-24 | 7 |  | Closed | Viking forgets all history info when i close it
19 | 2 | Windows | 2010-07-13 | 2 |  | Open | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-19 | 2 |  | Approved | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-19 | 2 | Bob | Assigned | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-21 | 3 |  | Resolved | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-24 | 3 |  | Tested | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-24 | 4 |  | Closed | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-24 | 5 |  | Closed | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-24 | 6 |  | Closed | Using with JRE Viking always hangs when it links to java verification page.
19 | 2 | Windows | 2010-07-24 | 7 |  | Closed | Using with JRE Viking always hangs when it links to java verification page.
20 | 2 | Windows | 2010-07-13 | 2 |  | Open | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-19 | 2 |  | Approved | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-19 | 2 | Bob | Assigned | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-21 | 3 |  | Resolved | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-24 | 3 |  | Tested | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-24 | 4 |  | Closed | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-24 | 5 |  | Closed | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-24 | 6 |  | Closed | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
20 | 2 | Windows | 2010-07-24 | 7 |  | Closed | Erratic keyboard behavior in form text entry box. Loss of focus in field, strange text selection behavior, can't copy or paste in text field
24 | 2 | Windows | 2010-07-14 | 2 |  | Open | Embed autosize param not working
24 | 2 | Windows | 2010-07-19 | 2 |  | Approved | Embed autosize param not working
24 | 2 | Windows | 2010-07-19 | 2 | Bob | Assigned | Embed autosize param not working
24 | 2 | Windows | 2010-07-21 | 3 |  | Resolved | Embed autosize param not working
24 | 2 | Windows | 2010-07-24 | 3 |  | Tested | Embed autosize param not working
24 | 2 | Windows | 2010-07-24 | 4 |  | Closed | Embed autosize param not working
24 | 2 | Windows | 2010-07-24 | 5 |  | Closed | Embed autosize param not working
24 | 2 | Windows | 2010-07-24 | 6 |  | Closed | Embed autosize param not working
24 | 2 | Windows | 2010-07-24 | 7 |  | Closed | Embed autosize param not working
32 | 2 | Windows | 2010-07-15 | 2 |  | Open | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-19 | 2 |  | Approved | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-19 | 2 | Bob | Assigned | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-21 | 3 |  | Resolved | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-24 | 3 |  | Tested | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-24 | 4 |  | Closed | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-24 | 5 |  | Closed | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-24 | 6 |  | Closed | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
32 | 2 | Windows | 2010-07-24 | 7 |  | Closed | java script chat, 100 % CPU usage, Viking.exe!jpeg_ifast+0*5595, process explorer 9.25
33 | 2 | Windows | 2010-07-15 | 2 |  | Open | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-19 | 2 |  | Approved | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-19 | 2 | Bob | Assigned | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-21 | 3 |  | Resolved | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-24 | 3 |  | Tested | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-24 | 4 |  | Closed | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-24 | 5 |  | Closed | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-24 | 6 |  | Closed | Viking Plug-In Dynamic Link Library performed an illegal operation
33 | 2 | Windows | 2010-07-24 | 7 |  | Closed | Viking Plug-In Dynamic Link Library performed an illegal operation
39 | 2 | Windows | 2010-07-20 | 3 |  | Open | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-26 | 3 |  | Approved | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-26 | 3 | Bob | Assigned | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-27 | 3 |  | Resolved | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-29 | 3 |  | Tested | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-30 | 4 |  | Closed | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-30 | 5 |  | Closed | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-30 | 6 |  | Closed | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
39 | 2 | Windows | 2010-07-30 | 7 |  | Closed | crash performing leaktest [@ nsContentUtils::GetDocShellFromCaller]
40 | 2 | Windows | 2010-07-20 | 3 |  | Open | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-26 | 3 |  | Approved | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-26 | 3 | Bob | Assigned | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-27 | 3 |  | Resolved | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-29 | 3 |  | Tested | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-30 | 4 |  | Closed | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-30 | 5 |  | Closed | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-30 | 6 |  | Closed | Hangs for about ~30 seconds when submitting FORM/INPUT information
40 | 2 | Windows | 2010-07-30 | 7 |  | Closed | Hangs for about ~30 seconds when submitting FORM/INPUT information
41 | 2 | Windows | 2010-07-20 | 3 |  | Open | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-26 | 3 |  | Approved | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-26 | 3 | Anjuli | Assigned | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-27 | 3 |  | Resolved | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-29 | 3 |  | Tested | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-30 | 4 |  | Closed | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-30 | 5 |  | Closed | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-30 | 6 |  | Closed | Scrolling is often/usually frozen when another Viking window is open.
41 | 2 | Windows | 2010-07-30 | 7 |  | Closed | Scrolling is often/usually frozen when another Viking window is open.
42 | 2 | Windows | 2010-07-20 | 3 |  | Open | LastMeasure not updated
42 | 2 | Windows | 2010-07-26 | 3 |  | Approved | LastMeasure not updated
42 | 2 | Windows | 2010-07-26 | 3 | Anjuli | Assigned | LastMeasure not updated
42 | 2 | Windows | 2010-07-27 | 3 |  | Resolved | LastMeasure not updated
42 | 2 | Windows | 2010-07-29 | 3 |  | Tested | LastMeasure not updated
42 | 2 | Windows | 2010-07-30 | 4 |  | Closed | LastMeasure not updated
42 | 2 | Windows | 2010-07-30 | 5 |  | Closed | LastMeasure not updated
42 | 2 | Windows | 2010-07-30 | 6 |  | Closed | LastMeasure not updated
42 | 2 | Windows | 2010-07-30 | 7 |  | Closed | LastMeasure not updated
46 | 2 | Windows | 2010-07-26 | 4 |  | Open | This URL makes Viking hang - reason unknown yet
46 | 2 | Windows | 2010-08-02 | 4 |  | Approved | This URL makes Viking hang - reason unknown yet
46 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | This URL makes Viking hang - reason unknown yet
46 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | This URL makes Viking hang - reason unknown yet
46 | 2 | Windows | 2010-08-04 | 4 |  | Tested | This URL makes Viking hang - reason unknown yet
46 | 2 | Windows | 2010-08-04 | 5 |  | Closed | This URL makes Viking hang - reason unknown yet
46 | 2 | Windows | 2010-08-04 | 6 |  | Closed | This URL makes Viking hang - reason unknown yet
46 | 2 | Windows | 2010-08-04 | 7 |  | Closed | This URL makes Viking hang - reason unknown yet
47 | 2 | Windows | 2010-07-26 | 4 |  | Open | Viking will not display results but is still running
47 | 2 | Windows | 2010-08-02 | 4 |  | Approved | Viking will not display results but is still running
47 | 2 | Windows | 2010-08-02 | 4 | Anjuli | Assigned | Viking will not display results but is still running
47 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | Viking will not display results but is still running
47 | 2 | Windows | 2010-08-04 | 4 |  | Tested | Viking will not display results but is still running
47 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Viking will not display results but is still running
47 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Viking will not display results but is still running
47 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Viking will not display results but is still running
49 | 2 | Windows | 2010-07-26 | 4 |  | Open | Viking hangs sometimes when Startup.Homepage uses document.write
49 | 2 | Windows | 2010-08-02 | 4 |  | Approved | Viking hangs sometimes when Startup.Homepage uses document.write
49 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | Viking hangs sometimes when Startup.Homepage uses document.write
49 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | Viking hangs sometimes when Startup.Homepage uses document.write
49 | 2 | Windows | 2010-08-04 | 4 |  | Tested | Viking hangs sometimes when Startup.Homepage uses document.write
49 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Viking hangs sometimes when Startup.Homepage uses document.write
49 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Viking hangs sometimes when Startup.Homepage uses document.write
49 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Viking hangs sometimes when Startup.Homepage uses document.write
51 | 2 | Windows | 2010-07-26 | 4 |  | Open | java applet locks up Viking after exit applet
51 | 2 | Windows | 2010-08-02 | 4 |  | Approved | java applet locks up Viking after exit applet
51 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | java applet locks up Viking after exit applet
51 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | java applet locks up Viking after exit applet
51 | 2 | Windows | 2010-08-04 | 4 |  | Tested | java applet locks up Viking after exit applet
51 | 2 | Windows | 2010-08-04 | 5 |  | Closed | java applet locks up Viking after exit applet
51 | 2 | Windows | 2010-08-04 | 6 |  | Closed | java applet locks up Viking after exit applet
51 | 2 | Windows | 2010-08-04 | 7 |  | Closed | java applet locks up Viking after exit applet
52 | 2 | Windows | 2010-07-26 | 4 |  | Open | Random access violations
52 | 2 | Windows | 2010-08-02 | 4 |  | Approved | Random access violations
52 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | Random access violations
52 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | Random access violations
52 | 2 | Windows | 2010-08-04 | 4 |  | Tested | Random access violations
52 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Random access violations
52 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Random access violations
52 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Random access violations
55 | 2 | Windows | 2010-07-27 | 4 |  | Open | Authentication Required' dialogue being application model produces a vector for attack
55 | 2 | Windows | 2010-08-02 | 4 |  | Approved | Authentication Required' dialogue being application model produces a vector for attack
55 | 2 | Windows | 2010-08-02 | 4 | Anjuli | Assigned | Authentication Required' dialogue being application model produces a vector for attack
55 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | Authentication Required' dialogue being application model produces a vector for attack
55 | 2 | Windows | 2010-08-04 | 4 |  | Tested | Authentication Required' dialogue being application model produces a vector for attack
55 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Authentication Required' dialogue being application model produces a vector for attack
55 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Authentication Required' dialogue being application model produces a vector for attack
55 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Authentication Required' dialogue being application model produces a vector for attack
56 | 2 | Windows | 2010-07-27 | 4 |  | Open | Launch Network File Generates Error That File Path is Invalid
56 | 2 | Windows | 2010-08-02 | 4 |  | Approved | Launch Network File Generates Error That File Path is Invalid
56 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | Launch Network File Generates Error That File Path is Invalid
56 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | Launch Network File Generates Error That File Path is Invalid
56 | 2 | Windows | 2010-08-04 | 4 |  | Tested | Launch Network File Generates Error That File Path is Invalid
56 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Launch Network File Generates Error That File Path is Invalid
56 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Launch Network File Generates Error That File Path is Invalid
56 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Launch Network File Generates Error That File Path is Invalid
57 | 2 | Windows | 2010-07-28 | 4 |  | Open | New Window Freezes ( may be a result of new window call from I-Frame then main window )
57 | 2 | Windows | 2010-08-02 | 4 |  | Approved | New Window Freezes ( may be a result of new window call from I-Frame then main window )
57 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | New Window Freezes ( may be a result of new window call from I-Frame then main window )
57 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | New Window Freezes ( may be a result of new window call from I-Frame then main window )
57 | 2 | Windows | 2010-08-04 | 4 |  | Tested | New Window Freezes ( may be a result of new window call from I-Frame then main window )
57 | 2 | Windows | 2010-08-04 | 5 |  | Closed | New Window Freezes ( may be a result of new window call from I-Frame then main window )
57 | 2 | Windows | 2010-08-04 | 6 |  | Closed | New Window Freezes ( may be a result of new window call from I-Frame then main window )
57 | 2 | Windows | 2010-08-04 | 7 |  | Closed | New Window Freezes ( may be a result of new window call from I-Frame then main window )
58 | 2 | Windows | 2010-07-28 | 4 |  | Open | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
58 | 2 | Windows | 2010-08-02 | 4 |  | Approved | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
58 | 2 | Windows | 2010-08-02 | 4 | Anjuli | Assigned | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
58 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
58 | 2 | Windows | 2010-08-04 | 4 |  | Tested | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
58 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
58 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
58 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Viking doesn't call applet init(), start(), stop(), destroy() at proper times.
59 | 2 | Windows | 2010-07-28 | 4 |  | Open | Viking fails to load more than a certain amount of images in one page
59 | 2 | Windows | 2010-08-02 | 4 |  | Approved | Viking fails to load more than a certain amount of images in one page
59 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | Viking fails to load more than a certain amount of images in one page
59 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | Viking fails to load more than a certain amount of images in one page
59 | 2 | Windows | 2010-08-04 | 4 |  | Tested | Viking fails to load more than a certain amount of images in one page
59 | 2 | Windows | 2010-08-04 | 5 |  | Closed | Viking fails to load more than a certain amount of images in one page
59 | 2 | Windows | 2010-08-04 | 6 |  | Closed | Viking fails to load more than a certain amount of images in one page
59 | 2 | Windows | 2010-08-04 | 7 |  | Closed | Viking fails to load more than a certain amount of images in one page
60 | 2 | Windows | 2010-07-29 | 4 |  | Open | java related Viking incompatibility which freezes tabs during forum use
60 | 2 | Windows | 2010-08-02 | 4 |  | Approved | java related Viking incompatibility which freezes tabs during forum use
60 | 2 | Windows | 2010-08-02 | 4 | Bob | Assigned | java related Viking incompatibility which freezes tabs during forum use
60 | 2 | Windows | 2010-08-04 | 4 |  | Resolved | java related Viking incompatibility which freezes tabs during forum use
60 | 2 | Windows | 2010-08-04 | 4 |  | Tested | java related Viking incompatibility which freezes tabs during forum use
60 | 2 | Windows | 2010-08-04 | 5 |  | Closed | java related Viking incompatibility which freezes tabs during forum use
60 | 2 | Windows | 2010-08-04 | 6 |  | Closed | java related Viking incompatibility which freezes tabs during forum use
60 | 2 | Windows | 2010-08-04 | 7 |  | Closed | java related Viking incompatibility which freezes tabs during forum use
65 | 2 | Windows | 2010-08-03 | 5 |  | Open | Viking locks up with file download
65 | 2 | Windows | 2010-08-09 | 5 |  | Approved | Viking locks up with file download
65 | 2 | Windows | 2010-08-09 | 5 | Bob | Assigned | Viking locks up with file download
65 | 2 | Windows | 2010-08-11 | 5 |  | Resolved | Viking locks up with file download
65 | 2 | Windows | 2010-08-12 | 5 |  | Tested | Viking locks up with file download
65 | 2 | Windows | 2010-08-12 | 6 |  | Closed | Viking locks up with file download
65 | 2 | Windows | 2010-08-12 | 7 |  | Closed | Viking locks up with file download
67 | 2 | Windows | 2010-08-03 | 5 |  | Open | Have had problems with Viking hanging with pdf files. On this page trying to print one or more pages caused bsod on two occasions today
67 | 2 | Windows | 2010-08-09 | 5 |  | Approved | Have had problems with Viking hanging with pdf files. On this page trying to print one or more pages caused bsod on two occasions today
67 | 2 | Windows | 2010-08-09 | 5 | Bob | Assigned | Have had problems with Viking hanging with pdf files. On this page trying to print one or more pages caused bsod on two occasions today
67 | 2 | Windows | 2010-08-11 | 5 |  | Resolved | Have had problems with Viking hanging with pdf files. On this page trying to print one or more pages caused bsod on two occasions today
67 | 2 | Windows | 2010-08-12 | 5 |  | Tested | Have had problems with Viking hanging with pdf files. On this page trying to print one or more pages caused bsod on two occasions today
67 | 2 | Windows | 2010-08-12 | 6 |  | Closed | Have had problems with Viking hanging with pdf files. On this page trying to print one or more pages caused bsod on two occasions today
67 | 2 | Windows | 2010-08-12 | 7 |  | Closed | Have had problems with Viking hanging with pdf files. On this page trying to print one or more pages caused bsod on two occasions today
71 | 2 | Windows | 2010-08-12 | 6 |  | Open | Viking process still around after all windows closed
71 | 2 | Windows | 2010-08-19 | 6 |  | Approved | Viking process still around after all windows closed
71 | 2 | Windows | 2010-08-19 | 7 | Bob | Assigned | Viking process still around after all windows closed
72 | 2 | Windows | 2010-08-12 | 6 |  | Open | with adobe flash set to window mode, keyboard functions are altered
72 | 2 | Windows | 2010-08-19 | 6 |  | Approved | with adobe flash set to window mode, keyboard functions are altered
72 | 2 | Windows | 2010-08-19 | 7 | Bob | Assigned | with adobe flash set to window mode, keyboard functions are altered
74 | 2 | Windows | 2010-08-12 | 6 |  | Open | After updating to this version both my computers have suffered system overload from Viking
74 | 2 | Windows | 2010-08-19 | 6 |  | Approved | After updating to this version both my computers have suffered system overload from Viking
74 | 2 | Windows | 2010-08-19 | 7 | Anjuli | Assigned | After updating to this version both my computers have suffered system overload from Viking
76 | 2 | Windows | 2010-08-12 | 6 |  | Open | Viking Not recognized Get ? also The Full Window icon when pressed makes browser 1" square
76 | 2 | Windows | 2010-08-19 | 6 |  | Approved | Viking Not recognized Get ? also The Full Window icon when pressed makes browser 1" square
76 | 2 | Windows | 2010-08-19 | 7 | Anjuli | Assigned | Viking Not recognized Get ? also The Full Window icon when pressed makes browser 1" square
79 | 2 | Windows | 2010-08-12 | 6 |  | Open | Had to manualy kill process after going from one SSL site to another without allowing page to render.
79 | 2 | Windows | 2010-08-19 | 6 |  | Approved | Had to manualy kill process after going from one SSL site to another without allowing page to render.
79 | 2 | Windows | 2010-08-19 | 7 | Anjuli | Assigned | Had to manualy kill process after going from one SSL site to another without allowing page to render.
81 | 2 | Windows | 2010-08-16 | 7 |  | Open | Running Viking while in Print Preview creates new tabs & can trigger crash
81 | 2 | Windows | 2010-08-19 | 7 |  | Approved | Running Viking while in Print Preview creates new tabs & can trigger crash
82 | 2 | Windows | 2010-08-16 | 7 |  | Open | Embedded videos won't play correctly
82 | 2 | Windows | 2010-08-19 | 7 |  | Approved | Embedded videos won't play correctly
85 | 2 | Windows | 2010-08-16 | 7 |  | Open | OnLoad/Onclick image load failure
85 | 2 | Windows | 2010-08-19 | 7 |  | Approved | OnLoad/Onclick image load failure
98 | 2 | Windows | 2010-08-19 | 7 |  | Open | Viking stalled when network connection suddenly lost
100 | 2 | Windows | 2010-08-19 | 7 |  | Open | form data not saved even after user confirmation, on moving to a different page in the web application
3 | 3 | Windows | 2010-07-05 | 1 |  | Open | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-12 | 1 |  | Approved | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-13 | 1 | Bob | Assigned | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-15 | 2 |  | Resolved | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-17 | 2 |  | Tested | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-17 | 3 |  | Closed | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-17 | 4 |  | Closed | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-17 | 5 |  | Closed | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-17 | 6 |  | Closed | Unexpected results after selecting cancel in migration screen
3 | 3 | Windows | 2010-07-17 | 7 |  | Closed | Unexpected results after selecting cancel in migration screen
8 | 3 | Windows | 2010-07-07 | 1 |  | Open | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-12 | 1 |  | Approved | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-13 | 1 | Bob | Assigned | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-14 | 2 |  | Resolved | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-17 | 2 |  | Tested | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-17 | 3 |  | Closed | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-17 | 4 |  | Closed | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-17 | 5 |  | Closed | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-17 | 6 |  | Closed | page locks up browser (cannot dismiss remember password dialog)
8 | 3 | Windows | 2010-07-17 | 7 |  | Closed | page locks up browser (cannot dismiss remember password dialog)
23 | 3 | Windows | 2010-07-14 | 2 |  | Open | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-19 | 2 |  | Approved | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-24 | 3 |  | Tested | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-24 | 4 |  | Closed | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-24 | 5 |  | Closed | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-24 | 6 |  | Closed | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
23 | 3 | Windows | 2010-07-24 | 7 |  | Closed | Viking does not recognise the 'Complete' state of the lingo cmd getStreamStatus(id)
25 | 3 | Windows | 2010-07-14 | 2 |  | Open | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-19 | 2 |  | Approved | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-19 | 2 | Bob | Assigned | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-24 | 3 |  | Tested | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-24 | 4 |  | Closed | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-24 | 5 |  | Closed | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-24 | 6 |  | Closed | All links open "Save As" dialog
25 | 3 | Windows | 2010-07-24 | 7 |  | Closed | All links open "Save As" dialog
28 | 3 | Windows | 2010-07-14 | 2 |  | Open | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-19 | 2 |  | Approved | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-19 | 2 | Bob | Assigned | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-24 | 3 |  | Tested | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-24 | 4 |  | Closed | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-24 | 5 |  | Closed | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-24 | 6 |  | Closed | Display window bounces once tabbed browsing is enabled.
28 | 3 | Windows | 2010-07-24 | 7 |  | Closed | Display window bounces once tabbed browsing is enabled.
29 | 3 | Windows | 2010-07-14 | 2 |  | Open | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-19 | 2 |  | Approved | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-24 | 3 |  | Tested | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-24 | 4 |  | Closed | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-24 | 5 |  | Closed | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-24 | 6 |  | Closed | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
29 | 3 | Windows | 2010-07-24 | 7 |  | Closed | Viking submits <select multiple="multiple"> as a single, non-array value and JavaScript behaves as if text input fields were filled in with values that were previously in them
30 | 3 | Windows | 2010-07-15 | 2 |  | Open | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-19 | 2 |  | Approved | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-19 | 2 | Bob | Assigned | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-24 | 3 |  | Tested | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-24 | 4 |  | Closed | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-24 | 5 |  | Closed | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-24 | 6 |  | Closed | User Authentication required again to download a file from FTP once the previous download is cancelled
30 | 3 | Windows | 2010-07-24 | 7 |  | Closed | User Authentication required again to download a file from FTP once the previous download is cancelled
31 | 3 | Windows | 2010-07-15 | 2 |  | Open | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-19 | 2 |  | Approved | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-24 | 3 |  | Tested | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-24 | 4 |  | Closed | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-24 | 5 |  | Closed | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-24 | 6 |  | Closed | At preview tables before printing which using css are cells on right end of page empty
31 | 3 | Windows | 2010-07-24 | 7 |  | Closed | At preview tables before printing which using css are cells on right end of page empty
34 | 3 | Windows | 2010-07-16 | 2 |  | Open | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-19 | 2 |  | Approved | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-19 | 2 | Bob | Assigned | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-24 | 3 |  | Tested | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-24 | 4 |  | Closed | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-24 | 5 |  | Closed | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-24 | 6 |  | Closed | Viking not giving up status as default browser : uninstall causes IE not to work
34 | 3 | Windows | 2010-07-24 | 7 |  | Closed | Viking not giving up status as default browser : uninstall causes IE not to work
35 | 3 | Windows | 2010-07-16 | 2 |  | Open | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-19 | 2 |  | Approved | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-21 | 3 |  | Resolved | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-24 | 3 |  | Tested | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-24 | 4 |  | Closed | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-24 | 5 |  | Closed | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-24 | 6 |  | Closed | Problem with printer-"friendly" web pages on Via website
35 | 3 | Windows | 2010-07-24 | 7 |  | Closed | Problem with printer-"friendly" web pages on Via website
43 | 3 | Windows | 2010-07-20 | 3 |  | Open | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-26 | 3 |  | Approved | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-26 | 3 | Anjuli | Assigned | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-27 | 3 |  | Resolved | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-29 | 3 |  | Tested | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-30 | 4 |  | Closed | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-30 | 5 |  | Closed | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-30 | 6 |  | Closed | Security problem - Dialer/Trojan successfully installed itself!
43 | 3 | Windows | 2010-07-30 | 7 |  | Closed | Security problem - Dialer/Trojan successfully installed itself!
45 | 3 | Windows | 2010-07-26 | 4 |  | Open | U+015E becomes U+00DE when part of URL
45 | 3 | Windows | 2010-08-02 | 4 |  | Approved | U+015E becomes U+00DE when part of URL
45 | 3 | Windows | 2010-08-02 | 4 | Bob | Assigned | U+015E becomes U+00DE when part of URL
45 | 3 | Windows | 2010-08-04 | 4 |  | Resolved | U+015E becomes U+00DE when part of URL
45 | 3 | Windows | 2010-08-04 | 4 |  | Tested | U+015E becomes U+00DE when part of URL
45 | 3 | Windows | 2010-08-04 | 5 |  | Closed | U+015E becomes U+00DE when part of URL
45 | 3 | Windows | 2010-08-04 | 6 |  | Closed | U+015E becomes U+00DE when part of URL
45 | 3 | Windows | 2010-08-04 | 7 |  | Closed | U+015E becomes U+00DE when part of URL
53 | 3 | Windows | 2010-07-26 | 4 |  | Open | Kernel panic consistent when printing particular page
53 | 3 | Windows | 2010-08-02 | 4 |  | Approved | Kernel panic consistent when printing particular page
53 | 3 | Windows | 2010-08-02 | 4 | Anjuli | Assigned | Kernel panic consistent when printing particular page
53 | 3 | Windows | 2010-08-04 | 4 |  | Resolved | Kernel panic consistent when printing particular page
53 | 3 | Windows | 2010-08-04 | 4 |  | Tested | Kernel panic consistent when printing particular page
53 | 3 | Windows | 2010-08-04 | 5 |  | Closed | Kernel panic consistent when printing particular page
53 | 3 | Windows | 2010-08-04 | 6 |  | Closed | Kernel panic consistent when printing particular page
53 | 3 | Windows | 2010-08-04 | 7 |  | Closed | Kernel panic consistent when printing particular page
54 | 3 | Windows | 2010-07-27 | 4 |  | Open | embed address bug load
54 | 3 | Windows | 2010-08-02 | 4 |  | Approved | embed address bug load
54 | 3 | Windows | 2010-08-02 | 4 | Bob | Assigned | embed address bug load
54 | 3 | Windows | 2010-08-04 | 4 |  | Resolved | embed address bug load
54 | 3 | Windows | 2010-08-04 | 4 |  | Tested | embed address bug load
54 | 3 | Windows | 2010-08-04 | 5 |  | Closed | embed address bug load
54 | 3 | Windows | 2010-08-04 | 6 |  | Closed | embed address bug load
54 | 3 | Windows | 2010-08-04 | 7 |  | Closed | embed address bug load
61 | 3 | Windows | 2010-07-29 | 4 |  | Open | The http request array is not receiving the data associated with files.
61 | 3 | Windows | 2010-08-02 | 4 |  | Approved | The http request array is not receiving the data associated with files.
61 | 3 | Windows | 2010-08-02 | 4 | Anjuli | Assigned | The http request array is not receiving the data associated with files.
61 | 3 | Windows | 2010-08-04 | 4 |  | Resolved | The http request array is not receiving the data associated with files.
61 | 3 | Windows | 2010-08-04 | 4 |  | Tested | The http request array is not receiving the data associated with files.
61 | 3 | Windows | 2010-08-04 | 5 |  | Closed | The http request array is not receiving the data associated with files.
61 | 3 | Windows | 2010-08-04 | 6 |  | Closed | The http request array is not receiving the data associated with files.
61 | 3 | Windows | 2010-08-04 | 7 |  | Closed | The http request array is not receiving the data associated with files.
62 | 3 | Windows | 2010-07-29 | 4 |  | Open | invalid character display
62 | 3 | Windows | 2010-08-02 | 4 |  | Approved | invalid character display
62 | 3 | Windows | 2010-08-02 | 4 | Bob | Assigned | invalid character display
62 | 3 | Windows | 2010-08-04 | 4 |  | Resolved | invalid character display
62 | 3 | Windows | 2010-08-04 | 4 |  | Tested | invalid character display
62 | 3 | Windows | 2010-08-04 | 5 |  | Closed | invalid character display
62 | 3 | Windows | 2010-08-04 | 6 |  | Closed | invalid character display
62 | 3 | Windows | 2010-08-04 | 7 |  | Closed | invalid character display
66 | 3 | Windows | 2010-08-03 | 5 |  | Open | cached images are not checked for reload when setting Document.location.href
66 | 3 | Windows | 2010-08-09 | 5 |  | Approved | cached images are not checked for reload when setting Document.location.href
66 | 3 | Windows | 2010-08-09 | 5 | Bob | Assigned | cached images are not checked for reload when setting Document.location.href
66 | 3 | Windows | 2010-08-11 | 5 |  | Resolved | cached images are not checked for reload when setting Document.location.href
66 | 3 | Windows | 2010-08-12 | 5 |  | Tested | cached images are not checked for reload when setting Document.location.href
66 | 3 | Windows | 2010-08-12 | 6 |  | Closed | cached images are not checked for reload when setting Document.location.href
66 | 3 | Windows | 2010-08-12 | 7 |  | Closed | cached images are not checked for reload when setting Document.location.href
73 | 3 | Windows | 2010-08-12 | 6 |  | Open | Does not respond in (New) Mail sometimes
73 | 3 | Windows | 2010-08-19 | 6 |  | Approved | Does not respond in (New) Mail sometimes
73 | 3 | Windows | 2010-08-19 | 7 | Anjuli | Assigned | Does not respond in (New) Mail sometimes
78 | 3 | Windows | 2010-08-12 | 6 |  | Open | entering a "paste" causes bookmark bar links to pop open
78 | 3 | Windows | 2010-08-19 | 6 |  | Approved | entering a "paste" causes bookmark bar links to pop open
78 | 3 | Windows | 2010-08-19 | 7 | Bob | Assigned | entering a "paste" causes bookmark bar links to pop open
83 | 3 | Windows | 2010-08-16 | 7 |  | Open | Memory leak after opening ajax-connection with a page on localhost with a bug that makes apache crash.
83 | 3 | Windows | 2010-08-19 | 7 |  | Approved | Memory leak after opening ajax-connection with a page on localhost with a bug that makes apache crash.
94 | 3 | Windows | 2010-08-19 | 7 |  | Open | SAP Internet Transaction Server page display different Theme in Viking
95 | 3 | Windows | 2010-08-19 | 7 |  | Open | A pop up window with your logo says I have spy ware
26 | 4 | Windows | 2010-07-14 | 2 |  | Open | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-19 | 2 |  | Approved | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-19 | 2 | Anjuli | Assigned | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-21 | 3 |  | Resolved | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-24 | 3 |  | Tested | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-24 | 4 |  | Closed | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-24 | 5 |  | Closed | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-24 | 6 |  | Closed | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
26 | 4 | Windows | 2010-07-24 | 7 |  | Closed | randomly (it seems) Viking just stalls for a while. No known reason for it yet determined
27 | 4 | Windows | 2010-07-14 | 2 |  | Open | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-19 | 2 |  | Approved | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-19 | 2 | Bob | Assigned | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-21 | 3 |  | Resolved | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-24 | 3 |  | Tested | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-24 | 4 |  | Closed | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-24 | 5 |  | Closed | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-24 | 6 |  | Closed | Viking works fine but slows page rendering
27 | 4 | Windows | 2010-07-24 | 7 |  | Closed | Viking works fine but slows page rendering

## Motivation
2009 | [6 empty] | 2010
# | Motivation | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Motivation | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
3 | I am provided with opportunities to broaden my skills and knowledge | 22 | 20 | 32 | 12 | 14 | 3 | I am provided with opportunities to broaden my skills and knowledge | 28 | 34 | 42 | 24 | 22
8 | I am empowered to make decisions | 18 | 21 | 19 | 18 | 24 | 8 | I am empowered to make decisions | 28 | 30 | 30 | 32 | 30
14 | My opinions are valued by my project team | 6 | 7 | 40 | 24 | 23 | 14 | My opinions are valued by my project team | 14 | 15 | 55 | 34 | 32
15 | I know how my work contributes to the success of ABC Systems | 8 | 13 | 17 | 36 | 26 | 15 | I know how my work contributes to the success of ABC Systems | 13 | 28 | 33 | 44 | 32
| TOTAL | 54 | 61 | 108 | 90 | 87 |  | TOTAL | 83 | 107 | 160 | 134 | 116
| RATE (%) | 13.5 | 15.25 | 27 | 22.5 | 21.75 |  | RATE (%) | 13.8333 | 17.8333 | 26.6667 | 22.3333 | 19.3333
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 13.5 | 15.25 | 27 | 22.5 | 21.75 | 4.75
2010 | 13.8333 | 17.8333 | 26.6667 | 22.3333 | 19.3333 | 3.1
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## 2009 Survey Results
Software Engineering Department Employee Satisfaction Survey - November, 2009 (Percents %)
Below are the results of the ABC Systems employee satisfaction survey given to employees of the Software Engineering Division from November, 2009.
At that time ABC Systems had ~100 technical employees (software developers, testers, technical support, etc.).
The numbers underneath each category represent the number of employees who provided that response to the question. For example, 18 employees Strongly Disagreed with the first survey question.
# | Survey Question | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
1 | I see career growth and advancement opportunities for myself at ABC Systems | 12 | 25 | 20 | 26 | 17
2 | I feel informed about changes that affect me | 14 | 18 | 28 | 24 | 16
3 | I am provided with opportunities to broaden my skills and knowledge | 22 | 20 | 32 | 12 | 14
4 | My department is a great place to work | 11 | 17 | 14 | 36 | 22
5 | ABC Systems is a great place to work | 12 | 18 | 17 | 31 | 22
6 | My project is a great place to work | 8 | 13 | 28 | 25 | 26
7 | I am currently looking for another job outside of ABC Systems | 20 | 25 | 7 | 33 | 15
8 | I am empowered to make decisions | 18 | 21 | 19 | 18 | 24
9 | There is cooperation between the departments in the company | 26 | 22 | 18 | 19 | 15
10 | I have the tools and resources that I need to get my job done | 7 | 12 | 21 | 32 | 28
11 | I have had the training I need to get the job done | 12 | 16 | 14 | 33 | 25
12 | I would recommend ABC Systems to friends as a great place to work | 10 | 23 | 21 | 28 | 18
13 | I have access to the information that I need to do my job well | 12 | 15 | 28 | 23 | 22
14 | My opinions are valued by my project team | 6 | 7 | 40 | 24 | 23
15 | I know how my work contributes to the success of ABC Systems | 8 | 13 | 17 | 36 | 26
16 | I take pride in my work | 0 | 5 | 15 | 15 | 65

## 2010 Survey Results
Software Engineering Department Employee Satisfaction Survey - November, 2010 (Percent %)
Below are the results of the ABC Systems employee satisfaction survey given to employees of the Software Engineering Division from November, 2010
At that time ABC Systems had ~150 technical employees (software developers, testers, technical support, etc.).
The numbers underneath each category represent the number of employees who provided that response to the question. For example, 18 employees Strongly Disagreed with the first survey question.
# | Survey Question | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
1 | I see career growth and advancement opportunities for myself at ABC Systems | 18 | 35 | 28 | 38 | 31
2 | I feel informed about changes that affect me | 26 | 28 | 40 | 36 | 20
3 | I am provided with opportunities to broaden my skills and knowledge | 28 | 34 | 42 | 24 | 22
4 | My department is a great place to work | 20 | 26 | 26 | 47 | 31
5 | ABC Systems is a great place to work | 19 | 27 | 34 | 40 | 30
6 | My project is a great place to work | 16 | 24 | 40 | 36 | 34
7 | I am currently looking for another job outside of ABC Systems | 31 | 34 | 15 | 46 | 24
8 | I am empowered to make decisions | 28 | 30 | 30 | 32 | 30
9 | There is cooperation between the departments in the company | 40 | 34 | 24 | 27 | 25
10 | I have the tools and resources that I need to get my job done | 15 | 25 | 32 | 42 | 36
11 | I have had the training I need to get the job done | 22 | 30 | 25 | 43 | 30
12 | I would recommend ABC Systems to friends as a great place to work | 18 | 35 | 34 | 40 | 23
13 | I have access to the information that I need to do my job well | 22 | 27 | 40 | 33 | 28
14 | My opinions are valued by my project team | 14 | 15 | 55 | 34 | 32
15 | I know how my work contributes to the success of ABC Systems | 13 | 28 | 33 | 44 | 32
16 | I take pride in my work | 0 | 12 | 30 | 35 | 73

## Physical Environment
2009 | [6 empty] | 2010
# | Physical Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Physical Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
4 | My department is a great place to work | 11 | 17 | 14 | 36 | 22 | 4 | My department is a great place to work | 20 | 26 | 26 | 47 | 31
5 | ABC Systems is a great place to work | 12 | 18 | 17 | 31 | 22 | 5 | ABC Systems is a great place to work | 19 | 27 | 34 | 40 | 30
| TOTAL | 23 | 35 | 31 | 67 | 44 |  | TOTAL | 39 | 53 | 60 | 87 | 61
| Rate (%) | 11.5 | 17.5 | 15.5 | 33.5 | 22 |  | Rate (%) | 13 | 17.6667 | 20 | 29 | 20.3333
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 11.5 | 17.5 | 15.5 | 33.5 | 22 | 7.4
2010 | 13 | 17.6667 | 20 | 29 | 20.3333 | 5.2
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Systems, Tools and Processes
2009 | [6 empty] | 2010
# | Systems, Tools and Processes | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Systems, Tools and Processes | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
6 | My project is a great place to work | 8 | 13 | 28 | 25 | 26 | 6 | My project is a great place to work | 16 | 24 | 40 | 36 | 34
9 | There is cooperation between the departments in the company | 26 | 22 | 18 | 19 | 15 | 9 | There is cooperation between the departments in the company | 40 | 34 | 24 | 27 | 25
10 | I have the tools and resources that I need to get my job done | 7 | 12 | 21 | 32 | 28 | 10 | I have the tools and resources that I need to get my job done | 15 | 25 | 32 | 42 | 36
13 | I have access to the information that I need to do my job well | 12 | 15 | 28 | 23 | 22 | 13 | I have access to the information that I need to do my job well | 22 | 27 | 40 | 33 | 28
| TOTAL | 53 | 62 | 95 | 99 | 91 |  | TOTAL | 93 | 110 | 136 | 138 | 123
| RATE (%) | 13.25 | 15.5 | 23.75 | 24.75 | 22.75 |  | RATE (%) | 15.5 | 18.3333 | 22.6667 | 23 | 20.5
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 13.25 | 15.5 | 23.75 | 24.75 | 22.75 | 5.65
2010 | 15.5 | 18.3333 | 22.6667 | 23 | 20.5 | 2.9333
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Emotional Environment
2009 | [6 empty] | 2010
# | Emotional Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Emotional Environment | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
12 | I would recommend ABC Systems to friends as a great place to work | 10 | 23 | 21 | 28 | 18 | 12 | I would recommend ABC Systems to friends as a great place to work | 18 | 35 | 34 | 40 | 23
16 | I take pride in my work | 0 | 5 | 15 | 15 | 65 | 16 | I take pride in my work | 0 | 12 | 30 | 35 | 73
| TOTAL | 10 | 28 | 36 | 43 | 83 |  | TOTAL | 18 | 47 | 64 | 75 | 96
| RATE (%) | 5 | 14 | 18 | 21.5 | 41.5 |  | RATE (%) | 6 | 15.6667 | 21.3333 | 25 | 32
| Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | Point
2009 | 5 | 14 | 18 | 21.5 | 41.5 | 16.1
2010 | 6 | 15.6667 | 21.3333 | 25 | 32 | 12.2667
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Management
2009 | [6 empty] | 2010
# | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
1 | I see career growth and advancement opportunities for myself at ABC Systems | 12 | 25 | 20 | 26 | 17 | 1 | I see career growth and advancement opportunities for myself at ABC Systems | 18 | 35 | 28 | 38 | 31
2 | I feel informed about changes that affect me | 14 | 18 | 28 | 24 | 16 | 2 | I feel informed about changes that affect me | 26 | 28 | 40 | 36 | 20
11 | I have had the training I need to get the job done | 12 | 16 | 14 | 33 | 25 | 11 | I have had the training I need to get the job done | 22 | 30 | 25 | 43 | 30
| TOTAL | 38 | 59 | 62 | 83 | 58 |  | TOTAL | 66 | 93 | 93 | 117 | 81
| RATE (%) | 12.6667 | 19.6667 | 20.6667 | 27.6667 | 19.3333 |  | RATE (%) | 14.6667 | 20.6667 | 20.6667 | 26 | 18
| Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | Point
2009 | 12.6667 | 19.6667 | 20.6667 | 27.6667 | 19.3333 | 4.2667
2010 | 14.6667 | 20.6667 | 20.6667 | 26 | 18 | 2.4
Strongly Disagree | -2
Disagree | -1
Neutral | 0
Agree | 1
Strongly Agree | 2

## Looking for another job
2009 | [6 empty] | 2010
# | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree | # | Management | Strongly Disagree | Disagree | Neutral | Agree | Strongly Agree
7 | I am currently looking for another job outside of ABC Systems | 20 | 25 | 7 | 33 | 15 | 7 | I am currently looking for another job outside of ABC Systems | 31 | 34 | 15 | 46 | 24
| TOTAL | 20 | 25 | 7 | 33 | 15 |  | TOTAL | 31 | 34 | 15 | 46 | 24
| RATE (%) | 20 | 25 | 7 | 33 | 15 |  | RATE (%) | 20.6667 | 22.6667 | 10 | 30.6667 | 16
| Strongly Disagree (%) | Disagree (%) | Neutral (%) | Agree (%) | Strongly Agree (%) | Point
2009 | 20 | 25 | 7 | 33 | 15 | 0.4
2010 | 20.6667 | 22.6667 | 10 | 30.6667 | 16 | 0.26667
Strongly Disagree | 2
Disagree | 1
Neutral | 0
Agree | -1
Strongly Agree | -2

## Project Schedule
Project Schedule
Update 30/3/2012
Year | Task Name | Work | Duration | Start | Finish | Resource Names
1 | Planning | 54 hrs | 21 days | Mon 4/2/07 | Sun 4/29/07
| Train Team | 40 hrs | 14 days | Mon 4/2/07 | Thu 4/19/07
| Produce basic schedule | 10 hrs | 5 days | Fri 4/20/07 | Thu 4/26/07 | Project Management Team
| Project Management Team | 10 hrs |  | Fri 4/20/07 | Thu 4/26/07
| Conduct Team Meeting | 4 hrs | 2 days | Fri 4/20/07 | Mon 4/23/07
| Kick - Off | 45 hrs | 9 days | Thu 4/26/07 | Tue 5/8/07 | Project Management Team
| Develop Strategy for Viking project | 36 hrs | 6 days | Fri 4/27/07 | Fri 5/4/07 | Project Management Team
| Project Management Team | 36 hrs |  | Fri 4/27/07 | Fri 5/4/07
| Review RE with customer | 9 hrs | 3 days | Fri 4/27/07 | Tue 5/1/07 | Project Management Team
| Project Management Team | 9 hrs |  | Fri 4/27/07 | Tue 5/1/07 | Viking Architecture Team
| Inception & Elaboration | 228 hrs | 15 days | Mon 5/7/07 | Fri 5/25/07 | Project Management Team
| Produce User Requirement | 36 hrs | 6 days | Mon 5/7/07 | Mon 5/14/07 | Project Management Team
| Project Management Team | 36 hrs |  | Mon 5/7/07 | Mon 5/14/07 | Viking Architecture Team
| Produce Viking Architecture Document | 30 hrs | 5 days | Tue 5/15/07 | Mon 5/21/07 | Viking Architecture Team
| Viking Architecture Team | 30 hrs |  | Tue 5/15/07 | Mon 5/21/07 | Viking Development Team and Testing Team
| Produce Project Charter | 24 hrs | 4 days | Mon 5/7/07 | Thu 5/10/07
| Project Management Team | 24 hrs |  | Mon 5/7/07 | Thu 5/10/07 | Viking Development Team[75%]
| Produce Project Plan | 60 hrs | 10 days | Mon 5/7/07 | Fri 5/18/07 | Viking Development Team
| Project Management Team | 60 hrs |  | Mon 5/7/07 | Fri 5/18/07 | Viking Development Team
| Develop High Level Design Document | 30 hrs | 5 days | Tue 5/15/07 | Mon 5/21/07 | Viking Development Team
| Viking Architecture Team | 30 hrs |  | Tue 5/15/07 | Mon 5/21/07 | Viking Development Team
| Develop Detailed Level Design Document | 24 hrs | 4 days | Tue 5/22/07 | Fri 5/25/07
| Viking Architecture Team | 24 hrs |  | Tue 5/22/07 | Fri 5/25/07
| Produce Test Plan (Unit Test and Integration Test) | 24 hrs | 4 days | Tue 5/22/07 | Fri 5/25/07 | ABC System testing team
| Viking Development Team and Testing Team | 24 hrs |  | Tue 5/22/07 | Fri 5/25/07 | Viking Development Team
| Construction | 1,008 hrs | 142 days | Mon 5/28/07 | Tue 12/11/07
| Produce Viking Module Construction | 720 hrs | 120 days | Mon 5/28/07 | Fri 11/9/07 | ABC System testing team
| Viking Development Team | 720 hrs |  | Mon 5/28/07 | Fri 11/9/07 | Project Management Team
| Adding functionality in each subsequent work package | 120 hrs | 20 days | Mon 5/28/07 | Fri 6/22/07 | Project Management Team
| Viking Development Team | 120 hrs |  | Mon 5/28/07 | Fri 6/22/07
| Address the work package | 36 hrs | 6 days | Mon 6/25/07 | Mon 7/2/07
| Viking Development Team | 36 hrs |  | Mon 6/25/07 | Mon 7/2/07
| Package the deliverables | 48 hrs | 8 days | Tue 7/3/07 | Thu 7/12/07
| Viking Development Team | 48 hrs |  | Tue 7/3/07 | Thu 7/12/07
| Test work package | 84 hrs | 14 days | Mon 11/12/07 | Thu 11/29/07
| Viking Development Team | 84 hrs |  | Mon 11/12/07 | Thu 11/29/07
| Transition | 102 hrs | 13 days | Fri 11/30/07 | Tue 12/18/07
| Produce Viking Material | 12 hrs | 2 days | Fri 11/30/07 | Mon 12/3/07
| Perform acceptance testing | 72 hrs | 12 days | Fri 11/30/07 | Mon 12/17/07
| ABC System testing team | 72 hrs |  | Fri 11/30/07 | Mon 12/17/07
| Produce Viking Product Document | 18 hrs | 3 days | Fri 11/30/07 | Tue 12/4/07
| Viking Development Team | 18 hrs |  | Fri 11/30/07 | Tue 12/4/07
| Close - Out | 72 hrs | 5 days | Tue 12/18/07 | Mon 12/24/07
| Final review | 30 hrs | 5 days | Tue 12/18/07 | Mon 12/24/07
| ABC System testing team | 30 hrs |  | Tue 12/18/07 | Mon 12/24/07
| Consume Lessons Learned | 30 hrs | 5 days | Tue 12/18/07 | Mon 12/24/07
| Project Management Team | 30 hrs |  | Tue 12/18/07 | Mon 12/24/07
| Produce Project Close out Document | 12 hrs | 2 days | Tue 12/18/07 | Wed 12/19/07
| Project Management Team | 12 hrs |  | Tue 12/18/07 | Wed 12/19/07
2 & 3 | Support and Train for Customer | 1,080 hrs | 522 days | Tue 1/1/13 | Wed 12/31/14
| Maitain the system | 2,700 hrs | 522 days | Tue 1/1/13 | Wed 12/31/14
| Testing and Maitain before develop | 0 hrs | 64 days | Thu 1/1/15 | Tue 3/31/15
4 | Requirement | 0 hrs | 65 days | Fri 1/1/16 | Thu 3/31/16
| Tìm hiểu nhu cầu thị trường | 0 hrs | 14 days | Fri 1/1/16 | Wed 1/20/16
| Lấy yêu cầu | 0 hrs | 51 days | Thu 1/21/16 | Thu 3/31/16
| Planning | 0 hrs | 37 days | Fri 4/1/16 | Sat 5/21/16
| Train Team | 0 hrs | 22 days | Fri 4/1/16 | Sat 4/30/16
| Produce basic schedule | 0 hrs | 10 days | Tue 5/1/12 | Mon 5/14/12
| Conduct Team Meeting | 0 hrs | 7 days | Sun 5/15/16 | Sat 5/21/16
| Kick - Off | 0 hrs | 23 days | Sun 5/22/16 | Tue 6/21/16
| Develop Strategy for Viking project | 0 hrs | 13 days | Sun 5/22/16 | Tue 6/7/16
| Review RE with customer | 0 hrs | 10 days | Wed 6/8/16 | Tue 6/21/16
| Design | 0 hrs | 42 days | Wed 6/22/16 | Thu 8/18/16
| Produce User Requirement | 0 hrs | 8 days | Wed 6/22/16 | Fri 7/1/16
| Produce Viking Architecture Document | 0 hrs | 7 days | Fri 7/1/16 | Sun 7/10/16
| Viking Architecture Team | 0 hrs | 7 days | Fri 7/1/16 | Sun 7/10/16
| Produce Project Charter | 0 hrs | 5 days | Mon 7/11/16 | Fri 7/15/16
| Produce Project Plan | 0 hrs | 5 days | Sat 7/16/16 | Thu 7/21/16
| Develop High Level Design Document | 0 hrs | 8 days | Fri 7/22/16 | Tue 8/2/16
| Viking Architecture Team | 0 hrs | 8 days | Fri 7/22/16 | Tue 8/2/16
| Develop Detailed Level Design Document | 0 hrs | 10 days | Mon 8/1/16 | Fri 8/12/16
| Viking Architecture Team | 0 hrs | 10 days | Mon 8/1/16 | Fri 8/12/16
| Produce Test Plan (Unit Test and Integration Test) | 0 hrs | 5 days | Fri 8/12/16 | Thu 8/18/16
| Viking Development Team and Testing Team | 0 hrs | 5 days | Fri 8/12/16 | Thu 8/18/16
| Code | 0 hrs | 52 days | Fri 8/19/16 | Sun 10/30/16
| Produce Viking Module Construction | 0 hrs | 27 days | Fri 8/19/16 | Sun 9/25/16
| Viking Development Team | 0 hrs | 27 days | Fri 8/19/16 | Sun 9/25/16
| Adding functionality in each subsequent work package | 0 hrs | 11 days | Mon 9/26/16 | Sat 10/8/16
| Viking Development Team | 0 hrs | 11 days | Mon 9/26/16 | Sat 10/8/16
| Address the work package | 0 hrs | 11 days | Sun 10/9/16 | Fri 10/21/16
| Viking Development Team | 0 hrs | 11 days | Sun 10/9/16 | Fri 10/21/16
| Package the deliverables | 0 hrs | 7 days | Sat 10/22/16 | Sun 10/30/16
| Viking Development Team | 0 hrs | 7 days | Sat 10/22/16 | Sun 10/30/16
| Test | 0 hrs | 15 days | Tue 11/1/16 | Mon 11/21/16
| Test work package | 0 hrs | 15 days | Tue 11/1/16 | Mon 11/21/16
| Viking Development Team | 0 hrs | 15 days | Tue 11/1/16 | Mon 11/21/16
| Close - Out | 0 hrs | 15 days | Tue 11/22/16 | Sat 12/10/16
| Final review | 0 hrs | 5 days | Tue 11/22/16 | Sun 11/27/16
| ABC System testing team | 0 hrs | 5 days | Tue 11/22/16 | Sun 11/27/16
| Consume Lessons Learned | 0 hrs | 6 days | Mon 11/28/16 | Mon 12/5/16
| Project Management Team | 0 hrs | 6 days | Mon 11/28/16 | Sun 12/4/16
| Produce Project Close out Document | 0 hrs | 6 days | Mon 12/5/16 | Sat 12/10/16
| Project Management Team | 0 hrs | 6 days | Mon 12/5/16 | Sat 12/10/16

## Resource Allocation
Viking Estimated Resource Allocation
No. | Role | Allocation
Year 01
1 | PM | 1
2 | Developer | 4
3 | Architect | 1
4 | Risk Manager | 1
5 | Change manager | 1
6 | Requirement Engineer | 2
7 | Tester | 2
8 | Quality Assurance Manager | 1
Year 2
1 | Mantaining Member | 3
2 | Training Member | 3
Year 03
1 | Mantaining Member | 1
2 | Training Member | 1
Year 04
1 | PM | 1
2 | Developer | 2
3 | Risk Manager | 1
4 | Change manager | 1
5 | Requirement Engineer | 1
6 | Tester | 2
7 | Designer | 1

## Project Budget Data Entry
Project Budget Data Entry
| Position | Work Hour | Hour Rate | Total Hour | Total Cost | From (month) | To (month)
Year 1 | PM | 2 | 100 | 396 | 39600 | 4 | 12
| Developer 1 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 2 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 3 | 4 | 60 | 528 | 31680 | 6 | 11
| Developer 4 | 4 | 60 | 528 | 31680 | 6 | 11
| Architect | 3 | 150 | 132 | 19800 | 2 | 3
| Risk Manager | 2 | 75 | 88 | 6600 | 5 | 6
| Change manager | 2 | 75 | 88 | 6600 | 5 | 6
| Requirement Engineer 1 | 6 | 75 | 264 | 19800 | 4 | 5
| Requirement Engineer 2 | 6 | 75 | 264 | 19800 | 4 | 5
| Tester 1 | 3 | 75 | 132 | 9900 | 11 | 12
| Tester 2 | 3 | 75 | 66 | 4950 | 12 | 12
| Quality Assurance Manager | 2 | 100 | 308 | 30800 | 4 | 10
Total |  |  |  |  | 284570
Year 2 | Mantaining Member 1 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 2 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 3 | 3 | 50 | 180 | 27000 | 1 | 12
| Training Member 1 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 2 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 3 | 3 | 50 | 450 | 22500 | 1 | 12
Total |  |  |  |  | 60750
Year 3 | Mantaining Member 1 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 2 | 3 | 50 | 180 | 27000 | 1 | 12
| Mantaining Member 3 | 3 | 50 | 180 | 27000 | 1 | 12
| Training Member 1 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 2 | 3 | 50 | 450 | 22500 | 1 | 12
| Training Member 3 | 3 | 50 | 450 | 22500 | 1 | 12
Total |  |  |  |  | 60750
Year 4 | PM | 2 | 100 | 132 | 13200 | 4 | 9
| Developer 1 | 4 | 60 | 352 | 21120 | 5 | 8
| Developer 2 | 4 | 75 | 352 | 26400 | 5 | 8
| Risk Manager | 2 | 75 | 44 | 3300 | 4 | 4
| Change manager | 2 | 75 | 44 | 3300 | 4 | 4
| Requirement Engineer | 6 | 75 | 66 | 4950 | 4 | 4
| Tester 1 | 3 | 75 | 132 | 9900 | 9 | 9
| Tester 2 | 3 | 75 | 132 | 9900 | 9 | 9
| Designer | 3 | 100 | 66 | 6600 | 4 | 4
Total |  |  |  |  | 98670