## Risk List
Risk List
Last updated: | 2010-07-01
By: | Quoc Nguyen, Project Manager
Risk Analysis
Risk ID | Risk Title | Risk Description | Identified Date | Earliest Impact Date | Latest Impact Date | Risk Category | Risk Source | Impact to |  |  |  | Probability | Level | Exposure | Priority | Status | Mitigation Plan | Contigency Plan | Owner | Relevant Stakeholders | Become Issue? | Date Occurred
[8 empty] | Scope | Budget | Schedule | Quality
R-001 | Risk of Customer participation in Acceptance Test | Customer representative may not be able to join in Acceptance Test that would deplay the product deployment schedule | 2010-07-01 |  |  | Customer risks | Integration & Test | None | Negligible | Significant | None | 30% | Medium | 0.9 |  | Control | Get customer's commitment participating in Acceptance Test as scheduled |  | Hieu To | Anthony Lattanzy (Customer) | No
R-002 | Risk of applying Java RMI | No experience in applying Java RMI to develop distributed system | 2010-07-01 |  |  | Technical risk | Code & Unit Test | None | Significant | Significant | Critical | 50% | Medium | 2 |  | Control | Develop prototype before July 6th 2010 |  | Huyen Pham | Air force 1 team | No
R-003 | Risk of applying Streaming technique | No experience in streaming technique | 2010-07-01 |  |  | Technical risk | Code & Unit Test | None | Significant | Significant | Critical | 50% | Medium | 2 |  | Control | Need to develop prototype by using RMI before July 6th 2010 |  | Huyen Pham | Air force 1 team | No
R-004 | Risk of applying AUP | No experience in AUP | 2010-07-01 |  |  | Process risks | Development Process | None | Significant | Significant | Significant | 70% | Medium | 2.1 |  | Control | Need to communicate frequently to mentor for suggestion |  | Quoc Nguyen | Air force 1 team | No
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
Note on A4: Hieu To: mmm dd, yy
Note on Q7: Hieu To: 1. Acceptance: Acknowledgment of risk but not taking any action 2. Monitor: Watching and periodically re-evaluating the risk 3. Control: Taking active action to mitigate risk 4. Transfer: Reallocating risk to other entity. Do not consider it any more 5. Avoid: Changing or lowering requirements while still meeting the user's needs 6. Retired: The time to impact is passed. Do not consider it any more 7. Occur: Risk occured

## Risk Glossary
Risk Taxonomy
| Risk Category | Risk Source
| Technical risk | Requirement
| Resource risks | Design
| Process risks | Code & Unit Test
| Business risks | Integration & Test
| Customer risks | Engineering Specialties
| Others | Development Process
Development System
Management Process
Management Methods
Work Environment
Resources
Contract
Program Interfaces
Status | Name | Description
A | Acknowledgment | Acknowledgment of risk but not taking any action
M | Monitor | Watching and periodically re-evaluating the risk
C | Control | Taking active action to mitigate risk
T | Transfer | Reallocating risk to other entity. Do not consider it any more
V | Avoid | Changing or lowering requirements while still meeting the user's needs
R | Retired | The time to impact is passed. Do not consider it any more
O | Occur | Risk occured
# | Probability | Meaning
1 | 10% | Remote
2 | 30% | Unlikely
3 | 50% | Likely
4 | 70% | High Likely
5 | 90% | Near certainty
| Consequence | Value
| None | 0
| Negligible | 1
| Marginal | 2
| Significant | 3
| Critical | 4
| Catastrophic | 5
| Probability | Consequence
|  | 1 | 2 | 3 | 4 | 5
| 10% | Low | Low | Low | Low | Low
| 30% | Low | Low | Medium | Medium | Medium
| 50% | Low | Medium | Medium | Medium | High
| 70% | Low | Medium | Medium | High | High
| 90% | Medium | Medium | High | High | High