## TimeLog
Time Recording Log For: POS Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Huy Huynh |  |  |  | Date: | 2012-05-14
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Inter. Time | Delta Time | Activity | Artifact | C | U | Plan and Schedule | #REF!
1 | 2012-05-18 | 22:30 | 12:00 | 0 | 1.5 | Kick off Project with Mentor |  |  |  | Architecture drivers | 12
[10 empty] | Architecture & Design | 73.5
[10 empty] | Class diagram and Database | 22
2 | 2012-05-21 | 21:00 | 23:00 | 0 | 2 | Team Meeting with Mentor |  |  |  | Coding | #REF!
| 2012-05-22 | 21:00 | 23:30 | 0 | 3.5 | Xem lai bản SRS của dự án trước
| 2012-05-23 | 21:00 | 22:30 | 0 | 1.5 | Làm bản SRS ver 1. |  |  |  | TOTAL | #REF!
[10 empty] | ON AVERAGE (hours/week) | #REF!
3 | 2012-05-28 | 9:00 | 11:00 | 0 | 2 | Team Meeting with Mentor
| 2012-05-29 | 20:00 | 22:00 | 0 | 2 | Tham khảo tài liệu
| 2012-05-30 | 9:00 | 11:00 | 0 | 2 | Team Meeting
| 2012-05-30 | 19:00 | 22:30 | 0 | 3.5 | Chỉnh sửa SRS ver 1
| 2012-05-31 | 19:00 | 21:00 | 0 | 1 | Xem user case
| 2012-06-01 | 21:00 | 12:00 | 0 | 3 | Miêu tả user case
4 | 2012-06-04 | 21:00 | 12:00 | 0 | 3 | Fix user case
| 2012-06-05 | 20:00 | 12:00 | 0 | 4 | Fix user case
| 2012-06-06 | 20:00 | 12:00 | 0 | 4 | Xem giao diện mẫu fix mô tả user case
| 2012-06-07 | 21:00 | 23:00 | 0 | 3 | Xem SDS
5 | 2012-06-14 | 21:00 | 23:00 |  | 3 | Vẽ activity diagram
| 2012-06-15 | 21:00 | 12:00 | 0 | 3 | Làm SDS ver1
| 2012-06-16 | 9:00 | 11:30 | 0 | 2.5 | Team Meeting
| 2012-06-16 | 20:00 | 12:00 | 0 | 4 | Chỉnh sửa SDS
6 | 2012-06-17 | 20:00 | 12:00 | 0 | 4 | Mô tả activity diagram
| 2012-06-18 | 8:30 | 11:00 | 0 | 2.5 | Team Meeting
| 2012-06-18 | 19:00 | 20:30 | 0 | 1.5 | Mô tả activity diagram
| 2012-06-19 | 9:00 | 10:00 | 0 | 1 | Mô tả activity diagram
| 2012-06-19 | 20:00 | 12:00 | 0 | 4 | Fix activity diagram
| 2012-06-20 | 20:00 | 12:00 | 0 | 4 | Fix activity diagram
| 2010-06-23 | 13:00 | 17:00 | 0 | 4 | SDS ver 2
7 | 2012-06-25 | 8:00 | 11:30 | 0 | 3.5 | Xem tài liệu
| 2012-06-26 | 8:00 | 11:30 | 0 | 3.5 | Xem tài liệu
| 2012-06-27 | 3:00 | 3:30 | 0 | 0.5 | Team Meeting with Mentor
9 | 2012-07-11 | 19:00 | 23:00 | 0 | 4 | Fix SDS ver 2
| 2012-07-12 | 19:00 | 23:00 | 0 | 4 | Fix SDS ver 2
| 2012-07-13 | 19:00 | 23:00 | 0 | 4 | Fix SRS ver 1
| 2012-07-14 | 19:00 | 23:00 | 0 | 4 | Fix SRS ver 1
| 2012-07-15 | 19:00 | 23:00 | 0 | 4 | Fix SRS ver 1
10 | 2012-07-16 | 19:00 | 23:00 | 0 | 4 | Tham khảo tài liệu
| 2012-07-17 | 19:00 | 23:00 | 0 | 4 | Tham khảo tài liệu
| 2012-07-18 | 19:00 | 23:00 | 0 | 4 | Theo dỏi tiến độ dự án fix 2 bản SRS &SDS
| 2012-07-19 | 19:00 | 23:00 | 0 | 4 | Theo dỏi tiến độ dự án fix 2 bản SRS &SDS
| 2012-07-20 | 19:00 | 23:00 | 0 | 4 | Theo dỏi tiến độ dự án fix 2 bản SRS &SDS
| 2012-07-21 | 19:00 | 15:00 | 0 | 8 | Test case
| 2012-07-22 | 19:00 | 15:00 | 0 | 8 | Test case
11 | 2012-07-30 | 10:00 | 0:00 | 0 | 2 | Test case
| 2012-07-31 | 10:00 | 11:30 | 0 | 4 | Test case
| 2012-07-31 | 13:00 | 20:30 | 0 | 7.5 | Fix tài liệu
| 2012-07-31 | 21:30 | 23:30 | 0 | 2 | Fix tài liệu
| 2012-08-01 | 13:00 | 20:00 | 0 | 7 | Fix tài liệu
| 2012-08-02 | 9:00 | 11:00 | 0 | 2 | Team Meeting with Mentor
12 | 2012-08-06 | 8:00 | 0:00 | 0 | 4 | Meting
| 2012-08-07 | 13:00 | 20:00 | 0 | 7 | Fix tài liệu
| 2012-08-08 | 13:00 | 21:00 | 0 | 8 | Fix tài liệu
| 2012-08-09 | 9:00 | 0:00 | 0 | 2 | Team Meeting
| 15/8/2012 | PRESENTATION
|  |  |  | Total | 178.5
|  |  |  | AVG (hours/week) | 14.875

## Planned Weekly Effort W#4 (hidden)
Planned Weekly Effort W#4
Name: | Huy Huỳnh | Starting Date: |  | 2012-05-21
Course: | SEP | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27 | Total
| Task | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27
| Team Meetings | 2012-05-21: 0.5 | 0.5
| Research Document | [7 empty] | 2 | bar: 2012-05-21; 2012-05-24
| Team Home Work | 2 | 2 |  | 2 |  | 2 | 1 | 9
| Meetings with Mentor | 2012-05-21: 2 | 2
| Total | 5.5 | 2 | 0 | 3 | 0 | 2 | 1 | 13.5