## TimeLog
Time Recording Log For: POS Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Huy Huynh |  |  |  | Date: | 2012-05-14
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Inter. Time | Delta Time | Activity | Artifact | C | U | Plan and Schedule | #REF!
1 | 2012-05-18 | 22:30 | 12:00 | 0 | 1.5 | Kick off Project with Mentor |  |  |  | Architecture drivers | 11
[10 empty] | Architecture & Design | 72
[10 empty] | Class diagram and Database | 18
2 | 2012-05-21 | 21:00 | 23:00 | 0 | 2 | Team Meeting with Mentor |  |  |  | Coding | #REF!
| 2012-05-22 | 21:00 | 21:30 | 0 | 2 | Đọc comment của thầy Phụng
| 2012-05-23 | 21:00 | 22:30 | 0 | 1.5 | Xem Crystal Report |  |  |  | TOTAL | #REF!
[10 empty] | ON AVERAGE (hours/week) | #REF!
3 | 2012-05-28 | 9:00 | 11:00 | 0 | 2 | Team Meeting with Mentor
| 2012-05-29 | 20:00 | 22:00 | 0 | 2 | Research Architecture
| 2012-05-30 | 9:00 | 11:00 | 0 | 2 | Team Meeting
| 2012-05-30 | 19:00 | 20:30 | 0 | 1.5 | Research Architecture
| 2012-05-31 | 19:00 | 21:00 | 0 | 2 | Draw Static Perspective
| 2012-06-01 | 20:00 | 21:00 | 0 | 1 | Fix Static Perspective
4 | 2012-06-05 | 20:00 | 21:00 | 0 | 1 | Fix Static Perspective
| 2012-06-06 | 20:00 | 21:00 | 0 | 1 | Research Architecture
| 2012-06-07 | 21:00 | 23:00 | 0 | 2 | Fix Static Perspective
5 | 2012-06-15 | 13:00 | 16:00 | 0 | 3 | Draw C&C View
| 2012-06-16 | 9:00 | 11:30 | 0 | 2.5 | Team Meeting
| 2012-06-16 | 13:00 | 17:00 | 0 | 4 | Describe C&C View
6 | 2012-06-17 | 13:00 | 17:00 | 0 | 4 | Describe Module View
| 2012-06-18 | 8:30 | 11:00 | 0 | 2.5 | Team Meeting
| 2012-06-18 | 19:00 | 20:30 | 0 | 1.5 | Fix C&C View
| 2012-06-19 | 9:00 | 10:00 | 0 | 1 | Meeting with Mr.Huyen to review Module View and CC View | Module View - C&C View
| 2012-06-19 | 20:00 | 12:00 | 0 | 4 | Fix C&C View
| 2012-06-20 | 20:00 | 12:00 | 0 | 4 | Fix Module View
| 2010-06-23 | 13:00 | 17:00 | 0 | 4 | Research List View for ASP.Net
7 | 2012-06-26 | 3:00 | 3:30 | 0 | 0.5 | Team Meeting with Mentor
9 | 2012-07-11 | 19:00 | 23:00 | 0 | 4 | Research Architecture
| 2012-07-12 | 19:00 | 23:00 | 0 | 4 | Research Architecture
| 2012-07-13 | 19:00 | 23:00 | 0 | 4 | Research Architecture
| 2012-07-14 | 19:00 | 23:00 | 0 | 4 | Research Architecture
| 2012-07-15 | 19:00 | 23:00 | 0 | 4 | Fix C&C View
10 | 2012-07-16 | 19:00 | 23:00 | 0 | 4 | Draw C&C View Packet
| 2012-07-17 | 19:00 | 23:00 | 0 | 4 | Draw C&C View Packet
| 2012-07-18 | 19:00 | 23:00 | 0 | 4 | Fix Module View
| 2012-07-19 | 19:00 | 23:00 | 0 | 4 | Draw Use Style
| 2012-07-20 | 19:00 | 23:00 | 0 | 4 | Fix Use Style
| 2012-07-21 | 19:00 | 23:00 | 0 | 4 | Draw Mapping View
| 2012-07-22 | 19:00 | 23:00 | 0 | 4 | Fix Mapping View
| 2012-07-23 | 19:00 | 23:00 | 0 | 4 | Comment for C&C View
| 2012-07-24 | 19:00 | 23:00 | 0 | 4 | Comment for Module View
| 2012-07-25 | 19:00 | 23:00 | 0 | 4 | Review All view and Comment
| 2012-07-26 | 20:00 | 23:30 | 0 | 3.5 | Fix Database
| 2012-07-27 | 20:00 | 23:30 | 0 | 3.5 | Fix Store Procedure
| 2012-07-28 | 13:00 | 20:00 | 0 | 7 | Meeting with Giang Nguyen for coding Import Student Record function
| 2012-07-29 | 7:00 | 11:30 | 0 | 4.5 | Code Import Student Record function
| 2012-07-29 | 13:00 | 19:00 | 0 | 6 | Test and fix Import Student Record function
11 | 2012-07-30 | 10:00 | 0:00 | 0 | 2 | Meeting with Giang Nguyen for fixing Database
| 2012-07-30 | 13:00 | 20:30 | 0 | 7.5 | Meeting with Giang Nguyen for fixing Database and code Check Record function
| 2012-07-31 | 10:00 | 11:30 | 0 | 4 | Meeting with Giang Nguyen for fixing Add User function
| 2012-07-31 | 13:00 | 20:30 | 0 | 7.5 | Meeting with Giang Nguyen for code Check Record function
| 2012-07-31 | 21:30 | 23:30 | 0 | 2 | test and fix check record function
| 2012-08-01 | 13:00 | 20:00 | 0 | 7 | Meeting with Giang Nguyen for code View Log Function
| 2012-08-02 | 9:00 | 11:00 | 0 | 2 | Team Meeting with Mentor
| 2012-08-02 | 12:30 | 19:30 | 0 | 7 | Meeting with Giang Nguyen for code View Log Function and Export to Excel file
| 2012-08-03 | 13:00 | 20:00 | 0 | 7 | Meeting with Giang Nguyen for code giving permission for user
| 2012-08-03 | 22:00 | 23:30 | 0 | 1.5 | Test and fix giving permission for user
| 2012-08-04 | 14:00 | 20:00 | 0 | 6 | Fixing Database and fixing Check record function (assign receipt id to reciept)
| 2012-08-05 | 13:00 | 17:00 | 0 | 4 | Fixing Module View
12 | 2012-08-06 | 9:00 | 11:30 | 0 | 2.5 | Team Meeting
| 2012-08-06 | 14:00 | 17:00 | 0 | 3 | Code function Language
| 2012-08-06 | 19:30 | 22:30 | 0 | 3 | Code function Language
| 2012-08-07 | 13:00 | 20:00 | 0 | 7 | Meeting with Giang Nguyen for code function Statistics (Winform) and fix function view log
| 2012-08-07 | 22:00 | 0:30 | 0 | 2.5 | Code function Statistics (Winform)
|  | 9:00 | 11:30 | 0 | 2.5 | Meeting with Giang Nguyen for fix function Language
| 2012-08-08 | 13:00 | 21:00 | 0 | 8 | Meeting with Giang Nguyen for Code function Statistics (Winform) And fix function Statistics (WebForm)
| 2012-08-09 | 9:00 | 11:00 | 0 | 2 | Team Meeting
| 15/8/2012 | PRESENTATION
[5 empty] | 225 | 18.75

## Planned Weekly Effort W#4
Planned Weekly Effort W#4
Name: | Huy Huỳnh | Starting Date: |  | 2012-05-21
Course: | SEP | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27 | Total
| Task | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-26 | 2012-05-27
| Team Meetings | 2012-05-21: 0.5 | 0.5
| Research Document | [7 empty] | 2 | bar: 2012-05-21; 2012-05-24
| Team Home Work | 2 | 2 |  | 2 |  | 2 | 1 | 9
| Meetings with Mentor | 2012-05-21: 2 | 2
| Total | 5.5 | 2 | 0 | 3 | 0 | 2 | 1 | 13.5