## Risk List
Risk Analysis
Risk ID | Risk Title | Risk Description | Identified Date | Earliest Impact Date | Latest Impact Date | Risk Category | Risk Source | Impact to |  |  |  | Probability | Level | Exposure | Priority | Status | Mitigation Plan | Contigency Plan | Owner | Relevant Stakeholders | Become Issue? | Date Occurred
[8 empty] | Scope | Budget | Schedule | Quality
R-001 |  | The release time was delayed |  |  |  | Vendor |  | None | None | Catastrophic | None | 90% | High | 4.5 |  | Control |  |  |  | Mr Hieu To | No
R-002 |  | Project had been over budget |  |  |  | Budget |  | None | Catastrophic | None | None | 90% | High | 4.5 |  | Monitor |  |  |  | Mr Hieu To | No
R-003 |  | Lack of experience in new tools |  |  |  | Development Team |  | None | Significant | Catastrophic | Catastrophic | 50% | High | 2.5 |  | Monitor |  |  |  | Mr Hieu To | No
R-004 |  | Lack of human resource in some phase |  |  |  | Resource |  | None | Catastrophic | None | None | 50% | High | 2.5 |  | Avoid |  |  |  | Mr Hieu To | No
R-005 |  | Change requirements or addition requirement |  |  |  | Requirement |  | Catastrophic | Negligible | Critical | Negligible | 70% | High | 3.5 |  | Control |  |  |  | Mr Hieu To | No
R-006 |  | New technology need to use for project is complex |  |  |  | Technology |  | Marginal | None | Marginal | Critical | 30% | Medium | 1.2 |  | Control |  |  |  | Mr Hieu To | No
R-007 |  | Unforeseen changes in expenditure and/or income during the year |  |  |  | Budget |  | Catastrophic | Significant | Critical | Significant | 30% | Medium | 1.5 |  | Monitor |  |  |  | Mr Hieu To | No
R-008 |  | Length of time necessary to meet a milestone was stretched unexpected |  |  |  | Schedule |  | None | Marginal | Catastrophic | Significant | 50% | High | 2.5 |  | Control |  |  |  | Mr Hieu To | No
R-009 |  | Sponsor reduce their funding contribution |  |  |  | Customer |  | None | Critical | Significant | Negligible | 30% | Medium | 1.2 |  | Monitor |  |  |  | Mr Hieu To | No
R-010 |  | Project facilities location was moved to another place |  |  |  | Migration |  | None | Significant | Significant | Marginal | 10% | Low | 0.3 |  | Monitor |  |  |  | Mr Hieu To | No
R-011 |  | Wrong time estimation |  |  |  | Schedule |  | None | Significant | Catastrophic | Marginal | 50% | High | 2.5 |  | Monitor |  |  |  | Mr Hieu To | No
R-012 |  | Unexpected project scope expansions lead to stretch schedule |  |  |  | Schedule |  | Catastrophic | None | Catastrophic | Negligible | 30% | Medium | 1.5 |  | Control |  |  |  | Mr Hieu To | No
R-013 |  | Wrong budget estimation lead to cost overruns |  |  |  | Budget |  | None | Catastrophic | None | Marginal | 70% | High | 3.5 |  | Control |  |  |  | Mr Hieu To | No
R-014 |  | Unrealistic schedules lead to frustrated members |  |  |  | Schedule |  | None | None | Catastrophic | Critical | 50% | High | 2.5 |  | Monitor |  |  |  | Mr Hieu To | No
R-015 |  | Inexperience of project manager |  |  |  | Senior Management |  | None | None | Significant | Significant | 30% | Medium | 0.9 |  | Control |  |  |  | Mr Hieu To | No
R-016 |  | Inexperience of team members, lack of training |  |  |  | Resource |  | None | None | Significant | Critical | 30% | Medium | 1.2 |  | Monitor |  |  |  | Mr Hieu To | No
R-017 |  | Reorganization resulting in loss of team members |  |  |  | Resource |  | None | None | Significant | Critical | 30% | Medium | 1.2 |  | Monitor |  |  |  | Mr Hieu To | No
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
Note on Q7: Hieu To: 1. Acceptance: Acknowledgment of risk but not taking any action 2. Monitor: Watching and periodically re-evaluating the risk 3. Control: Taking active action to mitigate risk 4. Transfer: Reallocating risk to other entity. Do not consider it any more 5. Avoid: Changing or lowering requirements while still meeting the user's needs 6. Retired: The time to impact is passed. Do not consider it any more 7. Occur: Risk occured

## Risk Glossary
Risk Taxonomy
| Risk Category | Risk Source
| Technical risk | Requirement
| Resource risks | Design
| Process risks | Code & Unit Test
| Business risks | Integration & Test
| Customer risks | Engineering Specialties
| Others | Development Process
Development System
Management Process
Management Methods
Work Environment
Resources
Contract
Schedule
Budget
Marketing
Program Interfaces
Status | Name | Description
A | Acknowledgment | Acknowledgment of risk but not taking any action
M | Monitor | Watching and periodically re-evaluating the risk
C | Control | Taking active action to mitigate risk
T | Transfer | Reallocating risk to other entity. Do not consider it any more
V | Avoid | Changing or lowering requirements while still meeting the user's needs
R | Retired | The time to impact is passed. Do not consider it any more
O | Occur | Risk occured
# | Probability | Meaning
1 | 10% | Remote
2 | 30% | Unlikely
3 | 50% | Likely
4 | 70% | High Likely
5 | 90% | Near certainty
| Consequence | Value
| None | 0
| Negligible | 1
| Marginal | 2
| Significant | 3
| Critical | 4
| Catastrophic | 5
| Probability | Consequence
|  | 1 | 2 | 3 | 4 | 5
| 10% | Low | Low | Low | Low | Low
| 30% | Low | Low | Medium | Medium | Medium
| 50% | Low | Medium | Medium | Medium | High
| 70% | Low | Medium | Medium | High | High
| 90% | Medium | Medium | High | High | High

## Top 10 Risk
Risk Analysis
Risk ID | Risk Title | Risk Description | Identified Date | Earliest Impact Date | Latest Impact Date | Risk Category | Risk Source | Impact to |  |  |  | Probability | Level | Exposure | Priority | Status | Mitigation Plan | Contigency Plan | Owner | Relevant Stakeholders | Become Issue? | Date Occurred
[8 empty] | Scope | Budget | Schedule | Quality
R-001 |  | The release time was delayed |  |  |  | Vendor |  | None | None | Catastrophic | None | 90% | High | 4.5 |  | Control | Always follow schedule keep track and make sure the release time wasn't delayed |  |  | Mr Hieu To | No
R-002 |  | Project had been over budget |  |  |  | Budget |  | None | Catastrophic | None | None | 90% | High | 4.5 |  | Monitor | Always follow schedule keep track and make sure the release time wasn't delayed |  |  | Mr Hieu To | No
R-003 |  | Lack of experience in new tools |  |  |  | Development Team |  | None | Significant | Catastrophic | Catastrophic | 50% | High | 2.5 |  | Monitor | Training team members before project begin about new tool and technology |  |  | Mr Hieu To | No
R-004 |  | Lack of human resource in some phase |  |  |  | Resource |  | None | Catastrophic | None | None | 50% | High | 2.5 |  | Avoid | Keep the schedule update and make a good WBS to allocate resource well |  |  | Mr Hieu To | No
R-005 |  | Change requirements or addition requirement |  |  |  | Requirement |  | Catastrophic | Negligible | Critical | Negligible | 70% | High | 3.5 |  | Control | Make a good Change management process to control change. |  |  | Mr Hieu To | No
R-008 |  | Length of time necessary to meet a milestone was stretched unexpected |  |  |  | Schedule |  | None | Marginal | Catastrophic | Significant | 50% | High | 2.5 |  | Control | Keep track with schedule to make sure the tasks are going well and on time |  |  | Mr Hieu To | No
R-011 |  | Wrong time estimation |  |  |  | Schedule |  | None | Significant | Catastrophic | Marginal | 50% | High | 2.5 |  | Monitor | Make a good schedule and always update it to reestimate the time. |  |  | Mr Hieu To | No
R-012 |  | Unexpected project scope expansions lead to stretch schedule |  |  |  | Schedule |  | Catastrophic | None | Catastrophic | Negligible | 30% | Medium | 1.5 |  | Control | Negotiation with stakeholder about the conclution of scope expansions and make a right decision |  |  | Mr Hieu To | No
R-013 |  | Wrong budget estimation lead to cost overruns |  |  |  | Budget |  | None | Catastrophic | None | Marginal | 70% | High | 3.5 |  | Monitor | Negotiate with customer for the contribute budget for the project |  |  | Mr Hieu To | No
R-014 |  | Unrealistic schedules lead to frustrated members |  |  |  | Schedule |  | None | None | Catastrophic | Critical | 50% | High | 2.5 |  | Monitor | Always check the schedule and collect comment from members to make sure the schedule is not unrealistic |  |  | Mr Hieu To | No
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
[13 empty] | #N/A | #N/A
Note on Q7: Hieu To: 1. Acceptance: Acknowledgment of risk but not taking any action 2. Monitor: Watching and periodically re-evaluating the risk 3. Control: Taking active action to mitigate risk 4. Transfer: Reallocating risk to other entity. Do not consider it any more 5. Avoid: Changing or lowering requirements while still meeting the user's needs 6. Retired: The time to impact is passed. Do not consider it any more 7. Occur: Risk occured