## Risk Glossary
Risk Taxonomy
| Risk Category | Risk Source
| Technical risk | Requirement
| Resource risks | Design
| Process risks | Code & Unit Test
| Business risks | Integration & Test
| Customer risks | Engineering Specialties
| Others | Development Process
Development System
Management Process
Management Methods
Work Environment
Resources
Contract
Schedule
Budget
Marketing
Program Interfaces
Status | Name | Description
A | Acknowledgment | Acknowledgment of risk but not taking any action
M | Monitor | Watching and periodically re-evaluating the risk
C | Control | Taking active action to mitigate risk
T | Transfer | Reallocating risk to other entity. Do not consider it any more
V | Avoid | Changing or lowering requirements while still meeting the user's needs
R | Retired | The time to impact is passed. Do not consider it any more
O | Occur | Risk occured
# | Probability | Meaning
1 | 10% | Remote
2 | 30% | Unlikely
3 | 50% | Likely
4 | 70% | High Likely
5 | 90% | Near certainty
| Consequence | Value
| None | 0
| Negligible | 1
| Marginal | 2
| Significant | 3
| Critical | 4
| Catastrophic | 5
| Probability | Consequence
|  | 1 | 2 | 3 | 4 | 5
| 10% | Low | Low | Low | Low | Low
| 30% | Low | Low | Medium | Medium | Medium
| 50% | Low | Medium | Medium | Medium | High
| 70% | Low | Medium | Medium | High | High
| 90% | Medium | Medium | High | High | High

## Risk List
Risk ID | Risk Statement
R01 | Cannot build a product of the size specified in the time allocated
R02 | Time for training resource is not enough
R03 | Perform the task more difficult than originally estimated
R04 | Allocation of time and human resource in the schedule is not reasonable
R05 | Integration with other systems of users fail
R06 | Technical development is difficult to apply
R07 | Development tools do not work as expected
R08 | Lack of equipment to support development process
R09 | Install system in customer 's hardware fail
R10 | Team members are not afford required to development product
R11 | Performance of team members is reduced
R12 | The product does not meet what customers need
R13 | The release product appear influence error
R14 | Quality of release product is not as expected
R15 | Not managing change effective.
R16 | Those tools using in SRM project may not use effectivelly
R17 | These are many formal documents deliverables hard to develop and manage
R18 | Members can be leave work that is performed at the middle of the project
R19 | Process is applied that is not really appropriate.
R20 | Difficulity in module intergration with each other.
R21 | Resources that support does not insufficent in order to develop the project
R22 | Some developer has lack of experiences in coding
R23 | Project Manager does not skill about planning and monitor the project
R24 | Team members disagree with others on work during project implementation
R25 | Requirement Engineer Lack of ability in analysis requirement
R26 | Difficulity in apply the software development process
R27 | The user infaces of programs that are too difficult for use
R28 | Team members has conflict with each other
R29 | Conflict with other Project

## TOP_Risk List
Risk List
Date Open | 2012-10-07
By: | Thanh Giang and HIT Team Members
Risk Analysis
Risk ID | Risk Title | Risk Description | Identified Date | Earliest Impact Date | Latest Impact Date | Risk Category | Risk Source | Impact to |  |  |  | Probability | Level | Exposure | Priority | Status | Mitigation Plan | Contigency Plan | Owner | Relevant Stakeholders | Become Issue? | Date Occurred
[8 empty] | Scope | Budget | Schedule | Quality
R18 | Employee Turnover | Members can be leave work that is performed at the middle of the project | 20/5/2012 |  |  | Resource risks | Resources | Marginal | Significant | Critical | Critical | 70% | High | 2.275 | High | Control | All work are performed by staff need to manage. It must be document in order to ensure that word still be continue when have a turn over staff. Increased collaboration and information sharing on the team. | Additional human resources in order to ensure that work must be continue. However, person who assign must be have ability solve the problem. | Thanh Giang
R19 | Process | Process is applied that is not really appropriate. | 20/5/2012 |  |  | Process risks | Management Process | Critical | Critical | Critical | Catastrophic | 50% | High | 2.125 | High | Control | Modify the process for appropriate of team and assign roles and responsibilities | a meeting quickly to find the problem and give a modify for process. Progress must be made faster | Thanh Giang
R26 | Code intergration | Difficulity in module intergration with each other. | 20/5/2012 |  |  | Technical risk | Integration & Test | Critical | Significant | Critical | Catastrophic | 50% | High | 2 | High | Control | Apply continus intergration system to manage code intergration. Set up an effective SCM(software configuration management) early in project. | Developers should be work together in order to synchronize and intergrate it better | Thanh Giang
R21 | Insufficient resources | Resources that support does not insufficent in order to develop the project | 20/5/2012 |  |  | Resource risks | Resources | Critical | Critical | Critical | Critical | 50% | Medium | 2 | Medium | Control | Resource planning need to perform early in the project. It need to analysis detail and ensure resource are available |  | Thanh Giang
R22 | Risk of Programming | Some developer has lack of experiences in coding | 20/5/2012 |  |  | Resource risks | Resources | None | Negligible | Negligible | Negligible | 30% | Low | 2 | Low | Control | Training about coding and develop class for team members |  | Thanh Giang
R23 | Lack of effective project management skill | Project Manager does not skill about planning and monitor the project | 20/5/2012 |  |  | Resource risks | Resources | Significant | Critical | Critical | Critical | 50% | Medium | 1.875 | Medium | Control | person who assigned in PM must have experience and may be train in order to manage the project |  | Thanh Giang
R24 | Conflicts in project teams | Team members disagree with others on work during project implementation | 20/5/2012 |  |  | Technical risk | Code & Unit Test | Significant | Significant | Significant | Critical | 50% | Medium | 1.625 | Medium | Control | Improve work environment and encourage team member comunicatie with each others. |  | Thanh Giang
R04 | Schedule | Allocation of time and human resource in the schedule is not reasonable | 20/5/2012 |  |  | Business risks | Schedule | Critical | Critical | Catastrophic | Critical | 30% | Medium | 1.275 | Medium | Control | Estimation shoul be planed early in the project by using earn value tool. It include estimate the schedule and its relevant. Re-allocate resources and time for the rest phase to in time for releasing the product. Or add resoures in the rest time to release the product in time | Mitigation: | Thanh Giang
R25 | Analysis requirement | Requirement Engineer Lack of ability in analysis requirement | 20/5/2012 |  |  | Resource risks | Resources | Critical | Significant | Critical | Catastrophic | 30% | Medium | 1.2 | Medium | Control | Requirement Engineer must be document and detail analysis them. Apply some method to analysis |  | Thanh Giang
R26 | Process | Difficulity in apply the software development process | 20/5/2012 |  |  | Process risks | Management Process | Significant | Critical | Critical | Critical | 30% | Medium | 1.125 | Medium | Control | Team members need to train about the process that will be applied, monitor and control all phase during the project |  | Thanh Giang
R27 | Usability | The user infaces of programs that are too difficult for use | 20/5/2012 |  |  | Technical risk | Program Interfaces | None | Negligible | Negligible | Negligible | 50% | Low | 0.375 | Low | Control | Need to make the surveys in order to collect the requirement about user interface |  | Thanh Giang
R28 | Communication | Team members has conflict with each other | 20/5/2012 |  |  | Resource risks | Resources | Significant | Significant | Significant | Significant | 10% | Low | 0.3 | Low | Control | Communication channel need to improve and enhancement. Make condition for people in order to participate in the entertainment activities. |  | Thanh Giang
R12 | Communication | The product does not meet what customers need | 20/5/2012 |  |  | Customer risks | Requirement |  |  | Critial |  | 30% |  | 0.21 | Medium | Control | Mitigation: negotiate with customer |  | Thanh Giang
R04 | Members | Allocation of time and human resource in the schedule is not reasonable | 20/5/2012 |  |  | Schedule risks | Development Process |  |  | Significant |  | 30% |  | 0.15 | Medium | Control | Mitigation: Re-allocate resources and time for the rest phase to in time for releasing the product. Or add resoures in the rest time to release the product in time |  | Thanh Giang
R13 | Product | Theare are some major bugs in the released product | 20/5/2012 |  |  | Technical risk | Integration & Test |  |  | Catastrophic |  | 30% |  | 0.27 | Medium | Control | Mitigation: negotiate with customer to fix that bugs Prevention: Integration and test phase should be done carefully |  | Thanh Giang
R11 | Motivation | Performance of team members is reduced | 20/5/2012 |  |  | Resource risks | Resources |  |  | Marginal |  | 50% |  | 0.15 | Medium | Control | Mitigation: have awards or punishment in team to motivate team morale, set trainning meetings to improve ability of weak team members Prevention: Set up rules of team as soon as |  | Thanh Giang
R17 | Document | These are many formal documents deliverables hard to develop and manage | 20/5/2012 |  |  | Process risks | Development Process |  |  | Marginal |  | 30% |  | 0.09 | Low | Control | Prevention: Built a process to manage document - Unique number for each document - Assign person who responsibility to collect and manage document - Release document after artifact as SRS, SDS, etc. |  | Thanh Giang
R10 | Skills | Team members are not enough required ability to development product | 20/5/2012 |  |  | Resource risks | Resources |  |  | Marginal |  | 50% |  | 0.15 | Medium | Control | Mitigation: set up quickly training courses to improve ability of weak team members |  | Thanh Giang
R05 | Integration | Integration with other systems of users fail | 20/5/2012 |  |  | Technical risk | Integration & Test |  |  | Marginal |  | 10% |  | 0.03 | Low | Control | Mitigation: Modify the design of product |  | Thanh Giang
R29 | Other Project | Conflict with other Project | 20/5/2012 |  |  | Process risks | Development Process |  |  | Critial |  | 90% |  | 2 | High | Control | Have an overview for both projects then assign task and schedule fixly |  | Thanh Giang