## SAD
Time Recording Log For: POS Project
SUMMARY: TIME FOR DOING PROJECT
Name: | Huy Huynh |  |  |  | Date: | 2012-05-14
[10 empty] | WORKS/ARTIFACTS | HOURS
Week | Date | Start | Stop | Inter. Time | Delta Time | Activity | Artifact | C | U | Plan and Schedule | 23
1 | 2012-05-14 | 10:30 | 0:00 | 0 | 1 | Kick off Team meeting |  |  |  | Architecture drivers | 11
| 2012-05-16 | 20:30 | 12:00 | 0 | 3.5 | Team Meeting | Final_Project_Guidelines |  |  | Architecture & Design | 36
| 2012-05-17 | 20:30 | 21:30 | 0 | 1.5 | List high level functional, constraints, Quality Attributes on Assignment 01.
| 2012-05-18 | 20:30 | 12:00 | 0 | 3.5 | Team Meeting
| 2012-05-19 | 19:30 | 21:00 | 0 | 1.5 | Research ACDM
[10 empty] | Class diagram and Database | 41
[10 empty] | Coding | 41
| 2012-05-22 | 21:00 | 23:00 | 0 | 2 | Research Module View and N-Tier. |  |  |  | TOTAL | 152
[10 empty] | ON AVERAGE (hours/week) | 19
2 | 2012-05-23 | 19:00 | 12:00 | 0 | 5 | Research & Draw Module View for MVC Framework (Draft)
| 2012-05-24 | 20:00 | 22:00 | 0 | 2 | Re-Draw Module View
| 2012-05-28 | 20:30 | 22:30 | 0 | 2 | Re-Draw Module View
| 2012-05-29 | 13:00 | 17:00 | 0 | 4 | Design Module View
| 2012-05-29 | 21:00 | 12:00 | 0 | 3 | Design Module View
| 2012-05-31 | 14:00 | 17:00 | 0 | 3 | Research ASP.NET MVC
| 2012-06-06 | 21:00 | 22:30 | 0 | 1.5 | Research ASP.NET MVC
4
| 2012-06-07 | 15:00 | 16:00 | 0 | 1 | Research ASP.NET MVC
| 2012-06-09 | 13:00 | 14:00 | 0 | 2 | Fix Module View
| 2012-06-09 | 20:00 | 22:00 | 0 | 2 | Fix Module View
5 | 2012-06-15 | 13:00 | 16:00 | 0 | 3 | Research Entity Framework
6 | 2012-06-17 | 13:00 | 17:00 | 0 | 4 | Draw C&C View
| 2012-06-18 | 8:30 | 11:00 | 0 | 2.5 | Team Meeting
| 2012-06-19 | 9:00 | 10:00 | 0 | 1 | Meeting with Mr.Huyen to review Module View and CC View | Module View - C&C View
| 2012-06-19 | 13:00 | 18:00 | 0 | 5 | Fix Module View
| 2012-06-20 | 13:00 | 18:00 | 0 | 5 | Fix C&C View
| 2012-06-21 | 13:00 | 14:30 | 0 | 1.5 | Write Technical Constrains
| 2010-06-22 | 13:00 | 18:00 | 0 | 5 | Meeting with Giang Nguyen for coding (Database +Project)
| 2010-06-23 | 13:00 | 17:00 | 0 | 4 | Research List View for ASP.Net
| 2012-06-24 | 13:00 | 17:00 | 0 | 4 | Research List View for ASP.Net
7 | 2012-06-25 | 9:00 | 11:00 | 0 | 2 | Meeting with Giang Nguyen for coding (GUI)
| 2012-06-25 | 13:00 | 18:00 | 0 | 5 | Meeting with Giang Nguyen for coding (fixing primary key problem)
| 2012-06-26 | 9:00 | 11:00 | 0 | 2 | Team Meeting
| 2012-06-26 | 13:00 | 15:00 | 0 | 2 | Meeting with Giang Nguyen for coding (Fix Store Procedure)
| 2012-06-26 | 16:00 | 17:30 | 0 | 1.5 | Meeting with Giang Nguyen for coding (Research View Model)
| 2012-06-26 | 19:00 | 22:00 | 0 | 3 | Fixing Database
| 2012-06-27 | 13:00 | 18:00 | 0 | 5 | Meeting with Giang Nguyen for coding (Research function searching and return the result on recent page)
| 2012-06-28 | 13:00 | 17:00 | 0 | 4 | Meeting with Giang Nguyen for coding (Multiple button problem)
| 2012-06-28 | 20:00 | 22:00 | 0 | 2 | Design a work flow for pay bill
| 2012-06-29 | 13:00 | 19:00 | 0 | 6 | Meeting with Giang Nguyen for coding (Show popup)
| 2012-06-30 | 9:00 | 11:00 | 0 | 2 | Team Meeting
| 2012-06-30 | 11:59 | 20:00 | 0 | 8 | Meeting with Giang Nguyen for coding (Fix Architecture (Data Model), Add Customer, Show Customer, Search Customer)
| 2012-07-01 | 13:00 | 17:00 | 0 | 4 | Fix Architecture (Module View & C&C View)
8 | 2012-07-02 | 13:00 | 19:00 | 0 | 6 | Meeting with Giang Nguyen for coding (Sale function)
| 2012-07-02 | 21:00 | 23:30 | 0 | 2.5 | Fix Architecture (Module View & C&C View)
| 2012-07-03 | 9:00 | 11:00 | 0 | 2 | Team Meeting: Review architecture document
| 2012-07-03 | 13:00 | 20:00 | 0 | 7 | Meeting with Giang Nguyen for coding (Sale function)
| 2012-07-03 | 21:30 | 23:30 | 0 | 2 | Fix Architecture (Module View & C&C View)
| 2012-07-04 | 9:00 | 11:00 | 0 | 2 | Team Meeting: Review architecture document
| 2012-07-04 | 13:00 | 19:00 | 0 | 6 | Meeting with Giang Nguyen for coding (Sale function)
| 2012-07-05 | 9:00 | 11:00 | 0 | 2 | Team Meeting: Review architecture document
| 2012-07-05 | 16:00 | 23:00 | 0 | 7 | Fix C&C View, Module View, Draw View Mapping, Decision design C&C View, Decision design Module View, Architecture Decision Design
9
| 2010-07-08 | COME BACK VIET NAM